## Slide 1
Wave Heating and Current Drive TSG:
XMP for Recomissioning the HHFW System
R.J. Perkins, J. C. Hosea
Theory & Modeling: N. Bertelli
NSTX-U
Supported by
Culham Sci Ctr
York U
Chubu U
Fukui U
Hiroshima U
Hyogo U
Kyoto U
Kyushu U
Kyushu Tokai U
NIFS
Niigata U
U Tokyo
JAEA
Inst for Nucl Res, Kiev
Ioffe Inst
TRINITI
Chonbuk Natl U
NFRI
KAIST
POSTECH
Seoul Natl U
ASIPP
CIEMAT
FOM Inst DIFFER
ENEA, Frascati
CEA, Cadarache
IPP, Jülich
IPP, Garching
ASCR, Czech Rep
NSTX-U Pre-Forum Meeting 1
December 16th, 2014
PPPL
V1.0
Coll of Wm & Mary
Columbia U
CompX
General Atomics
FIU
INL
Johns Hopkins U
LANL
LLNL
Lodestar
MIT
Lehigh U
Nova Photonics
ORNL
PPPL
Princeton U
Purdue U
SNL
Think Tank, Inc.
UC Davis
UC Irvine
UCLA
UCSD
U Colorado
U Illinois
U Maryland
U Rochester
U Tennessee
U Tulsa
U Washington
U Wisconsin
X Science LLC

## Slide 2
Complete transmission and matching hookups:
  Jan Finish loops
  Feb Hookup to loops, set decouplers, match vac from RFE
Complete source assembly and testing
  Feb Complete source assembly and test into dummy load
  March Labview updates for power/phase, EPICs system control
NSTX-U TC & RFE diagnostics re-commissioning
  March Into MDSplus
Conditioning of antenna
  April Vacuum conditioning
  May Plasma conditioning
Prepare diagnostics for supporting HHFW studies
  May Complete coaxial Langmuir probe electronic hookups and connect to central computer (MDS plus)
  May IR camera commissioning
  May ORNL Reflectometer, probe, etc. reactivation
  May RF probes at Bay J installation, hookup, commissioning
Research Plasma Operation
14 Run Weeks
Nov. 2014
Dec. 2014
Jan. 2015
Feb. 2015
Mar. 2015
Apr. 2015
May 2015
Jun. 2015
Sep. 2015
Jul. 2015
Aug 2015
Bakeout
ISTP / Comm
CD4
Nominal HHFW commissioning schedule for FY2015

## Slide 3
XMP026: Bring HHFW System online and operate into plasma
Evaluate performance and condition antenna to maximum voltage
  Verify phase and amplitude control, arc control, and plasma current inhibit
  Compare voltage limits and performance in multiple plasma configurations
  Monitor plasma heating utilizing magnetics and Thomson scattering
Run XMP for two days followed by three days of HHFW experiments
Need to evaluate heat load of 2nd NB on HHFW limiter
  Both with and without applied HHFW power
If possible, evaluate voltage standoff before and after lithium/boron conditioning

## Slide 4
Lead Author(s) | Title | Collaborating TSG
G. Taylor | Low Plasma Current Fully Non-Inductive HHFW H-Mode | Solenoid-Free Start-Up
G. Taylor | HHFW Ramp Up of Inductively Initiated Plasma from 250 to 400 kA | 
G. Taylor | HHFW Heating of CHI-initiated Plasma | Solenoid-Free Start-Up
J. Hosea R. Perkins | RF Heating at Divertor/SOL Regions | 
N. Bertelli M. Podesta B. LeBlanc | HHFW Absorption in NBI-Heated Plasmas | Energetic Particles
J. Hosea R. Perkins | Study HHFW Power Coupling Versus ELM Activity | 
J. Hosea | Turbulence Characteristics for HHFW Saturated Stored Energy versus RF Power | Transport and Turbulence
M. Podesta | Clamping of Edge Rotation by HHFW | 
Preliminary outline of HHFW experiments