## Slide 1: Plans for Diagnostic Removals, Storage, and Re-installations during NSTX Upgrade Outage
B. Stratton
NSTX Team Meeting
9/13/2011

## Slide 2: Summary of the Plan
See Erik Perry’s presentation at Upgrade FDR for overview of Test Cell activities during outage.
Erik will be the manager of the construction activities in the TC.
Joe Winston will coordinate and be responsible for for diagnostic removals and re-installations with help from Lane Roquemore.
Diagnostic removals will be performed by the diagnostic technicians, machine technicians, and physicists (as needed).
Near-term plan: complete MSE-LIF commissioning, MPTS testing, etc. TC will be open for general access until Oct. 14.
Until Oct. 14: Document diagnostic installations with photographs and labeling of diagnostic hardware on and near the machine. Some diagnostics can be removed.
2

## Slide 3
The vacuum vessel will be vented about Sept. 19. No vessel entry until well into the outage.
On Oct. 17: the power to the TC will be disconnected and temporary power to be used during construction will be connected (outlets and lighting).
After Oct. 17: only construction personnel with the required safety training will be permitted in the TC on a routine basis. Personnel accessing the TC will be briefed on hazards each morning. Non-construction personnel will be permitted access into the TC for specific tasks by pre-arrangement with Erik Perry or Joe Winston.
Entry into the test cell will require a written procedure for the work to be done and the procedure will need to be reviewed and approved by the Work Control Center (WCC). The WCC will schedule when the work can occur.
3

## Slide 4
Ist month of the outage: (starting mid-October), the cable tray at the top of the machine will be removed, RF piping within 10 feet of the vacuum vessel will be removed, the new 118 foot elevation platform on the west side of the machine will be installed, and removal of racks that will be moved will start. Diagnostics on the top and bottom of the machine will be removed.
2nd and 3rd months: rack removals will continue, diagnostic hardware will be removed from Bays J, K, and L.
Cables, tubing and optical fibers will be coiled up as far back as needed to provide space for construction work and to ensure that they are well protected. This will be the case everywhere around the machine. Cable and fiber ends will be protected by enclosures to prevent damage.
4

## Slide 5
Diagnostic removals will then proceed to other areas of the machine.
Later in the outage, diagnostic re-installations will take place as construction work is completed in specific areas of the machine.
Diagnostic removals will be done according to procedures that will be written for each area of the machine. Joe Winston will coordinate the execution of the procedures. A generic removal procedure will be used if a specific procedure has not been provided.
Diagnostic hardware will be stored in the Upper and Lower DARMs. Specially-built crates will be used to protect the hardware and to keep items that belong to each diagnostic together. Large items can be stored in the TFTR basement.
5

## Slide 6: Near-Term Plan
Lane Roquemore is organizing the effort to document the existing diagnostic installations with photographs and labels. This will be done by Tom Holoman, Doug LaBrie, and Gus Smalley.
Doug will be the point of contact for this work while Lane is on vacation until Oct. 3. Doug will be contacting you to get detailed information about your systems. Please work with him to provide the needed information.
Please contact Doug directly if you would like to remove something from the machine in the near future.
If you have questions about this process, please contact Brent Stratton or Erik Perry.
6