## Sheet1
|  | Accumulated FY | 41 | Cumulative
Date | TSG | Run Time (days) | days | shots | Plasmas | TSG | Comments
2010-05-27 | ASC | 0.17073 | 0.17073 | 7 | 7 |  | XP-1003. Combined X-point height and OSP control
2010-05-28 | ASC | 0.87805 | 0.70732 | 36 | 29 |  | XP-1003. Combined X-point height and OSP control
2010-06-16 | ASC | 1.6585 | 0.78049 | 68 | 32 |  | XP-1003. Combined X-point height and OSP control
2010-06-28 | ASC | 2 | 0.34146 | 82 | 14 |  | XP-1003. Combined X-point height and OSP control
2010-06-29 | ASC | 2.4634 | 0.46341 | 101 | 19 | done | XP-1003 Combined X-point height and OSP control
2010-04-09 | ASC | 0.58537 | 0.58537 | 24 | 24 |  | XP-1004. Application of early error field correction to advanced scenarios
2010-06-01 | ASC | 1.7805 | 1.1951 | 73 | 49 | done | XP-1004. Application of early error field correction to advanced scenarios
2010-06-16 | ASC | 0.46341 | 0.46341 | 19 | 19 | done | XP-1005. Some impurity reduction, but not a silver bullet
2010-09-03 | ASC | 1.2195 | 1.2195 | 50 | 50 | done | XP-1006. High-kappa Neutral Beam Heated Scenarios with Improved Control and LLD
2010-09-13 | ASC | 0.5122 | 0.5122 | 21 | 21 |  | XP-1025. Synergistic effects between 3D fields and vertical jogs in ELM pacing
2010-09-21 | ASC | 1.2195 | 0.70732 | 50 | 29 | done | XP-1025. Extended database of 3-D fields & jogs for ELM pacing
2010-08-02 | ASC | 0.17073 | 0.17073 | 7 | 7 |  | XP-1058. Impact of Outer Squareness on High-Kappa
2010-08-03 | ASC | 0.58537 | 0.41463 | 24 | 17 |  | XP-1058. Impact of Outer Squareness on High-Kappa
2010-09-02 | ASC | 1.0488 | 0.46341 | 43 | 19 |  | XP-1058. Impact of Outer Squareness on High-Kappa
2010-09-22 | ASC | 1.4878 | 0.43902 | 61 | 18 | done | XP-1058. PF4/PF5 shots were less stable than PF5 shots?
2010-06-03 | ASC | 0.60976 | 0.60976 | 25 | 25 |  | XP-1064. EPH modes, but not much luck controlling them
2010-06-04 | ASC | 0.92683 | 0.31707 | 38 | 13 |  | XP-1064. still no luck
2010-09-22 | ASC | 1.5122 | 0.58537 | 62 | 24 | done | XP-1064. Many EPH, but couldn't hold them.
2010-09-21 | ASC | 0.19512 | 0.19512 | 8 | 8 | done | XP-1069. Measure pedestal fluctuations as ELMs suppressed w/lithium
|  | 10.3415 | 10.3415 | 424 | 424 | 8 | Total ASC
2010-06-03 | ASC/ITER | 0.43902 | 0.43902 | 18 | 18 | done | XP-1027. No impurity control with sub-ELM RMPs
|  | 10.7805 | 10.7805 | 442 | 442 | 9 | Total ASC+ITER
2010-08-27 | BP | 0.26829 | 0.26829 | 11 | 11 |  | XP-1026. Short day for Mid-Run Mtg. Missed shots on TOR/COM/NB
2010-08-30 | BP | 1.1951 | 0.92683 | 49 | 38 | done | XP-1026. 3-D fields perturbed heat flux profiles. Done.
2010-06-04 | BP | 0.78049 | 0.78049 | 32 | 32 |  | XP-1043. Good first day with fast, 2-color camera
2010-06-15 | BP | 1.9512 | 1.1707 | 80 | 48 |  | XP-1043 BES data and confinement scaling with Btor
2010-08-16 | BP | 2.9512 | 1 | 121 | 41 |  | XP-1043. Delay for Phys Plan. Missed shots on COM/PF1AL limits (5)
2010-08-17 | BP | 3.8049 | 0.85366 | 156 | 35 |  | XP-1043 to 7PM. Down for LITER/TOR (Vac PLC). Missed shots on COM
2010-09-20 | BP | 4.9268 | 1.122 | 202 | 46 |  | XP-1043. CA for DIAG. Down for COM. Missed shots on Aborts/COM
2010-09-24 | BP | 5.4146 | 0.4878 | 222 | 20 | done | XP-1043. Finished drsep scan for divertor heat flux profiles (Bay K LITER aligned)
2010-06-30 | BP | 1.0488 | 1.0488 | 43 | 43 |  | XP-1044.
2010-07-28 | BP | 1.439 | 0.39024 | 59 | 16 | done | XP-1044. Scaling of pedestal heights, looking for high pedestal. done
2010-08-20 | BP | 0.53659 | 0.53659 | 22 | 22 |  | XP-1045 Two-coil snowflake
2010-08-20 | BP | 0.78049 | 0.2439 | 32 | 10 |  | XP-1045 (Boedo fast probe)
2010-08-03 | BP | 1.3415 | 0.56098 | 55 | 23 |  | XP-1045 more snowflakes
2010-08-26 | BP | 2.122 | 0.78049 | 87 | 32 |  | XP-1045 Three-coil snowflake from low triangularity
2010-09-20 | BP | 3.2439 | 1.122 | 133 | 46 | done | XP-1045. Snowflakes made by starting w/fiducial (Hi triangularity)
2010-07-28 | BP | 0.5122 | 0.5122 | 21 | 21 |  | XP-1046. The effect of 3-D fields on divertor profiles
2010-08-26 | BP | 1.122 | 0.60976 | 46 | 25 | done | XP-1046 The effect of 3-D fields on divertor profiles
2010-08-17 | BP | 0.70732 | 0.70732 | 29 | 29 | done | XP-1048 Park, RMPs & ELMs
2010-09-01 | BP | 0.46341 | 0.46341 | 19 | 19 | done | XP-1051. Test of LLD Electrodes for SOL Control
|  | 13.5854 | 13.5854 | 557 | 557 | 7 | Total BP
2010-04-02 | LR | 0.85366 | 0.85366 | 35 | 35 |  | XP-1000. LLD Commisioning
2010-04-05 | LR | 1.7073 | 0.85366 | 70 | 35 |  | XP-1000. LLD Commisioning
2010-04-06 | LR | 2.3415 | 0.63415 | 96 | 26 |  | XP-1000. LLD Commisioning
2010-04-07 | LR | 3.4146 | 1.0732 | 140 | 44 |  | XP-1000. LLD Heat before startup. Down for COM. Missed shots on COM/ECS
2010-04-08 | LR | 4.439 | 1.0244 | 182 | 42 | done | XP-1000. LLD Heated to 320º, no pumping
2010-08-11 | LR | 0.5122 | 0.5122 | 21 | 21 |  | XP-1001. LLD Pumping Group XP
2010-08-13 | LR | 1.0732 | 0.56098 | 44 | 23 | done | XP-1001. LLD Pumping Group XP
2010-06-21 | LR | 0.82927 | 0.82927 | 34 | 34 |  | XP-1002. Core impurity density and Prad reduction w/variations in LLD divertor conditions
2010-08-31 | LR | 1.5122 | 0.68293 | 62 | 28 | done | XP-1002 Core impurity density and Prad reduction w/variations in LLD divertor conditions
2010-07-30 | T&T | 1.0488 | 1.0488 | 43 | 43 | done | XP-1041A. Henry Kugel LLD pumping
2010-08-31 | LR | 0.53659 | 0.53659 | 22 | 22 | done | XP-1056 Imp. Reduction with Li aeorsol
2010-08-09 | LR | 0.41463 | 0.41463 | 17 | 17 |  | XP-1059. LLD Characterization part II
2010-08-10 | LR | 1.5854 | 1.1707 | 65 | 48 |  | XP-1059. LLD Characterization part II
2010-08-11 | LR | 2.0244 | 0.43902 | 83 | 18 |  | XP-1059. LLD Characterization part II
2010-08-12 | LR | 2.4146 | 0.39024 | 99 | 16 | done | XP-1059. LLD Characterization part II
|  | 11.0244 | 11.0244 | 452 | 452 | 6 | Total LR
2010-06-28 | MS | 0.46341 | 0.46341 | 19 | 19 |  | XP-1019 Optimization of beta-control
2010-07-29 | MS | 1.0244 | 0.56098 | 42 | 23 | done | XP-1019. Beta feedback is successful
2010-04-15 | MS | 0.58537 | 0.58537 | 24 | 24 |  | XP-1020. navigation through weak RWM stability Vf(psi)
2010-08-19 | MS | 1.2927 | 0.70732 | 53 | 29 | done | XP-1020. good data on rotation variation and RFA. done
2010-08-04 | MS | 0.65854 | 0.65854 | 27 | 27 |  | XP-1021 after LITER replacement. Missed shots on COM
2010-08-27 | MS | 1.1463 | 0.4878 | 47 | 20 | done | XP-1021. Collected halo current data, 2-color camera data. possible Li effects. done
2010-08-18 | MS | 1 | 1 | 41 | 41 | inc. | XP-1022. LQG controller for RWM stabilization, got some good data, want more
2010-04-13 | MS | 0.21951 | 0.21951 | 9 | 9 |  | XP-1023. Optimized RWM feedback for high <bN>pulse at low n and li
2010-04-15 | MS | 0.58537 | 0.36585 | 24 | 15 |  | XP-1023. Optimized RWM feedback for high <bN>pulse at low n and li
2010-07-29 | MS | 1.1463 | 0.56098 | 47 | 23 |  | XP-1023. Optimized RWM feedback for high <bN>pulse at low n and li
2010-08-03 | MS | 1.3415 | 0.19512 | 55 | 8 |  | XP-1023. Optimized RWM feedback for high <bN>pulse at low n and li
2010-08-19 | MS | 1.8293 | 0.4878 | 75 | 20 |  | XP-1023. Optimized RWM feedback for high <bN>pulse at low n and li
2010-09-24 | MS | 2.561 | 0.73171 | 105 | 30 | done | XP-1023. XP is done
2010-09-15 | MS | 0.85366 | 0.85366 | 35 | 35 | done | XP-1032. Error field threshold scaling in H mode - next step devices
2010-09-17 | MS | 0.36585 | 0.36585 | 15 | 15 | done | XP-1062. NTV behavior: low collisionality and maximum variation of wE
|  | 8.2439 | 8.2439 | 338 | 338 | 7 | Total MS
2010-06-02 | MS/ITER | 0.097561 | 0.097561 | 4 | 4 |  | XP-1031. Developed target
2010-06-22 | MS/ITER | 1.3171 | 1.2195 | 54 | 50 |  | XP-1031 Global MHD and ELM stability vs edge current, n*qped, edge nu
2010-09-17 | MS/ITER | 1.7561 | 0.43902 | 72 | 18 |  | XP-1031. Effects of current ramps, 3-D fields on ELMs
2010-09-21 | MS/ITER | 2.3171 | 0.56098 | 95 | 23 | done | XP-1031. Current ramp suppression of ELMs not reproducible? want 2 hours
|  | 10.561 | 10.561 | 433 | 433 | 8 | Total MS+ITER
2010-09-07 | SFSU | 0.19512 | 0.19512 | 8 | 8 |  | XP-1034 to 7PM. Test delays/problems during CHI ISTP. CA for TOR. Missed shots on CHI/ECS
2010-09-08 | SFSU | 1.3659 | 1.1707 | 56 | 48 |  | XP-1034. Missed shots on Aborts/COM/CHI
2010-09-09 | SFSU | 2.7073 | 1.3415 | 111 | 55 |  | XP-1034 to 7PM. Missed shots on ECS/Abort
2010-09-10 | SFSU | 3.1951 | 0.4878 | 131 | 20 | done | XP-1034. 7 Caps, no abs. arcs, 330 kA of CHI current
|  | 3.1951 | 3.1951 | 131 | 131 | 1 | Total SFSU
2010-09-14 | T&T | 1.3902 | 1.3902 | 57 | 57 | done | XP-936. Look for effects of rotation shear on confinement/turbulence
2010-09-16 | T&T | 0.7561 | 0.7561 | 31 | 31 | done | XP-1037 Study of the Parametric Dependence of High-k Turbulence
2010-06-29 | T&T | 0.65854 | 0.65854 | 27 | 27 |  | XP-1041 Poloidal rotation joint XP
2010-09-01 | T&T | 1.2927 | 0.63415 | 53 | 26 | inc. | XP-1041. Poloidal rotation joint XP
2010-08-13 | T&T | 0.65854 | 0.65854 | 27 | 27 |  | XP-1042. Use torque transients to understand rotation scaling
2010-09-16 | T&T | 0.92683 | 0.26829 | 38 | 11 | done | XP-1042. Use torque transients to understand rotation scaling
2010-08-02 | T&T | 0.56098 | 0.56098 | 23 | 23 | done | XP-1067. Zonal flows and blobs, no affect from BEEP
|  | 4.9268 | 4.9268 | 202 | 202 | 5 | Total T&T
2010-06-02 | T&T/ITER | 0.5122 | 0.5122 | 21 | 21 |  | XP-1028/922. Mostly done?
2010-09-15 | T&T/ITER | 0.63415 | 0.12195 | 26 | 5 |  | XP-1028/922. Density dependence of L-H threshold (XP922)
2010-09-23 | T&T/ITER | 0.90244 | 0.26829 | 37 | 11 | done | XP-1028/922. Lack of LITER impacted machine performance
2010-08-30 | BP | 0.26829 | 0.26829 | 11 | 11 |  | XP-1029. Dependence of PLH on Radius and triangularity of the X-point
2010-08-20 | T&T/ITER | 0.65854 | 0.39024 | 27 | 16 | done | XP-1029. Dependence of PLH on Radius and triangularity of the X-point
|  | 6.4878 | 6.4878 | 266 | 266 | 7 | Total T&T + ITER
2010-08-24 | WPI | 0.41463 | 0.41463 | 17 | 17 |  | XP-1009. HHFW heating at low Te, Ip
2010-08-25 | WPI | 1.2195 | 0.80488 | 50 | 33 | inc. | XP-1009. HHFW heating at low Te, Ip
2010-06-23 | WPI | 0.82927 | 0.82927 | 34 | 34 |  | XP-1011. H-mode avalanches
2010-09-23 | WPI | 1.0244 | 0.19512 | 42 | 8 | done | XP-1011. Acquired full BES profile of TAE
2010-09-23 | WPI | 0.70732 | 0.70732 | 29 | 29 | done | XP-1013. Good BES data on lfCAE. (Bay K LITER replaced, ready for bakeout)
2010-09-02 | WPI | 0.63415 | 0.63415 | 26 | 26 | done | XP-1014. Study of Angelfish instability & effect of HHFW
|  | 3.5854 | 3.5854 | 147 | 147 | 4 | Total WPI
2010-06-09 | WPI/ITER | 0.02439 | 0.02439 | 1 | 1 | inc. | XP-1017. Down/CA for NB/TOR (TVPS). Missed shots on TOR/COM
|  | 3.6098 | 3.6098 | 148 | 148 | 5 | Total WPI + ITER
2010-05-26 | XMP | 0 | 0 | 0 | 0 | XMP | ISTP-001/XMP-64. Machine conditioning/Li evaporation. No accrued run time
2010-04-14 | XMP | 0 | 0 | 0 | 0 | XMP | MSE Calibrations. No accrued run time
2010-09-23 | XMP | 0.12195 | 0.12195 | 5 | 5 | XMP | XMP-neutron calibration
2010-06-14 | XMP | 1.2195 | 1.2195 | 50 | 50 | XMP | XMP-26. Missed shots on COM/ECS
2010-06-17 | XMP | 2.3415 | 1.122 | 96 | 46 | XMP | XMP-26 to 7PM. Down for Mag Diag (2)
2010-06-08 | XMP | 3.5854 | 1.2439 | 147 | 51 | XMP | XMP-26 to 7PM. Delay for HHFW Vac Cond. Missed shot on ECS
2010-06-07 | XMP | 4.5854 | 1 | 188 | 41 | XMP | XMP-26. Delayed start for bay F LITER work. Missed shot on COM
2010-06-09 | XMP | 5.561 | 0.97561 | 228 | 40 | XMP | XMP-26. Down/CA for NB/TOR (TVPS). Missed shots on TOR/COM
2010-06-11 | XMP | 5.6829 | 0.12195 | 233 | 5 | XMP | XMP-26. Late start for OH/Machine reassembly. Missed shot on ECS
2010-08-23 | XMP | 6.5366 | 0.85366 | 268 | 35 | XMP | XMP-26
2010-08-24 | XMP | 7.1707 | 0.63415 | 294 | 26 | XMP | XMP-26
2010-08-12 | XMP | 1.122 | 1.122 | 46 | 46 | XMP | XMP-64. Missed shots on PHYS/COM
2010-04-13 | XMP | 0.60976 | 0.60976 | 25 | 25 | XMP | XMP-65. Improved beta feedback control was demonstrated.
2010-03-31 | XMP | 0.63415 | 0.63415 | 26 | 26 | XMP | XMP-66 w/SPAs, NB, LITER. Delay for SPA testing. Down/CA for DIAG. Missed shots on Abort
2010-04-01 | XMP | 1.0244 | 0.39024 | 42 | 16 | XMP | XMP-66. Strike point control, shots to 800ms.
2010-03-30 | XMP | 1.0244 | 0 | 42 | 0 | XMP | XMP-66. Machine conditioning without SPA's. No accrued run time
2010-06-18 | XMP/ASC | 0.58537 | 0.58537 | 24 | 24 | XMP/ASC | XMP-68. Delay for HHFW Vac Cond. Down for TOR (Gas). Missed shot on Abort (LITER) PF4 XMP
2010-07-27 | XMP | 1.3902 | 0.80488 | 57 | 33 | XMP | XMP-68 to 7PM. Test delays for ISTP. Down for ECS. Missed shots on COM/LITER. PF4 XMP
2010-05-27 | XMP | 0.34146 | 0.34146 | 14 | 14 | XMP | XMP-69. Down/CA for TOR (GIS/Vac). Missed shot on ECS Kolemen - relay control
2010-06-17 | XMP | 0.26829 | 0.26829 | 11 | 11 | XMP | XMP-70 to 7PM. Down for Mag Diag (2) BES
2010-06-23 | XMP | 0.63415 | 0.36585 | 26 | 15 | XMP | XMP-70. Delay for LITER. Down for ECS. Missed shot on DIAG. BES commissioning
|  | 12.4146 | 12.4146 | 509 | 509 | 10 | Total XMPs
4.3415
Totals | 0 | 71.6585 | 71.6585 | 2938 | 2938 | 43
| Run Hours |  | Run Days | Plasmas | Plasmas | 4
2010-10-06 | ASC | 0.65854 | 0.65854 | 27 | 27 | done | XP-1006. vertical stability at high kappa, high aspect ratio w/improved control
2010-10-14 | ASC/T&T | 0.57317 | 0.57317 | 23.5 | 23.5 | done | XP-1040. Yuh, Sustained ITBs and H-Mode ITBs
2010-10-26 | ASC | 0.53659 | 0.53659 | 22 | 22 | done | XP-1058. Kolemen squareness
2010-10-25 | ASC | 0.70732 | 0.70732 | 29 | 29 | done | XP-1071. Gerhardt high kappa/aspect ratio
|  | 2.4756 | 2.4756 | 101.5 | 101.5 | 4 | Total ASC
2010-10-22 | BP | 0.43902 | 0.43902 | 18 | 18 | inc. | XP-1030. Battaglia off-axis ELM suppression
2010-10-04 | BP | 0.97561 | 0.97561 | 40 | 40 | done | XP-1050. Divertor detachment Soukhanovskii
2010-10-21 | BP | 0.097561 | 0.097561 | 4 | 4 |  | XP-1072. Boedo plunging probe measurement of pedestal
2010-10-22 | BP | 0.58537 | 0.4878 | 24 | 20 | done | XP-1072. Boedo plunging probe measurement of pedestal (beginning/end of day
2010-10-25 | BP | 0.56098 | 0.56098 | 23 | 23 |  | XP-1074. Diallo pedestal structure vs. triangularity
2010-10-27 | BP | 0.73171 | 0.17073 | 30 | 7 | done | XP-1074. Diallo pedestal structure vs. triangularity
|  | 2.7317 | 2.7317 | 112 | 112 | 4 | Total BP
2010-10-28 | LR | 0.41463 | 0.41463 | 17 | 17 |  | XP-1000A. LLD heating with gas
2010-10-29 | LR | 1.439 | 1.0244 | 59 | 42 | done | XP-1000A. LLD heating with gas
2010-10-27 | LR | 0.19512 | 0.19512 | 8 | 8 | done | XP-1002 Core impurity density and Prad reduction w/variations in LLD divertor conditions
|  | 1.6341 | 1.6341 | 67 | 67 | 2 | Total LR
2010-10-26 | MS | 0.58537 | 0.58537 | 24 | 24 | inc. | XP-1022. State-space controller
|  | 0.58537 | 0.58537 | 24 | 24 | 1 | Total MS
2010-10-18 | SFSU | 0.78049 | 0.78049 | 32 | 32 |  | XP-1034. Extra testing for CHI. Down/CA for COM/TOR. Missed shot on Abort (CHI)
2010-10-19 | SFSU | 1.7317 | 0.95122 | 71 | 39 |  | XP-1034. Down/CA for PFAB/COM. Missed shots on Aborts (ECS)/TOR (Gas)
2010-10-20 | SFSU | 2.4878 | 0.7561 | 102 | 31 | done | XP-1034. Late start for MSE Calibration. CA to configure for CHI. Missed shot on Abort (CHI)
|  | 2.4878 | 2.4878 | 102 | 102 | 1 | Total SFSU
2010-10-13 | T&T | 0.56098 | 0.56098 | 23 | 23 |  | XP-1036. Battaglia H-mode threshold with D & He
2010-10-15 | T&T | 1.2927 | 0.73171 | 53 | 30 | done | XP-1036. Battaglia H-mode threshold with D & He
2010-10-05 | T&T | 0.60976 | 0.60976 | 25 | 25 | done | XP-1037. Ren
2010-10-07 | T&T | 0.4878 | 0.4878 | 20 | 20 | done | XP-1038. Smith multi-scale turbulence
2010-10-08 | T&T | 0.68293 | 0.68293 | 28 | 28 |  | XP-1039. Kubota Ohmic H-modes
2010-10-27 | T&T | 0.82927 | 0.14634 | 34 | 6 | done | XP-1039. Kubota Ohmic H-modes
2010-10-14 | T&T/ASC | 0.57317 | 0.57317 | 23.5 | 23.5 | done | XP-1040. Yuh, Sustained ITBs and H-Mode ITBs
2010-10-15 | T&T | 0.41463 | 0.41463 | 17 | 17 | done | XP-1041. Poloidal rotation joint XP
2010-10-06 | T&T | 0.53659 | 0.53659 | 22 | 22 | done | XP-1042. Solomon rotation
2010-10-08 | T&T | 0.46341 | 0.46341 | 19 | 19 | done | XP-1070. Smith turbulence anisotropy
2010-10-21 | T&T | 0.68293 | 0.68293 | 28 | 28 | done | XP-1073. Clayton imp. transport
|  | 5.8902 | 5.8902 | 241.5 | 241.5 | 9 | Total T&T
2010-10-05 | T&T/ITER | 0.21951 | 0.21951 | 9 | 9 |  | XP-1029. Battaglia Plh threshold w/triangularity
2010-10-21 | T&T/ITER | 0.68293 | 0.46341 | 28 | 19 |  | XP-1029. Battaglia Plh again
2010-10-22 | T&T/ITER | 0.92683 | 0.2439 | 38 | 10 |  | XP-1029. Battaglia with more Plh
2010-10-27 | T&T/ITER | 1.2927 | 0.36585 | 53 | 15 | done | XP-1029. Battaglia PLH
|  | 7.1829 | 7.1829 | 294.5 | 294.5 | 10 | Total T&T+ITER
2010-10-07 | WPI/ITER | 0.65854 | 0.65854 | 27 | 27 | done | XP-1015. Fu M3D-k validation
2010-10-13 | WPI/ITER | 0.26829 | 0.26829 | 11 | 11 | inc. | XP-1017. Hosea
|  | 0.92683 | 0.92683 | 38 | 38 | 2 | Total WPI
2010-10-11 | XMP | 0.97561 | 0.97561 | 40 | 40 |  | XMP-26. Extra testing for ISTP. Down/CA for DIAG/TOR. Missed shot on Abort
2010-10-12 | XMP | 2.0976 | 1.122 | 86 | 46 |  | XMP-26. Down/CA for TOR (TVPS)
2010-10-13 | XMP | 2.3171 | 0.21951 | 95 | 9 |  | XMP-26
|  | 2.3171 | 2.3171 | 95 | 95 | 1 | Total XMP
Totals | 0 | 20.3415 | 20.3415 | 834 | 834 | 24
| Run Hours | Run days | Run days | Attempts | Plasmas | 3