## Slide 1
FY2015 (and 2016) research milestones will guide prioritization of eXperimental Proposal (XP) ideas
TF OD = 40cm
Previous
center-stack
TF OD = 20cm
New
center-stack
FY2016
FY2015
14
12
18
15
Develop physics + operational tools for high-performance discharges (k, d, b, EF/RWM)
Develop snowflake configuration, study edge and divertor properties
Assess H-mode confinement, pedestal, SOL characteristics at higher BT, IP, PNBI
R15-1
R15-3
IR15-1
Quantify impact of broadened J(r) and p(r) on tokamak confinement and stability
Assess disruption mitigation, initial tests of real-time warning and prediction techniques
Develop high-non-inductive fraction NBI H-modes for ramp-up & sustainment
Assess fast-wave SOL losses, core thermal and fast ion interactions at increased BT, IP
R16-3
R16-4
Assess confinement and local transport and turbulence at low n* with full range of BT, IP, and NBI power
IR16-1
Expt. Run Weeks:
Incremental (full ops)
FES 3 Facility Joint Research Target (JRT)
Integrated Scenarios
Core Science
Boundary Science
New 2nd NBI
Present NBI
C-Mod leads JRT
NSTX-U leads JRT
Assess effects of NBI injection on fast-ion f(v) and NBI-CD profile
R15-2
Assess scaling, mitigation of steady-state, transient heat-fluxes w/ advanced divertor operation at high power density
R16-1
Assess high-Z divertor PFC performance and impact on operating scenarios
R16-2

## Slide 2
1st year goal: operating points with forces up to ½ way between NSTX and NSTX-U, ½ design-point heating limit of PF/TF coils.
  Will permit up to ~5 second operation at BT~0.65
2nd year goal: Full field & current, but still limiting coil heating
  Will revisit year 2 parameters once year 1 data has been accumulated
3rd year goal: Full capability
 | NSTX (Max.) | FY 2015 NSTX-U Operations | FY 2016 NSTX-U Operations | FY 2017 NSTX-U Operations | Ultimate Goal
IP [MA] | 1.2 | ~1.6 | 2.0 | 2.0 | 2.0
BT [T] | 0.55 | ~0.8 | 1.0 | 1.0 | 1.0
Allowed TF I2t [MA2s] | 7.3 | 80 | 120 | 160 | 160
Longest Likely IP Flat-Top at max. I2t, IP, and BT [s] | ~0.4 | ~3.5 | ~3 | 5 | 5
Expected progression of NSTX-U operational performance
Limits to assume for Research Forum idea submissions

## Slide 3: Provisional schedule for the 2015 research campaign
Research Plasma Operation
Bakeout
ISTP & Commissioning
First Plasma
Mar. 2015
Apr. 2015
May 2015
June 2015
July 2015
Aug 2015
Sept. 2015
Feb. 2015
Diagnostic Considerations
Magnetic Calibrations
MSE Calibrations
CHERS Calibrations & XMPs
Neutron Calibration Transfer
More…
Commissioning
Ip<=1.0 MA, BT<=0.5
Breakdown and current ramp scenarios
EFIT & rtEFIT Reconstructions
Shape & position control
Reliable H-mode
Diagnostic operations
DCPS under plasma operations
Boronizaton +He GDC for PFCs
Data Acquisition Commissioning for Diagnostics
Ex-Vessel Diagnostic Installations
Gas Delivery System Final Checks
Magnetics Debugging
Beamline Final Checks and Conditioning
IR Camera Calibrations
Rectifier Dummy Load Testing
MPTS Rayleigh/Raman Scattering
Research Operations
LITERs when the operational status allows and physics program desires
Continued discharge, control, and diagnostic commissioning

## Slide 4: Run schedule scope of Research Forum
Pre-forum meetings emphasized XMP/XP title, goal, author identification to cover first 2 run months (weeks 1-8)
Forum should emphasize prioritization of XPs for weeks 3-18, but also document commissioning XMP/XP goals + run-time
Mid-run (re-)assessment after first 6-8 Science run-weeks
Commissioning
Run Weeks 1-4
Run Weeks 5-8
Science
Science
Science
Run Weeks 9-12
Run Weeks 13-16
17-18
FY15
Early FY16
Scope of pre-forum meetings - see next page for additional details
Scope of Research Forum
Mid-run assessment

## Slide 5: Operations assumptions for first 2 run-months
Machine Commissioning…assume 1 month (run weeks 1-4)
  Develop basic breakdown, current ramp, shape/position control, diverted plasmas, H-mode access, basic fuelling optimizations.
  Goal: 1 MA, 0.5 T, NBI-heated H-mode (i.e. ~NSTX fiducial levels)
  Diagnostic commissioning
  Boronized PFCs
  Mostly eXperimental Machine Proposals (XMPs)
1st Month of Science Campaign (run weeks 5-8)
  Boronized PFCs, possibly begin lithium coatings
  Operations and basic profile diagnostics, neutron rate,…
  Operation up to 1.4 MA and 0.65 T, 2 seconds
  6 beam sources up to 90 kV
  HHFW available for commissioning

## Slide 6: Operational tools for density and impurity control
Out Years: Utilize Cryo-pumping and Partial NCC
Boronized PFC Studies
  Plan to start NSTX-U operations with TMB.
  Utilize regimes with natural ELMs to control impurity accumulation
  Between-shot He glow for wall conditioning
  Deuterium inventory likely to rise throughout the discharge
Lithiated PFC Studies
  High-tE, ELM-free regimes w/ Li conditioning
  Pulsed 3D fields or lithium granules for ELM pacing to provide impurity control
  Deuterium inventory likely well controlled, but unclear if target Zeff~2 can be achieved
Both Scenarios:
Realtime Density Measurements via FIReTIP
Supersonic Gas Inj. for Density Control
Years 1 & 2 of ops.: Examine Wall Conditioning, Fueling, and ELM Pacing

## Slide 7: Naming convention for NSTX-U NBI systems
Tangency Radius [cm] | Engineering Designation
50 | 1C
60 | 1B
70 | 1A
110 | 2C
120 | 2B
130 | 2A
Notes:
1. MSE-CIF collects light from the 1A source
2. CHERS collects light from the first beamline
3. Additional information on the NB upgrade and capabilities can be found in J.E. Menard, et al, Nuclear Fusion 52 (2012) 083015