## Slide 1: Run schedule assumptions
Pre-forum meeting #2 should emphasize XMP/XP title, goal, author identification to cover first 2 run months (Weeks 1-8)
Forum should emphasize prioritization of XPs for weeks 3-18, but also document commissioning XMP/XP goals + run-time
Mid-run (re-)assessment after first 6-8 Science run-weeks
Commissioning
Run Weeks 1-4
Run Weeks 5-8
Science
Science
Science
Run Weeks 9-12
Run Weeks 13-16
17-18
FY15
Early FY16
Scope of pre-forum meeting #2 - see next page for additional details
Scope of Research Forum
Mid-run assessment

## Slide 2: Assumptions for first 2 run-months to use in identifying XMP/XP titles/goals/authors for Jan 29th pre-forum meeting #2
Machine Commissioning…assume 1 month (run weeks 1-4)
  Develop basic breakdown, current ramp, shape/position control, diverted plasmas, H-mode access, basic fuelling optimizations.
  Goal: 1 MA, 0.5 T, NBI-heated H-mode (i.e. ~NSTX fiducial levels)
  Diagnostic commissioning
  Boronized PFCs
  Mostly XMPs
  What science (aka XPs) can be done during this phase?
1st Month of Science Campaign (run weeks 5-8)
  Boronized PFCs, possibly begin lithium coatings
  Operations and basic profile diagnostics, neutron rate,…
  Operation up to 1.4 MA and 0.65 T, 2 seconds
  6 beam sources up to 90 kV
  HHFW available for commissioning
  What critical XPs can/should be done during this phase?