## Slide 1
In-Vessel installations and Calibrations to conclude in mid-June to shift activities to the preparations for installing the new centerstack.
Most Buswork reinstalled in the NTC by late June.
Centerstack, flex bus and umbrella covers in place by late September.
Clean/Photo/Close on November 7th, followed immediately by the initial pump-down. NSTX-U turned over to Operations.
A limited Centerstack bake is planned for late November.
Field Coil Power Testing and the ISTP to CD-4 in December.
  Assumes that the full-bake and preparations for Physics Operations will occur after CD-4
  No Vessel Entry after CD-4
Transition to Operations
Milestones to NSTX-U CD-4

## Slide 2
The NSTX-U Activity Certification Committee (ACC), comprised of representatives from PPPL Engineering, Research, Safety, and the DOE PSO is currently reviewing technical and safety systems for NSTX-U
  Safety Assessment Doc. (SAD)
  Design review documentation and chit resolution
  Interviews with cognizant engineers
  Plans for pre-operational & integrated system testing
  Safety/interlock systems
  Physical walk-downs of equipment
  Resolution of remedial steps recommended by ACC
A PPPL Internal QA Audit of NSTX-U Start-Up Documentation is planned. Critical Start-Up and Interlock Test Procedures will be reviewed.
A Readiness for Operations Review is being arranged through the University, and is prerequisite for our safety certificate prescribing allowable operating parameters. Committee members from LANL, GA, JLAB, MIT, ORNL, CCFE & UW will be here for this review during the week of September 8th.
Approvals for Operations

## Slide 3
In-Vessel Tasks
  Work Packages in the Work Control Center for plans through mid-June
  Installations such as the HHFW Compliant Center Post, Langmuir probes , and VB Laser Dump
  Metrology and calibrations of Shunt Tiles, MSE-LIF, CHERS/tFIDA
Center Column Assembly
  Assembly of the Center Stack Casing is ongoing in the South High Bay.
  The center column pedestal is needed in June for layouts and alignment.
  The TF/OH, Ceramic Breaks, etc. are expected in early August to complete the assembly.
  Centerstack, flex bus, umbrella covers in place by late September.
TVPS and Gas Delivery Systems
  Assembly of the TVPS is going well and should be ready for pre-operational testing in July.
  High and low field gas fueling systems will be installed by August.
Preparations for Operations

## Slide 4
MG#1 Weld Repairs
  A contractor has been selected to make the repairs and work is expected to begin in May.
  Re-commissioning of MG# 1 is planned between July and September.
Field Coil Power Conversion (FCPC) Commissioning
  AC primary Power Systems and new rectifier firing generators ready to support Ops
  The new PLC-based fault relaying system to replace electromagnetic relays is being commissioned. Individual rectifier power testing will follow.
  The Digital Coil Protection System (DCPS) software is being tested, and hardware is being designed/fabricated. Integrated system testing in June
  The Power System Real Time Control (PSRTC) is being designed and and is expected to be ready for testing in July.
RF Systems
  Reinstallation of RF piping for HHFW will start next month and be completed in June.
  The ECH Pre-ionization system will be ready for CD-4 operation.
Preparations for Operations

## Slide 5
MPTS Commissioning
  Work packages in place to complete VV work and verify sight lines.
  Still much work on flight tube, laser dump, and alignment systems. Competing for resources.
  Still need to schedule time for MPTS calibrations. After CD-4?
  A conceptual design/layouts being developed for the new MPTS Burst laser.
RWM Coils
  RWM Coil Installations will be completed in July.
PF1 Field Changes
  PF1A and PF1C Upper and Lower Coils will be powered.
  PF1B Upper and Lower will not be powered at the start of the run (terminated into resistors and MOV’s).
  FCPC has been configured.
  Connections/labeling in the test cell still required.
Preparations for Operations

## Slide 6
Ip Calculator
  Schematics are being completed and circuit board assembly/testing in progress.
  All parts are expected to be at PPPL by mid May.
  Integrated system testing in August.
Stand Alone Digitizers (SAD II)
  System FDR rescheduled for May.
  Assembly/testing complete in July.
TMB System
  A conceptual design being developed with help of consultant, MIT, and GA.
  Working towards a January 2015 installation.
Neutron Calibration
  The new source on site, but equipment for calibration must be redesigned/built.
  Calibration must be performed with all VV structures in place.
Preparations for Operations

## Slide 7
Neutral Beam #2
  Primary power systems and protective relaying being prepared to start power supply testing in May.
  NB#2 is expected to be ready to pump-down in June.
  Refrigerator start-up and cryogenic cool-down as early as July.
  Need to be able to start ion source pre-operational testing (PTP-11) in September to complete the NB#2 CD-4 in November. As always, ion source operations will restrict test cell access.
  After NB#2 CD-4, will begin to re-commission NB#1. January, 2015
Preparations for Operations