## Slide 1
NSTX-U Program Update
J. Menard
For the NSTX-U Research Team
NSTX-U Team Meeting
PPPL – B318
June 5, 2015
NSTX-U
Supported by
Culham Sci Ctr
York U
Chubu U
Fukui U
Hiroshima U
Hyogo U
Kyoto U
Kyushu U
Kyushu Tokai U
NIFS
Niigata U
U Tokyo
JAEA
Inst for Nucl Res, Kiev
Ioffe Inst
TRINITI
Chonbuk Natl U
NFRI
KAIST
POSTECH
Seoul Natl U
ASIPP
CIEMAT
FOM Inst DIFFER
ENEA, Frascati
CEA, Cadarache
IPP, Jülich
IPP, Garching
ASCR, Czech Rep
Coll of Wm & Mary
Columbia U
CompX
General Atomics
FIU
INL
Johns Hopkins U
LANL
LLNL
Lodestar
MIT
Lehigh U
Nova Photonics
Old Dominion
ORNL
PPPL
Princeton U
Purdue U
SNL
Think Tank, Inc.
UC Davis
UC Irvine
UCLA
UCSD
U Colorado
U Illinois
U Maryland
U Rochester
U Tennessee
U Tulsa
U Washington
U Wisconsin
X Science LLC

## Slide 2: Outline
Diagnostic Solicitation
Impact of Schedule on Research Milestones
Draft Run Schedule

## Slide 3: FES solicitation for U.S. University and Industry DIAGNOSTIC Collaboration on NSTX-U
Expected Issue Date for FOA: 07/01/2015
  Letter of Intent Due Date: Not Applicable
Pre-Application Due Date: 07/29/2015 at 5 PM Eastern Time
  Pre-Application is required, 2-3 pages (Title, abstract, collaborators, …)
Application Due Date: 09/18/2015 at 11:59 PM Eastern Time
Gathering diagnostic idea updates from team via Google form
  Will share these with SG/TSG leaders once gathered (i.e. next week)
NSTX-U PAC-36 will review draft Program Letter via videoconference later in June (probably on June 23)
Program letter will be available no later than July 7

## Slide 4: Impact of restart schedule on milestones
For now, to zeroth order, assume FY15 milestones will be shifted to FY16, FY16  FY17, etc.
  Will likely run early FY18, then have outage for major enhancement(s)
Some milestones and all run-week distributions will need to be revised based on when we actually begin operations
FY15 JRT will have to be based on NSTX data, NSTX-U simulations, and/or analysis of results from other devices
MS and ASC TSGs should assess ability to meet JRT-16 goals using only hardware that will be available in early FY16
  We can/should modify text/deliverables accordingly

## Slide 5: Latest / possible / tentative run plan for 2015-16 Goal is to operate 14-16 run weeks as per research forum
September: 0-2 run weeks
October: 3-4 run weeks
November: 0-2 run weeks
  May want to pause for ST workshop, APS, Thanksgiving
December: 3 run weeks
January: Mid-run assessment (if applicable), PAC-37
Feb/Mar: Complete FY16 run
Mar/Apr: Start outage to install high-k, high-Z tiles, …
Resume operations fall 2016 for FY17
Fiscal Year Boundary

## Slide 6
Very preliminary (and unvetted) modified milestone schedule
FY2017
FY2016
20
18
Develop physics + operational tools for high-performance: k, d, b, EF/RWM
Assess H-mode confinement, pedestal, SOL characteristics at higher BT, IP, PNBI
Assess disruption mitigation, initial
tests of real-time warning, prediction
Develop high-non-inductive fraction NBI H-modes for sustainment and ramp-up
Assess fast-wave SOL losses, core thermal and fast ion interactions at increased field and current
Run Weeks:
FES 3 Facility Joint Research Target (JRT)
Integrated Scenarios
Core Science
Boundary Science
+ Particle Control
C-Mod leads JRT
Assess effects of NBI injection on fast-ion f(v) and NBI-CD profile
Assess scaling, mitigation of steady-state, transient heat-fluxes w/ advanced divertor operation at high power density
R17-1
Assess high-Z divertor PFC performance and impact on operating scenarios
R17-2
Assess impurity sources and edge and core impurity transport
R18-1
Assess role of fast-ion driven instabilities versus micro-turbulence in plasma thermal energy transport
R17-3
Control of current and rotation profiles to improve global stability limits and extend high performance operation
R18-2
Assess transient CHI current start-up potential in NSTX-U
R18-3
Investigation of power and momentum balance for high density and impurity fraction divertor operation
IR18-1
FY2018
12
10
R17-4
R17-5
R16-1
R16-2
R16-3
Incremental
TBD
DIII-D leads JRT
16
14
?
Begin long
outage
for major
facility
enhancement(s)
Timing TBD pending
resources, readiness

## Slide 7
New
center-stack
2nd NBI
Li granule injector
High-Z PFC diagnostics
Off-midplane 3D coils (NCC)
dB diag. - incremental
up to 1 MA plasma gun
Lower divertor cryo-pump
Upgraded CHI for ~0.5MA
LLD using bakeable cryo-baffle
0.5-1 MA CHI
DBS, PCI, or other intermediate-k
Divertor Prad
qmin
Snowflake
Run Weeks:
Five Year Facility Enhancement Plan (green – ongoing)
2015: Engineering design for high-Z tiles, Cryo-Pump, NCC, ECH
MGI disruption mitigation
4 coil AE antenna
HHFW limiter upgrade
Establish control of:
Rotation
Upward
LiTER
High kq
1 MW ECH/EBW
Laser blow-off
Boronization
Enhanced MHD sensors
Neutron collimator
Charged fusion product
Upgraded halo sensors
Pulse-burst MPTS
14-16
10-12
18-20
ne
Integrated Scenarios
Core Science
Boundary Science
+ Particle Control
2015 | 2016 | 2017 | 2018 | 2019
Upgrade Outage
1.5  2 MA, 1s  5s
MAPP
42 ch MPTS
48 ch BES
MSE/LIF
FIReTIP
Major enhancements:
Base funding
+15% incremental
High-Z tile row on lower OBD
10-12
Fiscal Year: