## Slide 1
A deformation of the PF-1aU bus lead flag indicated the water cooled flexible bus was not sufficiently restrained to withstand magnetic forces
The bus lead flag has been found to be sound, and new bracing has been designed and implemented on the PF1aU & L flexible bus and on the bus lead flags. New bracing will be completed over the weekend. Analysis of as-built configuration on Monday.
Early start of coil power testing would be Tuesday. An extended set of test shots are being planned, and will include the use of four new cameras at top and bottom of the machine, and one at the mid-plane, all with archiving.
Analysis and additional modifications will continue:
  PF1c U & L will remain off-line until similar bracing is implemented
  PF4 will remain off-line while analysis continues.
PF Coil Lead Repair/Analysis

## Slide 2
A chronic electrical leakage path exists between the inner and outer vessel exists. Checked daily and varies between 6 and 12 kOhms.
Specific troubleshooting activities continue, but a full analysis /repair may require a dismantling of the upper umbrella.
At this resistance this leakage path does not impact operations (Inner and Outer Vessel shorted for ohmic operations via the motorized ground switch).
Configurations are being considered to allow operation if this leakage path increases to unacceptable levels
  Fixed resistive shorts would be added at the top of the vessels to limit circulating currents.
  Modifications to GFM to continue loop fault monitoring with the I/O VV combined
  MOV’s at top and bottom of the vessel to limit fast Voltage.
Inner/Outer Vacuum Vessel

## Slide 3
An internal LHe Refrigerator vacuum leak was successfully repaired
  The 1070W LHe refrigerator is operating at full capability
  A scoping study has been completed and reviewed to replace the refrigerator with a more efficient modern unit that would also be capable of supporting the proposed divertor cryo-pump. An RFP is being released.
Neutral Beam conditioning has continued during this maintenance period. All six ion sources are operational and conditioning continues:
  NB1A has operated to 89kV, and is reliable at 86kV. There is a small throughput leak at the source isolation valve.
  NB1B is reliable at 90kV. An intermittent current imbalance measured at the Transformer/Rectifier is being investigated.
  NB1C is operating at 95kV.
  NB2A is operating at 90kV.
  NB2B is operating reliably at 90kV. Looking into some unexplained trips and a possible problem with the Fault Detector
  NB2C has been conditioned to 90kV, and is currently operating in mid 80kV range. Maintenance on the transmission line was completed and Hi-Potted to 95kV.
Neutral Beams

## Slide 4
MG#1 rotor welds have been fully restored and tested, and the set was rebalanced in August. MG#1 is available at full rated parameters
  Experienced a serious problem with the Cycloconvertor (variable frequency control to regulate speed, torque and power factor) in December. System had to be fully re-commissioned utilizing original GE Procedures and new procedures developed by PPPL engineering
  Also developed procedures to allow for limited “manual control” operation utilizing the Liquid Rheostat used to start the set. This capability has not been utilized.
  Since December MG#1 was has supported NSTX-U operations without incident
MG#2 operating parameters are limited due to existing cracking discovered on rotor welds
  Rotor welds could be restored utilizing the same procedures and systems exercised in the MG#1 repairs.
  The MG#2 Cycloconvertor is currently being re-commissioned as was done on MG#1. Power testing is in progress.
Motor Generator Sets

## Slide 5
FCPC Maintenance has been completed, and all systems are ready to resume operations
New DCCT’s are being used to replace aging Halmar DC current feedback devices and shunts to reduce noise and improve reliability.
  New DCCT’s will be installed in the PF and TF Coil Circuits
  New units will be installed on the coil sides of the SDS’s to accurately reflect coil polarity regardless of link positioning
FCPC Fault Detector (FD) functions not rectifier current related are being moved from the FD to the new HCS PLC
  More consistent with the functions of the FD and the PLC
  Also, additional FCPC Fault Data and coil currents from the DCPS expansion chassis are being added to data acquisition.
  Both will aid in troubleshooting problems
Methods to take data from FCPC rectifiers to MDS signal plotting to monitor performance are being considered.
Field Coil Power Conversion