## Slide 1: NSTX-U Project / Facility Status
Masa Ono and Jon Menard
NSTX-U FY 2016 Q3 Review Meeting
July 28, 2016

## Slide 2
Facility Operations Status and Plan
On-Going Facility Enhancement Status and Plan
Summary
Outline

## Slide 3: FY 2016 NSTX-U Run Ended Early Due to PF-1AU Coil Short(s) ~ 10.03 run weeks achieved (18 week target) with 1066 plasma shots
December 2015: 0.4 run weeks (XMP)
January 2016 (3 weeks): 2 run weeks (H-mode), PAC-37
Two week maintenance: NBI T-line repair, Argon purge system, Diagnostics
• February – March (4 weeks): 2.4 run weeks (routine H-mode)
Two week maintenance: BN piece recovery, NBI Auto/transformer/T-line repair,
March – April: (3 weeks) 2.4 run weeks (high power H-mode)
Three week maintenance: NBI LHe refrigeration regeneration & leak repair, Granular Injector, Diagnostics
May: (3 weeks) ~ 1.75 run weeks
Three week maintenance: PF-1A flex bus, MGI, GPI, LITER commissioning, Diagnostics
June: (2weeks) ~ 1.1 run weeks
After assessing the PF 1A-U internal short and potential risks, it was decided to discontinue the run on July 25 in consultation with FES.
Completed Plasma Operations
IAEA
APS
PF-1AU Arc Assessment
Outage

## Slide 4: PF-1AU Coil Failure History Detailed Narrative by Stefan Gerhardt Available
On June 29, black substance came out of PF-1A coil. The water had a pungent smell. Sample analyses showed elevated level of yeast/fungi. The black substance is organic as it is disolved by hydrogen peroxide and heat.
  On July 1, a copper piece came out of the PF-1AU The copper piece is a mixture of copper and carbon consistent with arcing involving coil and insulation. No sign of braze material so the arc is likely to be not at the braze in-line joints. But the presence trace amount of aluminum is still a puzzle.
  • On July 5, while trying to release the blockage, the walter leak occurred in the PF-1AU coil. At this point, we decided that PF-1AU is no longer usable and decided to operate without PF-1AU.
On June 28, Tuesday, the PF 1A upper coil cooling water blockage developed terminating the run. No significant coil electrical nor cooling water/temperature anomaly found until the last shot.

## Slide 5: PF-1AU Developed Water Leak Wetting TF and OH Normal TF and OH electrical coil insulation attained after drying
Water leak
On July 5, 2015
Water leak
On July 5, 2015
TF
OH
• On July 5, large water leak developed on PF-1AU and water went down the center-stack soaking TF and OH coils and other CS components including microtherm.
• Mild bake of up to 90 °C applied to CS casing for about three days. Additional drying of pedestal with heated/dried air enabled us to recover the normal impedance

## Slide 6: Operations restarted on July 20 without PF-1AU Intermittent turn-to-turn short(s) observed during the coil test shots
7/20/16
Glitch on 203521
202124 - reference
205321 – 1st 50% PF2U
205323 – next 50% PF2U

## Slide 7: Able to obtain the gradual coil deterioration history of PF-1AU  coil inductance has decreased 2-5% over three months period
204124
204124
PF-1AL thus far looks normal.
PF-1AU likely to be arcing locally for the last 2-3 months. The arc got worse until melting copper caused cooling water line blockage. The sustained arc condition may explain the growth of the organic material.
A coil inductance monitoring system for all coils to be implemented.
PF4 removed from
the test shot.

## Slide 8: Summary of PF-1AU
• PF-1AU coil suffered internal arc damage which were active for the last 2-3 months. The cause is unknown but likely to be coil insulation failure resulting from a small water leak (conductor defect?), presence of foreign object (metal chip?), manufacturing error during winding (insulation damaged?), or epoxy curing problem (charred .
• Damaged PF-1AU coil will be removed from the machine by early October and will be examine for the cause of failure. X-ray imaging will be performed immediately then followed by excavation. A forensic team was formed to plan and investigate and to report within 4 weeks of coil extraction..
• A design review will be held on the PF-1AU coil with external reviewers to identify any potential issues with the present design.
• The PF-1AU mandrel has been ordered to be available by early October.
• The coil winding would take 12 weeks. Pros and cons of fabrication at PPPL or by a vendor are considered.

## Slide 9: Replacement activities of PF-1AU has started
• PF-1AU coil mandrel procurement has started. The vendor was selected and purchase order placed within one week (record time!)with 10 week delivery schedule.
• The coil winding would take 12 weeks for both at PPPL and by a vendor. PPPL fabrication would cost more but has a better chance of on-time completion and QA/QC. Coil shop and manpower available at PPPL. This will require starting up the coil shop preparation now to be ready in October.
• The coil conductor is available to make PF-1AU but it is prudent to order the coil conductor at this time for possible future needs.
• Options are being considered:
  Fabricated a new PF-1AU and install it for the next run. This would shorten the FY 2017 run to only up to 3- 4 months for the best case.
  Install PF 1A-U mandrel only. Then fabricate a new PF-1AU for the following outage. This option should provide more FY 2017 run weeks ~ 6 - 7 months.

## Slide 10: Critical Path Scenarios Scenario #1 gives sufficient time for FY-17 run
Remove TF LE
Bakeout
Diag Cal.
ISTP
FY-17 Run
Pump
Vent & purge
Remove PF-1AU
PF-1AU mandrel fabr.
Install TF LE
High-Z Tiles?
Passive Plate
Diag. Install
OH Water Heater
Install PF-1AU
Mandrel
Diag Cal.
Bakeout
ISTP
Pump
Install TF LE
Diag Cal.
Wind and VPI PF-1AU
Install PF-1AU
Bakeout
ISTP
Pump
Install TF LE
Diag Cal.
Wind and VPI PF-1AU
Install PF-1AU
FY-17 Run
FY-17 Run
Autopsy and verify design
Pump
Install TF LE
Diag Cal.
Wind and VPI PF-1AU
Install PF-1AU
Autopsy and redesign
Scenario #1:
Mandrel Only
Scenario #2:
Duplicate and install PF-1AU
Scenario #3:
Duplicate but
Install PF-1AU after autopsy
Scenario #4:
Redesign and install PF-1AU after autopsy
Common / Parallel Tasks
Diagnostic Installation Tasks Includes:
  • Fusion Products
  • Divertor SPRED
  • FIReTIP waveguide, optics box, and table.
  • Resisitive Bolometer
  • High-K Scattering
  • Pulse-burst MPTS
  • Laser blow-off

## Slide 11: A Suggested Scenario Scenario #1 + 4 gives sufficient time for FY-17 run
Remove TF LE
Bakeout
Diag Cal.
ISTP
FY-17 Run
Pump
Vent & purge
Remove PF-1AU
PF-1AU mandrel fabr.
Install TF LE
High-Z Tiles
Passive Plate
Diag. Install
OH Water Heater
Install PF-1AU
Mandrel
Diag Cal.
Wind and VPI new PF-1AU
Autopsy PF-1AU and redesign
Install PF-1AU after FY 17 run
Comments:
• This scenario enables ~ 14 – 16 run weeks in FY 2017.
• We can energize PF-1BU utilizing the PF-1AU power supply to give more upper triangularity flexibility.
• We can take the time to examine PF-1AU and if needed redesign PF-1AU before winding.
• But the time would be very limited. Need to consider priority of diagnostic installations.
• Also needs to consider if we are ready for the high-Z tiles programmatically.

## Slide 12
Liquid helium and nitrogen cryogenics systems continue to operate at full capacity (over 19 months continuously)
All 6 neutral beam sources have been conditioned to 90 kV or higher
  All major power supply issues have been resolved
NBI Source Shop has three source refurbishments in progress to build and test as spares for the next run. Grid parts have arrived to build more source grid modules.
All 6 HHFW systems have been conditioned into dummy load to 1 MW and performed antenna conditioning to approximately 20 kV for plasma operations
  All AC Power protective relays have been installed and tested
Heating System Operations
Both NBI and HHFW are ready at full power

## Slide 13: NSTX-U device performance progression
1st year:
  Operated mostly at BT ~ 0.65T
  Pulse length was extended to ~ 2 sec
2nd year goal: Operate up to full field but at 75% plasma current, coil heating to 60% of limit
3rd year goal: Full capability
Parameter | NSTX (Max.) | Year 1 NSTX-U Operations | Year 2 NSTX-U Operations | Year 3 NSTX-U Operations | NSTX-U Ultimate Goal
IP [MA] | 1.2 | ~1.1 | 1.5 | 2.0 | 2.0
BT [T] | 0.55 | ~0.65 | 1.0 | 1.0 | 1.0
Allowed TF I2t [MA2s] | 7.3 | 25 | 100 | 160 | 160
IP Flat-Top at max. allowed I2t, IP, and BT [s] | ~0.4 | ~2 | ~3 | 5 | 5

## Slide 14
Facility Operations Status and Plan
On-Going Facility Enhancement Status and Plan
Summary
Outline

## Slide 15
New
center-stack
2nd NBI
Li granule injector
Up to 1 MA plasma gun
Lower divertor cryo-pump
Upgraded CHI for ~0.5MA
Graphite CHI/Lower Bullnose
DBS, PCI, or other intermediate-k
Snowflake
Run Weeks:
Five Year Facility Enhancement Plan (green – ongoing)
Incremental enables 5 year plan enhancements including NCC, ECH
MGI disruption mitigation
4 coil AE antenna
HHFW limiter upgrade
Establish control of:
Rotation
High kq
Laser blow-off
Boronization
Enhanced MHD sensors
Neutron collimator
Charged fusion product
sß
Upgraded halo sensors
Pulse-burst MPTS
10
12
16
ne
Integrated Scenarios
Core Science
Boundary Science
+ Particle Control
2015 | 2016 | 2017 | 2018 | 2019
Upgrade Outage
0.5 T  1T, 1.5  2 MA, 1s  5s
MAPP
42 ch MPTS
48 ch BES
MSE/LIF
FIReTIP
Major enhancements:
Base funding
incremental funding
Fiscal Year:
1 MW ECH/EBW
16
High-Z tile row on lower OBD
CPS dB diag.
LiTER
Upward
LiTER
APD-based GPI
Scanning MLP
XICS
Divertor Prad
Resistive
Bolometer
Off-midplane 3D coils (NCC)
?

## Slide 16
LITERs
First Year Boundary Physics Tools Operational
Boronization, Lithium Evaporators, Granule Injector
Lithium Evaporator (LITERs)
Granule injector (GI) for ELM pacing
Rotating Impeller
Successfully tested
on EAST and DIII-D
Granules: Li, B4C, C
f ~ up to 500 Hz
Boronization System
Granular Reservoir
• LITERs filing set up in high bay south of NSTX-U Test Cell.
• Argon purge system implemented for Li safety, used for the quick argon vent.
• Ready to support the run.
• Multiple injection and glow made more uniform boronization.
• System is working very well. Multiple # of boronization including daily ones performed. Also being used for He glow discharges.
• GI is now operational.
GI installed on NSTX-U

## Slide 17
Disruption Mitigation System for NSTX-U Massive gas injection system at multiple poloidal positions
  - Massive gas injector system at multi
  poloidal location with identical injection set-up
  - Compact power supply proto-type tested at UW
  - A new double solenoid MGI design (zero net J x B
  torque) based on the ORNL ITER MGI design
NSTX-U MGI Valve
• Successful final Design Review of MGI system was held on February 18, 2016.
• All the MGI components were installed on NSTX-U and the control is being installed.
• Initial gas pulses into NSTX-U were performed and it is ready to support the operations.
  MGI also tested on the U. Washington test stand with magnetic field
Magnets
Magnets
MGI
Valve
U. Washington

## Slide 18
Enhanced FIDA will measure NBI distribution function
For NBI fast ion transport and current drive physics
Vertical
Tangential
Fast Ion D-Alpha Diagnostics
Taking data on NSTX-U
FIDA Views
• Both vertical (perpendicular) and new tangential (parallel) FIDA systems are ready.
• Both FIDA systems have 10 ms, 5 cm, ≈ 10 keV resolutions.
HHFW
Antennas
CHI Gap
Center-Stack
sFLIP
TAE antennas
FY 2016 - 2017 Energetic Particle Conceptual Design and Diagnostic Upgrade
  SS-NPA installed and taking data.
  sFLIP installed for lost ion measurements
  Active 2 X 2 TAE antennas installed. Initially passive spectroscopy then active excitation at few kW level.
  Proto-type charged fusion product (CFP) profile diagnostic is being prepared to be installed.
  8+8 reflectometry array available for AEs.
UCI
FIU
UCLA

## Slide 19
Enhanced Capability for PMI Research
Multi-Institutional Contributions
ORNL
Divertor Imaging
Spectrometer
Dual-band fast IR Camera
Multiple fast 2D visible and IR cameras with full divertor coverage
Li I
C II
LLNL, ORNL, UT-K
U. of Illinois, PPPL
LLNL
ORNL
Divertor fast eroding thermocouples
MAPP probe for between-shots surface analysis – Now taking data

## Slide 20
Microturbulence Diagnostics Being Enhanced
To measure ion to electron gyro-scale, magnetic fluctuations
Beam Emission Spectroscopy
for low k turbulence
48 chs being readied
Cross-Polarization Scattering for magnetic fluctuations being developed in collaboration with DIII-D and MAST
Low k
High k
UC Davis
UCLA
High-k scattering for ETG
Available for FY 17
BES-2D-Fiber
Assembly
U Wisconsin
4x1 subharmonic mixer array
Collection optics (Bay L)
4–channel CPS system in 2017

## Slide 21
Procurement awarded
  Schedule to be delivered in September in time for the installation in NSTX-U
  The first fabricated tile (see below) looks quite good!
  While high-Z tile should be available, whether to install the at this outage will be decided by the programmatic needs.
Being assessed to install High-Z Tile for FY 2017 run
Design to replace a row of the graphite tiles in lower outer divertor
Surface heat flux
Temperature
First fabricated high-Z tile

## Slide 22
NCC Coils Conceptual Design Successfully Completed
NCC = Non-axisymmetric Control Coil
• CDR design includes selection criteria include thermal capability, manufacturability, impact on interfacing objects, fabrication lead time and cost.
• Cost and schedule were prepared as part of the CDR which is completed on May 13, 2016.
Prototype testing of joint design conducted

## Slide 23
Successful Peer Review of NSTX-U NBI LHe Refrigerator
Held on 6/3/16 at PPPL, PDR in September
500 feet of supply and return piping
• To be located in the Cryogenics Compressor Room near NSTX-U, accommodates all envisioned loads (NBI + top and bottom Divetor cryo pumps) due to greatly reduced piping and heat loss (x 3-4).
• The unit would reuse power and space previously used for a 225 Watt refrigerator with all the utilities and compressors available.
• The new refrigerator would remove down time risk and reduce operating and maintenance cost.
• Specification has been drafted and is in review. Plan to submit the requisition and spec to go out for bids hopefully next week.
Proposed 400 W L-He Linde LR-140 refrigerator

## Slide 24
Divertor Cryo-pump Design Making Good Progress
CDR is scheduled on August 3, 2016
Transfer line layout
Initial in-vessel geometry has been laid out.
MIT is designing the cryo-ring.
  Pump radius, throat dimensions taken from the modeling.
  The entire lower outer divertor region to be reduild.
• Cryo-baffle design to be finalized at CDR.
  Diagnostic access and cryo-ring maintainability are important design consideration.
  Graphite PFC option with bakeout capability is pursued for CDR.
“Baffle Top” (BT)
“Upper Bullnose” (UB)

## Slide 25
CHI can form a 200-400 kA seed plasma, but it is too cold for HHFW absorption.
Use of ECH can “bridge the Te gap” to where HHFW and then NB current drive can support the ramp and sustain the current – crucial for OH solenoid-free compact STs
  Good first pass absorption predicted.
Goal of first ECH power in 2019 run with 15% incremental funding.
28 GHz ECH System Design
Completed conceptual design and cost/schedule
28 GHz Gyrotron Development
• 2nd generation 1.5 MW 28/35 GHz gyroton being developed at Tsukuba University.
• The tube was delivered to Tsukuba and the preliminary power test looks promising for 1.5 MW operations.
NSTX-U
Test Cell
Power Supply Room
Gyroton room
28 GHz Gyrotron Room
28 GHz 1 MW Tube by Tsukuba
Gyrotron will be located in the TFTR basement. Stray magnetic fields was measured to be negligible

## Slide 26
MIT PSFC Complements Well Existing NSTX-U Capabilities
Discussions Started on Various Diagnostic Implementations
X-ray Imaging Crystal Spectroscopy
MIT is developing a next generation, servo-driven, compact scanning MLP system
MIT will enhance NSTX-U GPI systems
Avalanche-PhotoDiode (APD)-based GPI
CDR is planned on July 29, 2016.

## Slide 27
• NSTX-U plasma operation was ended due to the PF-1AU coil failure. The facility achieved 10.03 run weeks (18 run weeks target) with 1066 plasma shots.
• PF-1AU coil failure is identified as an internal arc which has been initiated 2 – 3 months prior to the coil failure likely due to a manufacture error or defect. Possible causes includes copper conductor defect causing small water leak, foreign metallic material trapped in the insulator, coil winding error, or epoxy cure error.
• A new PF-1AU coil fabrication is planned. The coil mandrel procurement is placed with a vendor. Various options for the coil manufacturing are being investigated. Outage plan is also being developed.
• Both NBI and and HHFW system are now operational at full power level.
• Good progress were made on a number of enhancements are being implemented to support the NSTX-U research plan. High-k, Pulse-Burst MPTS, Resistive Bolometers. Completed CDR for NCC and ECH.
• Good progress toward the divertor cryo-pump CDR next week.
Summary of Facility and Diagnostics