## XP status
XP | TSG priority | Status | Lead author | PPPL contact | Title | TSG | TSG review | Team review | Approval | Next run | Previous run | Shot range
811 | 4 | Chit revision | Koleman | Gates | Vertical stability physics and performance limits in highly elongated tokamaks | ASC | 1/21/2008 | 1/25/2008
806 | 8 | Approved | Zweben |  | Edge Electrode Biasing | BP |  | 1/14/2008 | 1/25/2008
809 | 10 | Pending final review | Canik | Kaye | ELM Destabilization by RMP | BP/MS | 1/8/2008
801 | 1 | Pending approval | LaHaye | Gerhardt | Beta ramp down 2/1 tearing mode: study of self-stabilization | MS | 1/4/2008 | 1/25/2008
802 | 2 | Pending final review | Sabbagh |  | Active RWM stabilization optimization and ITER support | MS | 1/4/2008
803 |  | Pending final review | Tritz |  | SXR tomography of neon-seeded RWM stabilized plasmas | MS | 1/10/2008
804 | 3 | Pending final review | Sabbagh |  | Comparison of NTV among tokamaks (n = 2 fields, nu_i scaling) | MS | 1/10/2008
805 | 6 | Pending final review | Gerhardt |  | n = 2 intrinsic error fields and RWM critical rotation | MS | 1/10/2008
810 |  |  | Buttery |  | Error field sensistivity of 2/1 NTM onset thresholds at high and low rotation | MS
807 | 10 | Pending final review | Medley |  | Vertical NPA scan | WPI | 12/12/2007
808 | 4 | Pending final review | Crocker | Fredrickson | Alfvén cascades and associated transport | WPI | 12/12/2007
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840

## High priority
Title | Authors | TSG-# | TSG Ranking | Run days assigned | XP # | XP Review Date | Related Milestone and/or ITPA Task | Special Requirements | Run Dates & Comments | Notes
HHFW Phase Scan & Current Drive in Deuterium L-Mode | Phil Ryan, Joel Hosea | 2 |  | 1 | 825 | 2008-04-03 |  | Needs 2 day HHFW XMP | 3 hours of run on 4/3/08 | Initial TSG review 1/09/08 Teleconference 3/27/08
HHFW Phase scan & Current Drive into NB Deuterium H-Mode | Joel Hosea, Phil Ryan | 5 |  | 1.5 |  |  |  | Needs 2 day HHFW XMP
Fast ion transport induced by Alfvén avalanches | Eric Fredrickson, Mario Podestà, Bill Heidbrink, Doug Darrow | 14 |  | 2 | 819 | 2008-02-14 | MDC-11 (a) |  | A few setup shots on 4/4/08 then run on 4/10/08 | TSG reviewed 12/19/07
Identify sustained fast-ion loss with Alfven Cascade modes | Neal Crocker, Eric Fredrickson | 16 |  | 1 | 808 |  | MDC-11 (a) |  |  | TSG reviewed 12/12/07
Profile of fast ions that are accelerated by HHFW | Bill Heidbrink | 21 |  | 1 | 832 |  | MDC-11 (c) |  |  | TSG Reviewed 4/1/08
Optimization of EBW Coupling from H-Mode Plasmas | Gary Taylor | 1 |  | 0.5 | [5 empty] | 28 GHz EBW heating no longer in NSTX baseline FY09 & 10 budget
Ramp up in D2 from ECH target | Joel Hosea, Phil Ryan, Gary Taylor | 4 |  | 0.5 |  |  |  | Needs 2 day HHFW XMP |  | In 3-year plan? Need for CTF?
Neutral Beam Ion Loss During Energetic Particle Mode Bursts | Doug Darrow | 26 |  | 0.5 | [5 empty] | TSG reviewed 1/16/08
Angelfish (CAE or GAE hole-clumps) studies | Eric Fredrickson, Neal Crocker | 20 |  | 0.5 |  |  | MDC-11 (b) |  |  | TSG reviewed 1/16/08
Measurement of BAAE and TAE_RSAE Mode Structures with High-k Scattering System | Woochang Lee, Nikolai Gorelenkov | 23 |  | 0.5 |  |  | MDC-11 (b) |  |  | TSG reviewed 1/16/08, thesis work
Vertical NPA scan w/wo low f MHD and with hf only MHD | Sid Medley | 25 |  | 0.5 | 807 | 2008-04-07 | MDC-11 (a) |  |  | TSG reviewed 12/12/07
Note on I1: In clude requirements for NBI power above 6MW, any HHFW heating, CHI, lithium evaporation, LPI, non-standard gases, SGI, SPA use, non-standard coil use (e.g. PF4, different polarities).
Note on D1: 1 is the highest ranking. Numbers must be consecutive
Note on E1: Recommendation by TSG. May not represent actual assignment.

## Full list
Lead Author | Institution | Title | TSG | TSG-# | Combined # | Special Requirements | Run days requested | TSG Ranking | Run days assigned | Related Milestone | Related ITPA Task | Notes
R. Raman | U-Wash | Central Solenoid Flux savings using Transient CHI Startup | SFS | 1 | 1 | CHI, SGI, Branch-5 LDGIS,NBI, HHFW, PF2L reversed, PF2U,L at 2kV, OH reduced to 4kV, | 8 | 1 | 4 | R08-2 |  | 2 campaigns of 4 days each Reassess requirements after first 4 day campaign
D. Mueller | PPPL | Edge Current Drive Requirements | SFS | 2 | 2 | CHI, SGI, Branch-5 LDGIS,NBI, HHFW, PF2U,L at 2kV, OH reduced to 4kV, | 0 | 2 |  |  |  | No runtime requested - planning for a test in 2009 Up to 1 day may be allocated for test to support 2009 experiments - time permitting
A. Redd | U-Wash | Relaxation Current Drive | SFS | 3 | 3 | CHI, Branch-5 LDGIS, PF2L reversed, PF2U.L at 2kV. | 3 | 2 |  |  |  | Requirements to be assessed during TSG meeting Up to 1 day may be allocated for tests - time permitting
A. Sontag | U-Wisc | Plasma Gun Startup | SFS | 4 |  | To be assessed | 0 |  |  |  |  | None at this time- Planning for tests in 2009-10
X. Tang | LANL | CHI Application to Future Devices | SFS | 5 |  | Theory | 0
Group | PPPL | Outer PF Startup | SFS | 6 |  | To be assessed | 0 |  |  |  |  | None at this time - planning for experiments in 2009
Gary Taylor | PPPL | Optimization of EBW Coupling from H-Mode Plasmas | WPI | 1 | 1 |  | 1 | 1 | 0.5
Joel Hosea | PPPL | HHFW Phase Scan in Deuterium L-Mode | WPI | 2 | 2 | Needs 2 day HHFW XMP | 1 | 1 | 0.5
Joel Hosea | PPPL | HHFW Current Drive in Deuterium L-mode | WPI | 3 | 3.1 | Needs 2 day HHFW XMP | 1 | 1 | 0.5 |  |  | Combine with WPI-08
Phil Ryan | ORNL | CD in Deuterium L-mode | WPI | 8 | 3.2 | [6 empty] | Combine with WPI-03
Joel Hosea | PPPL | HHFW Phase scan & Current Drive into NB Dueterium H-Mode | WPI | 5 | 4.1 | Needs 2 day HHFW XMP | 2 | 1 | 1 |  |  | Combine with WPI-06, WPI-21 Possible additional 0.5 day
Phil Ryan | ORNL | RF accountability in Deuterium NB H-Mode with HHFW Modulation | WPI | 6 | 4.2 |  |  | 2 |  |  |  | Combine with WPI-05
Bill Heidbrink | UC Irvine | Spatial profile of beam ions accelerated by HHFW | WPI | 21 | 4.3 |  | 1 | 2 |  |  | MDC-11 (c) | Combine with WPI-05
Mario Podestà | UC Irvine | Fast-ion transport induced by Alfvén instabilities | WPI | 14 | 5.1 |  | 2 | 1 | 2 |  | MDC-11 (a) | Combine with WPI-11, WPI-12, WPI-13, WPI-15
Bill Heidbrink | UC Irvine | Quiet plasmas for FIDA and SSNPA validation | WPI | 11 | 5.2 | Needs 2-3 hrs XMP | 1 | 1 |  |  | MDC-11 (c) | Combine with WPI-14
Eric Fredrickson | PPPL | Expansion of quiescent operation regime | WPI | 12 | 5.3 |  | 0.5 | 1 |  |  | MDC-11 (c) | Combine with WPI-14
Eric Fredrickson | PPPL | Energetic Particle Transport during TAE avalanches | WPI | 13 | 5.4 |  | 2 | 1 |  |  | MDC-11 (a) | Combine with WPI-14
Doug Darrow | PPPL | Energetic Particle Mode Induced NBI loss | WPI | 15 | 5.5 |  | 1 | 2 |  |  | MDC-11 (a) | Combine with WPI-14
Neal Crocker | UCLA | Identify sustained fast-ion loss with Alfven Cascade modes | WPI | 16 | 6.1 |  | 1 | 1 | 1 |  | MDC-11 (a) | Combine with WPI-17, WPI-18
Neal Crocker | UCLA | Validate MHD Spectroscopy at high beta with AC and BAAE | WPI | 17 | 6.2 |  | 3 | 1 |  |  | MDC-11 (b) | Combine with WPI-16
Eric Fredrickson | PPPL | Alfvén Cascade Threshold Experiment | WPI | 18 | 6.3 |  | 1 | 1 |  |  | MDC-11 (b) | Combine with WPI-16
Eric Fredrickson | PPPL | Detection of CAE or GAE with RF antenna | WPI | 26 | 7 |  | 0 | 1 |  |  | MDC-11 (c)
Joel Hosea | PPPL | Ramp up in D2 from ECH | WPI | 4 | 8.1 | Needs 2 day HHFW XMP | 1 | 2 | 0.5 |  |  | Combine with WPI-09 In 3-year plan? Need for CTF?
Phil Ryan | ORNL | Coupling to ECH plasmas | WPI | 9 | 8.2 |  |  | 2 |  |  |  | Combine with WPI-04
Phil Ryan | ORNL | HHFW Loading (<200kW) into NB Deuterium H-mode | WPI | 7 | 9 |  | 0 | 2 |  |  |  | Piggyback
Phil Ryan | ORNL | low power to measure sheath loss | WPI | 10 | 10 | During 2 day HHFW XMP |  | 2
Bill Heidbrink | UCI | Suppression Angelfish chirping | WPI | 19 | 11.1 |  | 1 | 2 |  |  | MDC-11 (b)
Eric Fredrickson | PPPL | Documentation of Angelfish (CAE or GAE hole-clumps) | WPI | 20 | 11.2 |  | 1 | 2 |  |  | MDC-11 (b)
Woochang Lee | Postech, South Korea | Measurement of BAAE and TAE_RSAE Mode Structures with High-k Scattering System | WPI | 23 | 12.1 |  | 1 | 2 |  |  | MDC-11 (b) | Combine with WPI-22 Possible 0.5 day
Nikolai Gorelenkov | PPPL | BAAE Frequency Sweep Study | WPI | 22 | 12.2 |  | 1 | 3 |  |  | MDC-11 (b) | Combine with WPI-23
Sid Medley | PPPL | Vertical NPA scan w/wo low f MHD and with hf only MHD | WPI | 25 | 13 |  | 1 | 2 |  |  | MDC-11 (a) | Possible 0.5 day
Doug Darrow | PPPL | NBI prompt loss study | WPI | 24 | 14 |  | 0.5 | 3 |  |  | MDC-11 (c)
V. Soukhanovskii | LLNL | Divertor detachment in highly-shaped high-performance H-mode plasmas | BP | 13 | 1 | no lithium | 1 | 1 | 1 | R08-3
J-W. Ahn | UCSD | Characterization of the divertor heat flux width and the mid-plane SOL widths | BP | 18 | 2 |  | 2 | 1 | 1 | R08-3
A. Hubbard | ORNL | Comparison of Small ELM Regimes in Alcator C-MOD, MAST, and NSTX | BP | 16 | 3 | no lithium | 1 | 1 | 0.5 |  | PEP-16
R. Maingi | ORNL | Dependence of pedestal structure on aspect ratio | BP | 14 | 4 | no lithium | 1 | 1 | 0.5 |  | PEP-9
D. Mansfield | PPPL | Initial Use of Dual LITER for ELMS Mitigation and Evaporator Characterization | BP | 7 | 5 | LITER | 2 | 1 | 1
V. Soukhanovskii | LLNL | Particle balance and poloidal particle source strength for Liquid Lithium Divertor baseline characterization | BP | 2 | 6.1 | no lithium | 1 | 1 | 0.5 | (Joule FY09) |  | Combine with BP-9, BP-4 (Define reference conditions at outset and piggyback early on)
R. Maingi | ORNL | Gas balance in unpumped and pumped discharges - Comparison of graphite and high Z plasma facing materials | BP | 9 | 6.2 | no lithium | 1 |  |  |  |  | Combine with BP-2
C. Skinner | PPPL | Measurement of Li pumping efficacy | BP | 4 | 6.3 | lithium | 0.5 |  |  |  |  | Combine with BP-2
R. Maingi | ORNL | Edge characterization in high performance discharges | BP | 17 | 7 | All diagnostics | 1 | 1 | 1 | R08-3
S. Zweben | PPPL | Biased Electrodes for SOL Control | BP | 20 | 8 | BeAP | 1 | 1 | 0.5
H. Meyer | ORNL | Dependence of ELMS and Power Balance on Magnetic Balance and Fueling | BP | 15 | 9 |  | 1 | 1 | 1 |  | PEP-6
J. Canik | ORNL | ELM Destabilization by RMP | BP | 12 | 10.1 | RMP coils | 1 | 2 | 1 |  |  | Combine with BP-11 & MS XP Consider as cross-cutting?
J-K. Park | PPPL | ELM experiment with various RMP | BP | 11 | 10.2 | RMP coils | 1 |  |  |  |  | Combine with BP-12
R. Maqueda | Nova Photonics | Fast camera studies, edge turbulence & blobs, ELMs, MARFEs, etc | BP | 10 | 11 |  | 5 | 2 | 0.5 |  | DSOL-15
D. Mansfield | PPPL | Injection of Li Powder into the NSTX Scrape-off Layer | BP | 6 | 12 | Li powder injector | 1 | 2 | 0.5
L.F. Delgado-Aparicio | JHU | Role of neoclassical impurity transport in the NSTX gradient region | BP | 21 | 13 |  | 1 | 3 | 0.5
K. Tritz | JHU | Study of Type V ELMs and edge gradients | BP | 22 | 14 |  | 1 | 3 | 0.5
J.P. Allain | Purdue U | Understanding the correlation of lithium-graphite surface chemistry on plasma performance in NSTX | BP | 1 |  | LITER | 1 |  |  |  |  | Piggyback
D. Mansfield | PPPL | NSTX Lithium Conditioning Using both Dual LITER and Li Powder Injection | BP | 3 |  | LITERs, li powder | 1 |  |  |  |  | Piggyback
V. Soukhanovskii | LLNL | High flux expansion divertor - heat flux reduction and properties | BP | 8 |  | no lithium | 1 |  |  | R08-3 |  | Piggyback
Y. Raitses | PPPL | Investigation of dust production in NSTX | BP | 5 |  |  | 0 |  |  |  |  | Piggyback
C. Skinner | PPPL | Can resonant magnetic peturbations broaden the SOL heat flux profile | BP | 19 |  | RMP coils | 0 |  |  |  |  | Piggyback
Kaye | PPPL | Dependence of energy confinement on rotation | TT | 4 | 1.1 | n=3 SPAs, PCHERS, ERD | 0.5 | 1 | 1 | Joule |  | Combined with TT-18 (Delgado-Aparicio)
Delgado-Aparicio | JHU | Correlation between impurity transport and ExB shear in beam-heated NSTX H-modes | TT | 18 | 1.1 | SPAs n=3, EFC, Ne puff | 0.5 |  |  | Joule |  | Combine with TT-04 (Kaye)
Kaye | PPPL | Perturbative modulation of core rotation and assessment of core momentum transport using beam blips | TT | 5 | 2 | PCHERS, ERD, NB blips | 1 | 1 | 1 | Joule | TP6.3
Solomon | PPPL | Momentum transport studies on NSTX | TT | 6 | 3 | PCHERS, ERD, n=3 SPAs | 1 | 1 | 1 | Joule | TP-6.3
Solomon | PPPL | Energy confinement similarity experiment between NSTX and DIII-D | TT | 7 | 4 |  | 1 | 4 | 1 |  | TP-9 | Major ST topic as well
Mazzucato | PPPL | High-k plasma turbulence I | TT | 11 | 5 | Puff/use Ne, Ar, HHFW | 2 | 4 | 1 |  |  | First day
Kaye | PPPL | Effect of nRMP on L-H threshold | TT | 1 | 6 | n=3 SPAs | 1 | 6 | 1 |  | ITPA
Yuh | Nova | Magnetic shear effects on electron and ion thermal transport and momentum transport | TT | 14 | 7 | RF radial reflectometer, NB B@1MW | 2 | 7 | 1
Stutman | JHU | Field scaling of electron transport change with heating power | TT | 9 | 8 | LPI? NPA scan | 2 | 8 | 1
Mazzucato | PPPL | High-k plasma turbulence II | TT | 12 | 9 | Puff/use Ne, Ar, HHFW | 3 | 9 | 1 |  |  | Second day (needs definition)
Kaye | PPPL | beta-scaling using Li evaporation to suppress ELMs | TT | 2 | 10 | n=3 SPAs, Li | 0.5 | 10 |  |  | CDB-2 | Reassess if Li evap can reproducibly suppress ELMs
Delgado-Aparicio | JHU | Role of neoclassical impurity transport in the NSTX gradient region | TT | 17 | 11 | Ne puff, He H-mode? | 1 | 11 | 1
Kaye | PPPL | Effect of nRMP on edge intrinsic rotation | TT | 3 | 12 | ohmic H-mode development, ERD, n=3 SPAs | 0.5 | 12 |  | Joule |  | Run if without beams and RF
Stutman | JHU | Assessing magnetic electron transport in NSTX using He H-modes | TT | 10 | 13 | He H-mode plasmas | 1 | 14
Bush |  | Source of rotation in Ohmic H-modes | TT | 8 | 14
Smith | PPPL | Novel turbulence topics suitable for the NSTX high-k scattering system | TT | 12 | 15 |  | 0
Kubota | UCLA | Mean and Oscillating Turbulent Flows and Their Connection to Internal Transport Barrier Formation | TT | 13 | 16 | RF, need commissioning | 1 |  |  | Joule, R08-1 |  | Scope out first piggyback, then request dedicated run time if necessary
Ross | PPPL | Investigation of ion transport with beam modulation | TT | 15 | 17 | NPA scan, NB modulation, LITER, thesis | 1
Lee | UC Davis | NSTX H-mode measurement in conjunction with gyrocenter shift via FIReTIP system | TT | 16 |  | scan X-point, edge neutral density measurement | 1 |  |  |  |  | Originally considered by TT Combine with ASC-05 (Bell)
J. Menard | PPPL | Robustness of improved error field suppression in long-pulse discharges | ASC | 1 | 1 |  | 1 | 1 | 1
D. Gates | PPPL | Parametric study of high elongation plasmas | ASC | 2 | 2 |  | 1.5 | 2 | 1.5
J. Menard | PPPL | Impact of 2 LITER system on long-pulse discharges | ASC | 3 | 3 | LITER | 1.5 | 3 | 1.5
E. Kolemen | Princeton U. | Vertical Stability Physics and Performance Limits in Tokamaks with highly elongated tokamaks | ASC | 4 | 4 |  | 1 | 4 | 1 |  | MDC-13
M. G. Bell | PPPL | Development and Assessment of X-point limiter plasmas | ASC | 5 | 5.1 |  | 1 | 5 | 1
K-C. Lee | UC Davis | NSTX H-mode measurement in conjunction with gyrocenter shift via FIReTIP system | ASC | 16 | 5.2 | scan X-point, edge neutral density measurement | 1 |  |  |  |  | Originally considered by TT Combine with ASC-05 (Bell)
C. E. Kessel | PPPL | HHFW into Early diverted plasmas and late (end of Ip ramp) Discharges | ASC | 6 | 6 |  | 1.5 | 6 | 1
C. E. Kessel | PPPL | Hybrid Discharges on NSTX | ASC | 7 | 7 |  | 1 | 7 |  |  | SSO-2.2
D. Humphreys | GA | Use of Nonaxisymmetric Coils for Vertical Stability Control in NSTX | ASC | 8 | 8 |  | 1 | 8
D. Humphreys | GA | Development and Performance of model based multivariable shape controllers | ASC | 9 | 9 |  | 1 | 9
D. Mueller | PPPL | Low li startup | ASC | 10 | 10 |  | 0.5 | 10
V. Soukhanovskii | LLNL | H-mode fuelling optimization with high pressure multi-pulse SGI | ASC | 11 | 11 |  | 0 | 11
E. Schuster | Lehigh U. | Advanced Model-based Shape controller | ASC | 12 | 12 |  | 0 | 12
E. Schuster | Lehigh U. | Model-based rotation profile control | ASC | 13 | 13 |  | 0 | 13
R. LaHaye | General Atomics | Beta ramp down 2/1 tearing mode: study of self-stabilization (LaHaye) | MS | 1 | 1.1 |  | 1 | 1 | 1 | Joule | MDC-4 | Combine with MS-02
R. Buttery | UKAEA | Rotation dependence of 2/1 NTM thresholds (Buttery) | MS | 2 | 1.2 |  | 1.5 |  |  |  |  | Combine with MS-01
S.A. Sabbagh | Columbia U. | Active RWM stabilization optimization and ITER support (Sabbagh) | MS | 3 | 2.1 | current in one RWM coil minimized | 1.5 | 2 | 1 | Joule, R09-1 | MDC-2, IIC RWM-1, DCR-096 RWM coil | Combine with MS-04
K. Tritz | Johns-Hopkins U. | SXR tomography of neon-seeded RWM stabilized plasmas (Tritz) | MS | 4 | 2.2 | Neon | 1 |  |  |  |  | Combine with MS-03
S.A. Sabbagh | Columbia U. | Comparison of NTV among tokamaks (n = 2 fields, nu_i scaling) (Sabbagh) | MS | 5 | 3.1 | n = 2 RWM coil | 1 | 3 | 1 | Joule | MDC-12, IIC AUX-1 | Combine with MS-06
R. Buttery | UKAEA | Testing NTV theory of error field penetration (Buttery) | MS | 6 | 3.2 |  | 0.5 |  |  |  |  | Combine with MS-05
S. Gerhardt/D. Gates | PPPL | Studies of the 3/2 NTM: Rotation and Beta Rampdown (Gerhardt/Gates) | MS | 7 | 4 |  | 1.5 | 4 | 1.5 | Joule | MDC-4
J. Berkery | Columbia U. | RWM stabilization physics – comparison to theory (Berkery) | MS | 8 | 5.1 |  | 1.5 | 5 | 1.5 | Joule, R09-1 | MDC-2, IIC RWM-1 | Combine with MS-09, MS-10
J. Berkery | Columbia U. | DIII-D/NSTX RWM joint XP – stability vs. A, rotation profile, nu_i (Berkery) | MS | 9 | 5.2 |  | 1.5 |  |  |  |  | Combine with MS-08
H. Reimerdes | Columbia U. | Parametric dependence RWM damping in rotating plasmas (Reimerdes) | MS | 10 | 5.3 |  | 1 |  |  |  |  | Combine with MS-08
S. Gerhardt/ J. Menard | PPPL | n=2 intrinsic error fields and RWM critical rotation (Gerhardt/Menard) | MS | 11 | 6 | n = 2 RWM coil | 1 | 6 | 1 | Joule | MDC-2, IIC RWM-1
S.A Sabbagh/ K.C. Shaing | Columbia U. | Island-induced neoclassical toroidal viscosity (NTV) (Sabbagh/Shaing) | MS | 12 | 7 |  | 1.5 | 7 | 1 | Joule | MDC-4, MDC-12, IIC AUX-1
S.A. Sabbagh | Columbia U. | Deformation of RWM and multi-mode characteristics (Sabbagh) | MS | 13 | 8.1 |  | 1 | 8 | 1 |  | MDC-2, IIC RWM-1, DCR-096 RWM coil | Combine with MS-14
M. Okabayashi | PPPL | Assessment of non-rigidity in RWM feedback (Okabayashi) | MS | 14 | 8.2 |  | 1 |  |  |  |  | Combine with MS-13
S. Gerhardt | PPPL | Measurement of Halo Currents in the Lower Divertor (Gerhardt) | MS | 15 | [7 empty] | Piggyback
S. Sabbagh |  | ELM mitigation with midplane control coils | MS | 16 |  | RWM coil polarity change | 1 | ? |  |  | IO request | Consider and possibly combine with BP-11, -12
[6 empty] | Totals: | 110 |  | 46
[6 empty] | Proposals requesting/allocated runtime: | 84 |  | 46
[6 empty] | Average request/allocation: | 1.3095 |  | 1
[6 empty] | JM Guidance / TSG request: SFS | 7 |  | 4 | 0.57143
[6 empty] | Guidance / request: WPI | 6 |  | 6 | 1
[6 empty] | Guidance / request: BP | 7 |  | 10 | 1.4286
[6 empty] | Guidance / request: TT | 8 |  | 10 | 1.25
[6 empty] | Guidance / request: ASC | 5.5 |  | 7 | 1.2727
[6 empty] | Guidance / request: MS | 6.5 |  | 9 | 1.3846
Note on G1: In clude requirements for NBI power above 6MW, any HHFW heating, CHI, lithium evaporation, LPI, non-standard gases, SGI, SPA use, non-standard coil use (e.g. PF4, different polarities).
Note on H1: Total must include shot development time, equipment commissioning, etc. Assume 30 standard shots per run day.
Note on I1: 1 is the highest ranking. Numbers must be consecutive
Note on J1: Recommendation by TSG. May not represent actual assignment.

## Milestone XPs
Milestone | Description | Experiment(s) | Title | TSG Priority | TSG days | Total
Joule (08) | Evaluate MHD sources of plasma viscosity and assess impact of plasma rotation on stability, including NTM | TT-4+18 | Dependence of energy & impurity transport on rotation | =1 | 1 | 11
|  | TT-5 | Perturbative modulation of core rotation and assessment of momentum transport | =1 | 1
|  | TT-6 | Momentum transport studies on NSTX | =1 | 1
|  | TT-3 | Effect of nRMP on edge intrinsic rotation | 12
|  | TT-13 | Mean and Oscillating Turbulent Flows and Their Connection to Internal Transport Barrier Formation |  | 0
|  | MS-1+2 | Rotation dependence of 2/1 NTM thresholds | 1 | 1
|  | MS-3+4 | Active RWM stabilization optimization and ITER support | 2 | 1
|  | MS-5+6 | Comparison of NTV among tokamaks (n = 2 fields, nu_i scaling) | 3 | 1
|  | MS-7 | Studies of the 3/2 NTM: Rotation and Beta Rampdown | 4 | 1.5
|  | MS-8+9+10 | RWM stabilization and damping | 5 | 1.5
|  | MS-11+12 | Island-induced neoclassical toroidal viscosity | 6 | 2
R(08-1) | Measure poloidal rotation at low A and compare with theory | TT-4+18 | Dependence of energy confinement on rotation | =1 | 1 | 3
|  | TT-5 | Perturbative modulation of core rotation and assessment of core momentum transport using beam blips | =1 | 1
|  | TT-6 | Momentum transport studies on NSTX | =1 | 1
|  | TT-13 | Mean and Oscillating Turbulent Flows and Their Connection to Internal Transport Barrier Formation |  | 0
R(08-2) | Couple inductive ramp-up to CHI plasmas | SFS-1 | Central Solenoid Flux savings using Transient CHI Startup | 1 | 4 | 4
R(08-3) | Study variation and control of heat flux in SOL | BP-13 | Divertor detachment in highly-shaped high-performance H-mode plasmas |  | 1 | 3
|  | BP-17 | Edge characterization in high performance discharges |  | 1
|  | BP-18 | Characterization of the divertor heat flux width and the mid-plane SOL widths |  | 1
|  | BP-8 | High flux expansion divertor - heat flux reduction and properties |  | 0
ITER task | ELM mitigation with RMP coils | BP-11 | ELM experiment with various RMP |  | 1 | 1
|  | BP-12 | ELM Destabilization by RMP |  | 0
|  | MS-16 | ELM mitigation with midplane control coils