## Full list
Lead Author | Institution | Title | TSG | TSG-# | Combined # | Special Requirements | Run days requested | TSG Ranking | Run days assigned | Related Milestone | Related ITPA Task | Notes
R. Raman | U-Wash | Central Solenoid Flux savings using Transient CHI Startup | SFS | 1 | 1 | CHI, SGI, Branch-5 LDGIS,NBI, HHFW, PF2L reversed, PF2U,L at 2kV, OH reduced to 4kV, | 8 | 1 | 4 | R08-2 |  | 2 campaigns of 4 days each Reassess requirements after first 4 day campaign
D. Mueller | PPPL | Edge Current Drive Requirements | SFS | 2 | 2 | CHI, SGI, Branch-5 LDGIS,NBI, HHFW, PF2U,L at 2kV, OH reduced to 4kV, | 0 | 2 |  |  |  | No runtime requested - planning for a test in 2009 Up to 1 day may be allocated for test to support 2009 experiments - time permitting
A. Redd | U-Wash | Relaxation Current Drive | SFS | 3 | 3 | CHI, Branch-5 LDGIS, PF2L reversed, PF2U.L at 2kV. | 3 | 2 |  |  |  | Requirements to be assessed during TSG meeting Up to 1 day may be allocated for tests - time permitting
A. Sontag | U-Wisc | Plasma Gun Startup | SFS | 4 |  | To be assessed | 0 |  |  |  |  | None at this time- Planning for tests in 2009-10
X. Tang | LANL | CHI Application to Future Devices | SFS | 5 |  | Theory | 0
Group | PPPL | Outer PF Startup | SFS | 6 |  | To be assessed | 0 |  |  |  |  | None at this time - planning for experiments in 2009
Gary Taylor | PPPL | Optimization of EBW Coupling from H-Mode Plasmas | WPI | 1 | 1 |  | 1 | 1 | 0.5
Joel Hosea | PPPL | HHFW Phase Scan in Deuterium L-Mode | WPI | 2 | 2 | Needs 2 day HHFW XMP | 1 | 1 | 0.5
Joel Hosea | PPPL | HHFW Current Drive in Deuterium L-mode | WPI | 3 | 3.1 | Needs 2 day HHFW XMP | 1 | 1 | 0.5 |  |  | Combine with WPI-08
Phil Ryan | ORNL | CD in Deuterium L-mode | WPI | 8 | 3.2 | [6 empty] | Combine with WPI-03
Joel Hosea | PPPL | HHFW Phase scan & Current Drive into NB Dueterium H-Mode | WPI | 5 | 4.1 | Needs 2 day HHFW XMP | 2 | 1 | 1 |  |  | Combine with WPI-06, WPI-21 Possible additional 0.5 day
Phil Ryan | ORNL | RF accountability in Deuterium NB H-Mode with HHFW Modulation | WPI | 6 | 4.2 |  |  | 2 |  |  |  | Combine with WPI-05
Bill Heidbrink | UC Irvine | Spatial profile of beam ions accelerated by HHFW | WPI | 21 | 4.3 |  | 1 | 2 |  |  | MDC-11 (c) | Combine with WPI-05
Mario Podestà | UC Irvine | Fast-ion transport induced by Alfvén instabilities | WPI | 14 | 5.1 |  | 2 | 1 | 2 |  | MDC-11 (a) | Combine with WPI-11, WPI-12, WPI-13, WPI-15
Bill Heidbrink | UC Irvine | Quiet plasmas for FIDA and SSNPA validation | WPI | 11 | 5.2 | Needs 2-3 hrs XMP | 1 | 1 |  |  | MDC-11 (c) | Combine with WPI-14
Eric Fredrickson | PPPL | Expansion of quiescent operation regime | WPI | 12 | 5.3 |  | 0.5 | 1 |  |  | MDC-11 (c) | Combine with WPI-14
Eric Fredrickson | PPPL | Energetic Particle Transport during TAE avalanches | WPI | 13 | 5.4 |  | 2 | 1 |  |  | MDC-11 (a) | Combine with WPI-14
Doug Darrow | PPPL | Energetic Particle Mode Induced NBI loss | WPI | 15 | 5.5 |  | 1 | 2 |  |  | MDC-11 (a) | Combine with WPI-14
Neal Crocker | UCLA | Identify sustained fast-ion loss with Alfven Cascade modes | WPI | 16 | 6.1 |  | 1 | 1 | 1 |  | MDC-11 (a) | Combine with WPI-17, WPI-18
Neal Crocker | UCLA | Validate MHD Spectroscopy at high beta with AC and BAAE | WPI | 17 | 6.2 |  | 3 | 1 |  |  | MDC-11 (b) | Combine with WPI-16
Eric Fredrickson | PPPL | Alfvén Cascade Threshold Experiment | WPI | 18 | 6.3 |  | 1 | 1 |  |  | MDC-11 (b) | Combine with WPI-16
Eric Fredrickson | PPPL | Detection of CAE or GAE with RF antenna | WPI | 26 | 7 |  | 0 | 1 |  |  | MDC-11 (c) | High priority but no runtime. Piggyback?
Joel Hosea | PPPL | Ramp up in D2 from ECH | WPI | 4 | 8.1 | Needs 2 day HHFW XMP | 1 | 2 | 0.5 |  |  | Combine with WPI-09 In 3-year plan? Need for CTF?
Phil Ryan | ORNL | Coupling to ECH plasmas | WPI | 9 | 8.2 |  |  | 2 |  |  |  | Combine with WPI-04
Phil Ryan | ORNL | HHFW Loading (<200kW) into NB Deuterium H-mode | WPI | 7 | 9 |  | 0 | 2 |  |  |  | Piggyback
Phil Ryan | ORNL | low power to measure sheath loss | WPI | 10 | 10 | During 2 day HHFW XMP |  | 2
Bill Heidbrink | UCI | Suppression Angelfish chirping | WPI | 19 | 11 |  | 1 | 2 |  |  | MDC-11 (b)
Eric Fredrickson | PPPL | Documentation of Angelfish (CAE or GAE hole-clumps) | WPI | 20 | 12 |  | 1 | 2 |  |  | MDC-11 (b)
Woochang Lee | Postech, South Korea | Measurement of BAAE and TAE_RSAE Mode Structures with High-k Scattering System | WPI | 23 | 13.1 |  | 1 | 2 |  |  | MDC-11 (b) | Combine with WPI-22 Possible 0.5 day
Nikolai Gorelenkov | PPPL | BAAE Frequency Sweep Study | WPI | 22 | 13.2 |  | 1 | 3 |  |  | MDC-11 (b) | Combine with WPI-23
Sid Medley | PPPL | Vertical NPA scan w/wo low f MHD and with hf only MHD | WPI | 25 | 14 |  | 1 | 2 |  |  | MDC-11 (a) | Possible 0.5 day
Doug Darrow | PPPL | NBI prompt loss study | WPI | 24 | 15 |  | 0.5 | 3 |  |  | MDC-11 (c)
V. Soukhanovskii | LLNL | Divertor detachment in highly-shaped high-performance H-mode plasmas | BP | 13 | 1 | no lithium | 1 | 1 | 1 | R08-3
J-W. Ahn | UCSD | Characterization of the divertor heat flux width and the mid-plane SOL widths | BP | 18 | 2 |  | 2 | 1 | 1 | R08-3
A. Hubbard | ORNL | Comparison of Small ELM Regimes in Alcator C-MOD, MAST, and NSTX | BP | 16 | 3 | no lithium | 1 | 1 | 0.5 |  | PEP-16
R. Maingi | ORNL | Dependence of pedestal structure on aspect ratio | BP | 14 | 4 | no lithium | 1 | 1 | 0.5 |  | PEP-9
D. Mansfield | PPPL | Initial Use of Dual LITER for ELMS Mitigation and Evaporator Characterization | BP | 7 | 5 | LITER | 2 | 1 | 1
V. Soukhanovskii | LLNL | Particle balance and poloidal particle source strength for Liquid Lithium Divertor baseline characterization | BP | 2 | 6.1 | no lithium | 1 | 1 | 0.5 | (Joule FY09) |  | Combine with BP-9, BP-4 (Define reference conditions at outset and piggyback early on)
R. Maingi | ORNL | Gas balance in unpumped and pumped discharges - Comparison of graphite and high Z plasma facing materials | BP | 9 | 6.2 | no lithium | 1 |  |  |  |  | Combine with BP-2
C. Skinner | PPPL | Measurement of Li pumping efficacy | BP | 4 | 6.3 | lithium | 0.5 |  |  |  |  | Combine with BP-2
R. Maingi | ORNL | Edge characterization in high performance discharges | BP | 17 | 7 | All diagnostics | 1 | 1 | 1 | R08-3
S. Zweben | PPPL | Biased Electrodes for SOL Control | BP | 20 | 8 | BeAP | 1 | 1 | 0.5
H. Meyer | ORNL | Dependence of ELMS and Power Balance on Magnetic Balance and Fueling | BP | 15 | 9 |  | 1 | 1 | 1 |  | PEP-6
J. Canik | ORNL | ELM Destabilization by RMP | BP | 12 | 10.1 | RMP coils | 1 | 2 | 1 |  |  | Combine with BP-11 & MS XP Consider as cross-cutting?
J-K. Park | PPPL | ELM experiment with various RMP | BP | 11 | 10.2 | RMP coils | 1 |  |  |  |  | Combine with BP-12
R. Maqueda | Nova Photonics | Fast camera studies, edge turbulence & blobs, ELMs, MARFEs, etc | BP | 10 | 11 |  | 5 | 2 | 0.5 |  | DSOL-15
D. Mansfield | PPPL | Injection of Li Powder into the NSTX Scrape-off Layer | BP | 6 | 12 | Li powder injector | 1 | 2 | 0.5
L.F. Delgado-Aparicio | JHU | Role of neoclassical impurity transport in the NSTX gradient region | BP | 21 | 13 |  | 1 | 3 | 0.5
K. Tritz | JHU | Study of Type V ELMs and edge gradients | BP | 22 | 14 |  | 1 | 3 | 0.5
J.P. Allain | Purdue U | Understanding the correlation of lithium-graphite surface chemistry on plasma performance in NSTX | BP | 1 |  | LITER | 1 |  |  |  |  | Piggyback
D. Mansfield | PPPL | NSTX Lithium Conditioning Using both Dual LITER and Li Powder Injection | BP | 3 |  | LITERs, li powder | 1 |  |  |  |  | Piggyback
V. Soukhanovskii | LLNL | High flux expansion divertor - heat flux reduction and properties | BP | 8 |  | no lithium | 1 |  |  | R08-3 |  | Piggyback
Y. Raitses | PPPL | Investigation of dust production in NSTX | BP | 5 |  |  | 0 |  |  |  |  | Piggyback
C. Skinner | PPPL | Can resonant magnetic peturbations broaden the SOL heat flux profile | BP | 19 |  | RMP coils | 0 |  |  |  |  | Piggyback
Kaye | PPPL | Dependence of energy confinement on rotation | TT | 4 | 1.1 | n=3 SPAs, PCHERS, ERD | 0.5 | 1 | 1 | Joule |  | Combined with TT-18 (Delgado-Aparicio)
Delgado-Aparicio | JHU | Correlation between impurity transport and ExB shear in beam-heated NSTX H-modes | TT | 18 | 1.1 | SPAs n=3, EFC, Ne puff | 0.5 |  |  | Joule |  | Combine with TT-04 (Kaye)
Kaye | PPPL | Perturbative modulation of core rotation and assessment of core momentum transport using beam blips | TT | 5 | 2 | PCHERS, ERD, NB blips | 1 | 1 | 1 | Joule | TP6.3
Solomon | PPPL | Momentum transport studies on NSTX | TT | 6 | 3 | PCHERS, ERD, n=3 SPAs | 1 | 1 | 1 | Joule | TP-6.3
Solomon | PPPL | Energy confinement similarity experiment between NSTX and DIII-D | TT | 7 | 4 |  | 1 | 4 | 1 |  | TP-9 | Major ST topic as well
Mazzucato | PPPL | High-k plasma turbulence I | TT | 11 | 5 | Puff/use Ne, Ar, HHFW | 2 | 4 | 1 |  |  | First day
Kaye | PPPL | Effect of nRMP on L-H threshold | TT | 1 | 6 | n=3 SPAs | 1 | 6 | 1 |  | ITPA
Yuh | Nova | Magnetic shear effects on electron and ion thermal transport and momentum transport | TT | 14 | 7 | RF radial reflectometer, NB B@1MW | 2 | 7 | 1
Stutman | JHU | Field scaling of electron transport change with heating power | TT | 9 | 8 | LPI? NPA scan | 2 | 8 | 1
Mazzucato | PPPL | High-k plasma turbulence II | TT | 12 | 9 | Puff/use Ne, Ar, HHFW | 3 | 9 | 1 |  |  | Second day (needs definition)
Kaye | PPPL | beta-scaling using Li evaporation to suppress ELMs | TT | 2 | 10 | n=3 SPAs, Li | 0.5 | 10 |  |  | CDB-2 | Reassess if Li evap can reproducibly suppress ELMs
Delgado-Aparicio | JHU | Role of neoclassical impurity transport in the NSTX gradient region | TT | 17 | 11 | Ne puff, He H-mode? | 1 | 11 | 1
Kaye | PPPL | Effect of nRMP on edge intrinsic rotation | TT | 3 | 12 | ohmic H-mode development, ERD, n=3 SPAs | 0.5 | 12 |  | Joule |  | Run if without beams and RF
Stutman | JHU | Assessing magnetic electron transport in NSTX using He H-modes | TT | 10 | 13 | He H-mode plasmas | 1 | 14
Bush |  | Source of rotation in Ohmic H-modes | TT | 8 | 14
Smith | PPPL | Novel turbulence topics suitable for the NSTX high-k scattering system | TT | 12 | 15 |  | 0
Kubota | UCLA | Mean and Oscillating Turbulent Flows and Their Connection to Internal Transport Barrier Formation | TT | 13 | 16 | RF, need commissioning | 1 |  |  | Joule, R08-1 |  | Scope out first piggyback, then request dedicated run time if necessary
Ross | PPPL | Investigation of ion transport with beam modulation | TT | 15 | 17 | NPA scan, NB modulation, LITER, thesis | 1
Lee | UC Davis | NSTX H-mode measurement in conjunction with gyrocenter shift via FIReTIP system | TT | 16 |  | scan X-point, edge neutral density measurement | 1 |  |  |  |  | Originally considered by TT Combine with ASC-05 (Bell)
J. Menard | PPPL | Robustness of improved error field suppression in long-pulse discharges | ASC | 1 | 1 |  | 1 | 1 | 1
D. Gates | PPPL | Parametric study of high elongation plasmas | ASC | 2 | 2 |  | 1.5 | 2 | 1.5
J. Menard | PPPL | Impact of 2 LITER system on long-pulse discharges | ASC | 3 | 3 | LITER | 1.5 | 3 | 1.5
E. Kolemen | Princeton U. | Vertical Stability Physics and Performance Limits in Tokamaks with highly elongated tokamaks | ASC | 4 | 4 |  | 1 | 4 | 1 |  | MDC-13 IO priority
M. G. Bell | PPPL | Development and Assessment of X-point limiter plasmas | ASC | 5 | 5.1 |  | 1 | 5 | 1
Lee | UC Davis | NSTX H-mode measurement in conjunction with gyrocenter shift via FIReTIP system | ASC | 16 | 5.2 | scan X-point, edge neutral density measurement | 1 |  |  |  |  | Originally considered by TT Combine with ASC-05 (Bell)
C. E. Kessel | PPPL | HHFW into Early diverted plasmas and late (end of Ip ramp) Discharges | ASC | 6 | 6 |  | 1.5 | 6 | 1
C. E. Kessel | PPPL | Hybrid Discharges on NSTX | ASC | 7 | 7 |  | 1 | 7 |  |  | SSO-2.2
D. Humphreys | GA | Use of Nonaxisymmetric Coils for Vertical Stability Control in NSTX | ASC | 8 | 8 |  | 1 | 8
D. Humphreys | GA | Development and Performance of model based multivariable shape controllers | ASC | 9 | 9 |  | 1 | 9 |  |  | IO priority?
D. Mueller | PPPL | Low li startup | ASC | 10 | 10 |  | 0.5 | 10
V. Soukhanovskii | LLNL | H-mode fuelling optimization with high pressure multi-pulse SGI | ASC | 11 | 11 |  | 0 | 11
E. Schuster | Lehigh U. | Advanced Model-based Shape controller | ASC | 12 | 12 |  | 0 | 12
E. Schuster | Lehigh U. | Model-based rotation profile control | ASC | 13 | 13 |  | 0 | 13
R. LaHaye | General Atomics | Beta ramp down 2/1 tearing mode: study of self-stabilization | MS | 1 | 1.1 |  | 1 | 1 | 1 | Joule | MDC-4 | Combine with MS-02
R. Buttery | UKAEA | Rotation dependence of 2/1 NTM thresholds | MS | 2 | 1.2 |  | 1.5 |  |  |  |  | Combine with MS-01
S.A. Sabbagh | Columbia U. | Active RWM stabilization optimization and ITER support | MS | 3 | 2.1 | current in one RWM coil minimized | 1.5 | 2 | 1 | Joule, R09-1 | MDC-2, IIC RWM-1, DCR-096 RWM coil | Combine with MS-04
K. Tritz | Johns-Hopkins U. | SXR tomography of neon-seeded RWM stabilized plasmas | MS | 4 | 2.2 | Neon | 1 |  |  |  |  | Combine with MS-03
S.A. Sabbagh | Columbia U. | Comparison of NTV among tokamaks (n = 2 fields, nu_i scaling) | MS | 5 | 3.1 | n = 2 RWM coil | 1 | 3 | 1 | Joule | MDC-12, IIC AUX-1 | Combine with MS-06
R. Buttery | UKAEA | Testing NTV theory of error field penetration | MS | 6 | 3.2 |  | 0.5 |  |  |  |  | Combine with MS-05
S. Gerhardt/D. Gates | PPPL | Studies of the 3/2 NTM: Rotation and Beta Rampdown | MS | 7 | 4 |  | 1.5 | 4 | 1.5 | Joule | MDC-4
J. Berkery | Columbia U. | RWM stabilization physics – comparison to theory | MS | 8 | 5.1 |  | 1.5 | 5 | 1.5 | Joule, R09-1 | MDC-2, IIC RWM-1 | Combine with MS-09, MS-10
J. Berkery | Columbia U. | DIII-D/NSTX RWM joint XP – stability vs. A, rotation profile, nu_i | MS | 9 | 5.2 |  | 1.5 |  |  |  |  | Combine with MS-08
H. Reimerdes | Columbia U. | Parametric dependence RWM damping in rotating plasmas | MS | 10 | 5.3 |  | 1 |  |  |  |  | Combine with MS-08
S. Gerhardt/ J. Menard | PPPL | n=2 intrinsic error fields and RWM critical rotation | MS | 11 | 6 | n = 2 RWM coil | 1 | 6 | 1 | Joule | MDC-2, IIC RWM-1 | Combine with MS-12
S.A Sabbagh/ K.C. Shaing | Columbia U. | Island-induced neoclassical toroidal viscosity (NTV) | MS | 12 | 7 |  | 1.5 | 7 | 1 | Joule | MDC-4, MDC-12, IIC AUX-1 | Combine with MS-11
S.A. Sabbagh | Columbia U. | Deformation of RWM and multi-mode characteristics | MS | 13 | 8.1 |  | 1 | 8 | 1 |  | MDC-2, IIC RWM-1, DCR-096 RWM coil | Combine with MS-14
M. Okabayashi | PPPL | Assessment of non-rigidity in RWM feedback | MS | 14 | 8.2 |  | 1 |  |  |  |  | Combine with MS-13
S. Gerhardt | PPPL | Measurement of Halo Currents in the Lower Divertor | MS | 15 | [7 empty] | Piggyback
S. Sabbagh |  | ELM mitigation with midplane control coils | MS | 16 |  | RWM coil polarity change | 1 | ? |  |  | IO request | Consider and possibly combine with BP-11, -12
[6 empty] | Totals: | 110 |  | 46
[6 empty] | Proposals requesting/allocated runtime: | 84 |  | 46
[6 empty] | Average request/allocation: | 1.3095 |  | 1
[6 empty] | JM Guidance / TSG request: SFS | 7 |  | 4 | 0.57143
[6 empty] | Guidance / request: WPI | 6 |  | 6 | 1
[6 empty] | Guidance / request: BP | 7 |  | 10 | 1.4286
[6 empty] | Guidance / request: TT | 8 |  | 10 | 1.25
[6 empty] | Guidance / request: ASC | 5.5 |  | 7 | 1.2727
[6 empty] | Guidance / request: MS | 6.5 |  | 9 | 1.3846
Note on G1: In clude requirements for NBI power above 6MW, any HHFW heating, CHI, lithium evaporation, LPI, non-standard gases, SGI, SPA use, non-standard coil use (e.g. PF4, different polarities).
Note on H1: Total must include shot development time, equipment commissioning, etc. Assume 30 standard shots per run day.
Note on I1: 1 is the highest ranking. Numbers must be consecutive
Note on J1: Recommendation by TSG. May not represent actual assignment.

## Milestone XPs
Milestone | Description | Experiment(s) | Title | TSG Priority | TSG days | Total
Joule (08) | Evaluate the generation of plasma rotation and momentum transport, and assess the impact of plasma rotation on stability and confinement, and Evaluate MHD sources of plasma viscosity and assess impact of plasma rotation on stability, including NTM | TT-4+18 | Dependence of energy & impurity transport on rotation | =1 | 1 | 11
|  | TT-5 | Perturbative modulation of core rotation and assessment of momentum transport | =1 | 1
|  | TT-6 | Momentum transport studies on NSTX | =1 | 1
|  | TT-3 | Effect of nRMP on edge intrinsic rotation | 12
|  | TT-13 | Mean and Oscillating Turbulent Flows and Their Connection to Internal Transport Barrier Formation |  | 0
|  | MS-1+2 | Rotation dependence of 2/1 NTM thresholds | 1 | 1
|  | MS-3+4 | Active RWM stabilization optimization and ITER support | 2 | 1
|  | MS-5+6 | Comparison of NTV among tokamaks (n = 2 fields, nu_i scaling) | 3 | 1
|  | MS-7 | Studies of the 3/2 NTM: Rotation and Beta Rampdown | 4 | 1.5
|  | MS-8+9+10 | RWM stabilization and damping | 5 | 1.5
|  | MS-11+12 | Island-induced neoclassical toroidal viscosity | 6 | 2
R(08-1) | Measure poloidal rotation at low A and compare with theory | TT-6 | Momentum transport studies on NSTX | =1 | 1 | 1
|  | TT-? (suggested) | Characterization of poloidal rotation and comparison with theory | TBD
|  | TT-13 | Mean and Oscillating Turbulent Flows and Their Connection to Internal Transport Barrier Formation |  | 0
R(08-2) | Couple inductive ramp-up to CHI plasmas | SFS-1 | Central Solenoid Flux savings using Transient CHI Startup | 1 | 4 | 4
R(08-3) | Study variation and control of heat flux in SOL | BP-13 | Divertor detachment in highly-shaped high-performance H-mode plasmas |  | 1 | 4
|  | BP-17 | Edge characterization in high performance discharges |  | 1
|  | BP-18 | Characterization of the divertor heat flux width and the mid-plane SOL widths |  | 1
|  | BP-8 | High flux expansion divertor - heat flux reduction and properties |  | 0
|  | ASC-5 | Development and assessment of X-point limiter plasmas | 5 | 1
ITER request | ELM mitigation with RMP coils | BP-11 | ELM experiment with various RMP |  | 1 | 1
|  | BP-12 | ELM Destabilization by RMP |  | 0
|  | MS-16 | ELM mitigation with midplane control coils
ITER request | Assess vertical stability limits | ASC-4 | Vertical Stability Physics and Performance Limits in Tokamaks with highly elongated tokamaks | 4 | 1 | 1