Applicability

This procedure is applicable to procurements made by PPPL staff for the NSTX project.

Introduction

This procedure describes the steps and guidance for NSTX procurements.  All procurements shall be in accordance with PPPL Procurement Policies and Procedures; guidance is available, when necessary, via the PPPL Procurement Division.

Referenced Documents

| NSTX-PROC-005 | Preparation, Review & Approval of Specifications and Statements of Work |
| --- | --- |

| PPPL Procurement Policies and Procedures |  |
| --- | --- |

Definitions

| Mission Critical | Items or services which have the potential to impact the NSTX critical path or have significant ES&H, quality, or project consequences. The decision on whether a particular item or service is mission critical is made by the appropriate WBS Manager. If a procurement is determined to be critical, the critical box of the requisition form must be checked. Otherwise, either the minor or major box must be checked. |
| --- | --- |

Procedure

A.	Procurements ≥ $50K and/or mission critical

| Responsibility | Action |
| --- | --- |

| NSTX Requisitioner | 1. Develops specification or statement of work per NSTX-PROC-005. Specifications or statements of work for hardware fabrication or software development shall require the prospective supplier to submit a QA Plan and a Manufacturing/Inspection/Test Plan (MIT). |
| --- | --- |

|  | 2. Involves Quality Assurance and Procurement in the review of the specification or statement of work. E/NL/P&S (Safety) shall also be included if appropriate. Requests minimally two copies of all deliverables — one for storage by the NSTX Document Administrator and one for use by the requisitioner. |
| --- | --- |

| Reviewer | 3. Reviews documents and provides feedback to the NSTX Requisitioner. |
| --- | --- |

| NSTX Requisitioner | 4. Incorporates comments, as appropriate. Contacts reviewers to discuss those comments that were not incorporated. Obtains signatures of Quality Assurance and Procurement on these documents. Sends a copy of final, signed specification or statement of work to the reviewers. |
| --- | --- |

|  | 5. Transmits final specification or statement of work with completed requisition form to Procurement. All requisition forms must be signed by the NSTX Engineering Manager or higher management and the NSTX Project Control Officer. The NSTX Engineering Manager shall judge, based on cost, complexity, and criticality — • the adequacy of the procurement documentation which accompanies the requisition, • the adequacy of the proposed documentation requested of prospective suppliers, • and the procedure for proposal evaluation. |
| --- | --- |

| Procurement Representative | 6. Develops a Request for Proposal (RFP) which should include a list of weighted evaluation criteria developed jointly by the requisitioner and the Procurement Representative. (ref. PPPL Procurement Policies and Procedures, Section 2-15) |
| --- | --- |

|  | 7. Transmits/receives all correspondance to/from prospective vendors, and maintains file of records of same. |
| --- | --- |

| Requisitioner | 8. Upon receipt of proposals, assembles committee to review the proposals. The committee shall minimally include the requisitioner, Quality Assurance, and Procurement Representative. |
| --- | --- |

| Committee | 9. Visits, as a full committee or selected members, the facilities of the most likely prospective supplier(s) to confirm the technical capability and manufacturing competence. |
| --- | --- |

|  | 10. Documents recommendation for selection of a supplier in a memorandum. The memorandum shall include as a minimum: • nature and purpose of the procurement • identification, revision number and issue date of specification or SOW and RFP • names and addresses of offerors • ranking of proposals with respect to evaluation criteria • recommendation for selection of vendor. |
| --- | --- |

| Responsible WBS Manager | 10. Signs recommendation indicating approval. |
| --- | --- |

| Requisitioner | 11. Following completion of contractual activities, provides Drafting with copies of all drawings and the NSTX Document Administrator with copies of all other documentation deliverables, such as Manufacturing, Inspection, and Test Plans or Operating Manuals. |
| --- | --- |

B.	Procurements ≥$5K AND ≤$50K AND NOT mission critical

General guidelines are listed in this section subject to the discretion of the NSTX Engineer Manager on a case by case basis.

| Responsibility | Action |
| --- | --- |

| NSTX Requisitioner | 1. Provides all necessary information regarding description and required characteristics of the equipment and/or services using a specification or statement of work (per NSTX-PROC-005) unless the procurement can be completely described on the face of the requisition. Includes quality and ES&H requirements, as appropriate. These may be provided as attachments to the requisition. |
| --- | --- |

|  | 2. Obtains the approval signatures of Quality Assurance, the appropriate WBS Manager, the NSTX Engineering Manager, and the NSTX Project Control Officer on the specification, statement of work, or requisition. |
| --- | --- |

|  | 3. Documents approval to proceed with the purchase via a memorandum to project file from the Requisitioner to the Procurement Representation with an approval signature by the responsible WBS Manager. |
| --- | --- |

|  | 4. Following completion of contractual activities, provides Drafting with copies of all drawings and the NSTX Document Administrator with copies of all other documentation deliverables, such as Manufacturing, Inspection, or Test Plans or Operating Manuals. |
| --- | --- |