National Spherical Torus Experiment

NSTX

Configuration Control

D R A F T   G

NSTX-PROC-006-00G

Revision 0

mm dd, yy

______________________________

Masayuki Ono

NSTX Project Manager

Applicability

This procedure is applicable to the entire NSTX Project.

Introduction

This procedure describes how the configuration of NSTX is controlled. This procedure covers changes to the following documents which define the configuration of NSTX:

The NSTX Project Execution Plan (PEP)

The NSTX Quality Assurance Plan (QAP)

The NSTX Documents & Records Plan

The NSTX Program Definition Statement (PDS)

The NSTX Project Requirements Document (PRD)

The NSTX General Requirements Document (GRD)

The NSTX System Requirements Documents (SRDs)

The NSTX Environmental Assessment (EA)

The NSTX Safety Assessment Document, if generated, (SAD)

The NSTX System Design Descriptions (SDDs)

The NSTX Baseline Cost and Schedule

NSTX Drawings

Further information on these documents may be found in the NSTX Documents & Records Plan.

Referenced Documents

| NSTX-PLAN-PEP | NSTX Project Execution Plan |
| --- | --- |

| NSTX-PLAN-DOC-REC | NSTX Documents and Records Plan |
| --- | --- |

| EMD-001 | Preparing and Processing a Drawing Change Notice (DCN) - Engineering and Technology Development Department Procedure |
| --- | --- |

| TOP 23.009 | Calculation Development and Checking |
| --- | --- |

Procedure

Note:	NSTX documents do not come under configuration control until the first signed off version.

A. Configuration Changes

| Responsibility | Action |
| --- | --- |

| NSTX Staff Member | 1. Identifies need for change to the NSTX Configuration. |
| --- | --- |

|  | 2. Completes the NSTX Configuration Change form, page 1, contained in Attachment 1 of this procedure. Provides as much detail as necessary to adequately describe the proposed change. Additional sheets may be used as necessary. Obtains number for the form by contacting the NSTX Document Administrator. Note that changes may occur in the requirements or design. Changes to reflect as-built conditions are implemented via the NSTX Field Change Request (see section B). A change may effect both requirements and design. Requirements changes typically impact the PDS, PRD, GRD, PEP, QAP, EA, SAD, or one of the SRDs. These proposed changes should be clearly identified on the applicable pages of the document and attached to the Configuration Change Form. Design changes typically impact one of the SDDs, ISTPs, or drawings. Details on these changes need not be attached to the Configuration Change Form. |
| --- | --- |

|  | 3. Sends completed form to the NSTX Engineering Manager with a copy to the NSTX Document Administrator. Email is preferred. |
| --- | --- |

| NSTX Engineering Manager | 4. Completes the top of page 2 of the NSTX Configuration Change form classifying the change per the PEP and specifying the required reviews and calculation checks. |
| --- | --- |

|  | 5. Sends proposed configuration change form to the Chairperson of the either the MRB or TRB, as appropriate. The requirements for committee review are defined in the PEP. |
| --- | --- |

| MRB or TRB Chairperson | 6. Determines best method to effect committee review. Options include emailing form to committee members with specified response dates or formal committee meetings. |
| --- | --- |

|  | 7. Using information from the committee members, either approves the change, denies the change, OR discusses concerns about the change with the originator. Once a decision is made, completes the form and forwards the signed original to the NSTX Document Administrator. Note: Approval is not granted until all required signatures have been obtained. |
| --- | --- |

| NSTX Document Administrator | 8. Determines if additional approvals are necessary and, if so, works with NSTX management to obtain them. Once all approvals have been obtained, forwards a copy of the completed form to the originator and Central Drafting. |
| --- | --- |

|  | 9. Maintains records of all approved NSTX Configuration Change Requests and their status on the NSTX File Server. Status values are pending, denied, approved, completed, or cancelled. If pending, the status should indicate the level of approvals already received. |
| --- | --- |

| Originator | 10. Implements change. Signs bottom of page 2 of approved NSTX Configuration Change Request when change has been completed or cancelled and forwards completed copy to the NSTX Document Administrator. Note: A change to the PEP, QAP, Documents & Records Plan, PDS, PRD, GRD, SRD, EA, or SAD are considered to be "implemented" with the approval of the corresponding NSTX Configuration Change Request. Incorporating the changes into the actual procedure may be delayed until later. The NSTX Document Administrator is responsible for maintaining records on the status of incorporation of these changes into the original document. |
| --- | --- |

B. Field Changes

An NSTX Field Change Request is used to expedite changes to drawings or documentation to reflect the "as-built" condition.  An FCR is NOT to be used for changes that impact the PDS, PRD, GRD, PEP, QAP, EA, SAD, SRD, SDD, or Documents and Records Plan nor is it to be used to add new scope or significant design changes within a design document or drawing. Examples of appropriate uses for the FCR are minor changes to fabrication or assembly techniques, minor changes to accommodate field interferences, or editorial or drawing error corrections.

| Responsibility | Action |
| --- | --- |

| NSTX Staff Member | 1. Describes the proposed change and the reasons for the change on the NSTX Field Change Request (attachment 3). Identifies all drawings that are involved in the proposed change. |
| --- | --- |

|  | 2. Obtains number for the form by contacting the NSTX Document Administrator. |
| --- | --- |

|  | 3. Marks up the required changes in red ink, annotated with the FCR number. |
| --- | --- |

| NSTX WBS Manager | 4. Approves FCR. Sends a copy of the approved FCR to the Originator and Drafting. Sends the original FCR to the NSTX Document Administrator. |
| --- | --- |

C. Peer Reviews

| Responsibility | Action |
| --- | --- |

| Cognizant Design Engineer | 1. Proposes the attendees for the peer review. |
| --- | --- |

| Responsible WBS Manager | 2. Approves list of attendees. |
| --- | --- |

| Cognizant Design Engineer | 3. Conducts peer review. Documents the results of the peer review in a memorandum listing date, time, and attendees, and questions, concerns, and recommendations that were identified and their resolution. The chit form of attachment 4 may be used for the documentation. |
| --- | --- |

|  | 4. Forwards documentation to the NSTX Document Administrator and copies attendees. |
| --- | --- |

| NSTX Document Administrator | 5. Maintains peer review documentation with the original NSTX Configuration Control Form. |
| --- | --- |

D. Design Reviews

| Responsibility | Action |
| --- | --- |

| NSTX Engineering Manager | 1. Selects the Design Review Chairperson. |
| --- | --- |

| Design Review Chairperson | 2. Discusses the design change with the Cognizant Design Engineer and jointly selects the members of the Review Board and the other individuals to be invited to the review. The Review Board should contain representatives from systems impacted by the design to be reviewed. Invitees, it not part of the review board, should include the NSTX ES&H Engineer and the NSTX QA Engineer. |
| --- | --- |

| Cognizant Design Engineer | 3. Schedules the time and place for the review meeting and issues notification to the Board and other invitees at least one week prior to the review. |
| --- | --- |

|  | 4. Supplies a documentation package to the invitees at least three working days before the review. Note: The one week and/or three day time requirements may be waived with the approval of the NSTX Engineering Manager. |
| --- | --- |

|  | 5. Makes presentation at the design review. Includes resolution of chits from any previous design reviews. |
| --- | --- |

| Review attendees | 6. Document on CHIT forms, Attachment 4, questions, concerns, and recommendations raised during the review that were not adequately resolved. |
| --- | --- |

| Design Review Chairperson | 7. Facilitates the Design Review Board responses/comments on CHITs after the conclusion of the design review. |
| --- | --- |

|  | 8. Documents the results of the Design Review on the NSTX Design Review Results Form, attachment 5. Attaches the completed CHIT forms and distributes to the Review Board Members, invited attendees, and the Cognizant Design Engineer. Forwards the original package to the NSTX Document Administrator. |
| --- | --- |

| NSTX Document Administrator | 9. Maintains all design review documentation with the original NSTX Configuration Change form. |
| --- | --- |

| Cognizant Design Engineer | 10. Responds to the recommendations of the Design Review Board by dispositioning the CHITs. |
| --- | --- |

| NSTX Engineering Manager | 11. Reviews the completed CHITs and concurs with the Design Engineer's disposition by signing each CHIT. Sends the completed CHIT to the NSTX Document Administrator. Note: All design review CHITs may be resolved prior to declaring the NSTX Configuration Change complete (i.e. actions must be completed, or the CHIT disposition determined to be "Other", "Out-of-scope", or "Disagree." |
| --- | --- |

E. Calculation Checks

The checking of all calculations required by the NSTX Configuration Change form should be performed according to procedure 23.009.

Attachments

Attachment 1:	NSTX Configuration Change Request Form

Attachment 2:	NSTX Drawing Log Sheets

Attachment 3:	NSTX Field Change Request

Attachment 4:	NSTX Design Review Chit

Attachment 5:	NSTX Design Review Results Form

NSTX CONFIGURATION CHANGE		ID #  			Rev. #

Cog. Name							Date

(printed and signature)

Provide a title for the change:

Cost Center: 			Work Package:			Job #

Type of change:	Requirement 			Design

Description and justification:

Cost and Schedule Impact:     Change to scope? 	Yes 		No

Estimated cost  					Estimated impact on schedule

Check and/or list documents impacted by this change:

__  PDS (rev. __)*	__ PRD (rev. __)*	__ GRD (rev. __)*	__ PEP (rev. __)*

__  QAP(rev. __)*	__ EA  (rev. __)*	__ SAD (rev. __)*	__ Doc&Recs Plan (rev. __)*

__ SRD (doc # _______)*	__ SDD (doc # _______)	__ NSTX ISTP  (doc # _______)

* For these documents, attach copies of the pages to be changed with the proposed changes indicated in red.

Other documents impacted:

List  drawings  impacted by this change and their revision number:   None

| DCN # | transmitted/ disposition | Drawing Numbers | Rev. # | Sheet # | TITLE | TFTR Drawing? |
| --- | --- | --- | --- | --- | --- | --- |

Shaded columns are for Drafting's use only. Note that all red-lined drawings must have a completed DCN appliqué to be accepted by Drafting. See EMD-001 for details. Attach additional drawing log sheets, if necessary.

NSTX CONFIGURATION CHANGE		ID #  			Rev. #

To be completed by NSTX Project Engineer:

Classification of change:  A 		B 		C 		D 		E

(from NSTX-PLAN-PEP)

Required reviews:   None 		Peer 		FDR 		PDR 		CDR

Independent calculation checking is required for the following:

NSTX Proj. Eng. 							date:

Approvals (by classification): - Signatures and dates required:

(A, B, C)

(MRB Approval - NSTX Project Director, Chair)

(A, B, C)

(NSTX Program Director)

(A, B)

(PPPL Senior Management)

(A)

(Department of Energy)

(D, E)

(TRB Approval - NSTX Project Engineering Manager, Chair)

(D)

(NSTX Project Director)

Change completed:   The change indicated by this form has been implemented,  documents have been updated, and approved DCN's have been transmitted to Drafting.

Cog. Name							Date

(printed and signature)

Change cancelled/withdrawn:  The change indicated by this form has been cancelled:

Cog. Name							Date

(printed and signature)

| DCN # | transmitted/ disposition | Drawing Numbers | Rev. # | Sheet # | TITLE | TFTR Drawing? |
| --- | --- | --- | --- | --- | --- | --- |

NSTX FIELD CHANGE REQUEST		ID

Drawings to be changed

Justification for the change

Approved 						   Date

(WBS Manager)

NSTX Design Review CHIT

{COPY OF TFTR CHIT FORM RELABELLED NSTX CHIT FORM WILL BE COPIED HERE WHEN AVAILABLE ELECTRONICALLY.}

NSTX Design Review Results

{COPY OF TFTR Design Review Results FORM RELABELLED NSTX CHIT FORM WILL BE COPIED HERE WHEN AVAILABLE ELECTRONICALLY.}