National Spherical Torus Experiment

NSTX

PROJECT DEFINITION STATEMENT

NSTX-RQMT-PDS-034

DRAFT Revision 1

October 9, 1996

Masa Ono		Martin Peng		NSTX Project Manager		NSTX Program Manager

John Schmidt		Rob Goldston

PPPL Advanced Projects Department Head		PPPL Associate Director for Research

Ron Davidson		Greg Pitonik			PPPL Director		DOE NSTX Project Manager

Princeton Area Office

Jeff Hoy

DOE NSTX OFES Project Manager

Cherri Langenfeld		N. Anne Davies

Manager, DOE Chicago Field Office		Director, DOE Office of Fusion Energy

RECORD OF REVISIONS

| Revision | Date | ECP | Description of Change |
| --- | --- | --- | --- |

| 0 | 5/96 | Sinnis | Several adjustments in precision of statements |
| --- | --- | --- | --- |

| 1 | 10/96 | Ono | Revised name of NSTX to National Spheridal Torus Experiment, incorporation of ECSR comments, and updated TPC. |
| --- | --- | --- | --- |

TABLE OF CONTENTS

PREFACE	1

1 PERFORMANCE REQUIREMENTS	1

1.1 Device Parameters	1

1.2 Heating and Current Drive	2

1.3 Operational Requirements	2

1.4 Diagnostics	2

2 COST OBJECTIVES	3

3 SCHEDULE OBJECTIVES	3

PREFACE

The mission of the National Spherical Torus Experiment (NSTX) is to investigate, with broad participation by leading laboratories and universities, the physics priciples of:

• Non-inductive start-up, current sustainment and profile control;

• Confinement and transport;

• Pressure limits and pressure gradient driven currents;

• Scrape-off layers and divertors; and

• Stability and disruption-free operation,

in a low aspect ratio (spherical) torus as a plasma confinement innovation.  These principles are to be investigated in the scientifically interesting regimes relevant to the Volume Neutron Source (VNS) and future power plants, characterized by:

• High average βτ (plasma pressure/applied toroidal field pressure) ~ 25 - 45 %;

• High pressure gradient d;lriven current fraction ~ 50 - 90 %;

• Fully relaxed, non-inductively sustained current profile;

• Collisionless plasmas with high temperatures and densities; and

• Low aspect ratio R/a ≥ 1.25 with high elogation κ ≥ 2.

This document defines the top-level requirements for the device performance (Section 1),  cost (Section 2), and schedule (Section 3) that must be satisfied by the NSTX Design and Construction Project. The major participants of the Project will be the Priceton Plasma Physics Laboratory (PPPL), the Oak Ridge National Laboratory (ORNL), the University of Washington, and Columbia University.

More detailed physics performance requirements are summarized in the Project Requirements Document (PRD), engineering performance requirements in the General Requirements Document (GRD), and component performance requirements for the elements of the Work Breakdown Structure (WBS) the System Requirements Documents (SRDs).

1 PERFORMANCE REQUIREMENTS

1.1 Device Parameters

The NSTX device shall be designed to provide single null divertor, double null divertor, and inboard limited naturally diverted discharges, in hydrogen and deuterium.  The device shall be capable of operation with the following parameters:

• Plasma Major Radius 	R0  	= 0.8m;

• Plasma Minor Radius	a    	= 0.64m;

• Applied Toroidal Field	BT 	= 3.2kG at R0 ;

• Plasma Current 	Ip	= 1.0MA;

• Plasma Elongation	κx 	≥ 2.2 ; and

• Plasma Triangualraity	δx 	~ 0.4; and

• Plasma Pulse lengths	τpp	≥ 1 second (inductive operation)

≥ 5 seconds (driven current operation)

1.2 Heating and Current Drive

The NSTX facility shall be equipped to deliver to the plasma and handle the following energy inputs for startup, heating and current drive:

• 6 MW of High Harmonic Fast Wave (HHFW) for up to 5 seconds;

• 2 MJ of Coaxial Helicity Injection (CHI) during 5 to 10 milli-seconds; and

• 200kW of Electron Cyclotron Heating (ECH) for up to 5 milli-seconds.

The NSTX facility design will further account for the possibility of adding and handling, as future upgrades, the following:

• 200kW of ECH for up to 0.1 seconds;

• 15 MW of CHI for up to 5 seconds; and

• 5 MW of Neutral Beam Injection (NBI) for up to 5 seconds.

1.3 Operational Requirements

The NSTX facility shall be capable of:

• A 300 second pulse repetition rate;

• Up to 96 pulses per day;

• Up to 5 days of operation per week;

• Up to 3 weeks of operation per month;

• Up to 9 months of operation per year;

• Up to 10 years of operation; and

• Up to 130,000 total pulses.

1.4 Diagnostics

NSTX shall be equipped with diagnostic systems as required for machine operation, as well as plasma, plasma facing component, and vacuum chamber measurements needed by the NSTX Research Program to fulfill the NSTX mission.  The required diagnostics are listed in the PRD.

2 COST OBJECTIVES

The NSTX Total Project Cost (TPC) for design, fabricastion, and assembly shall not exceed $22.9 million (as spent), predicated on the start of construction in Fiscal Year 1997, and the following funding profile:

| Fiscal Year | Funding |
| --- | --- |

| 1996 | $ 1.0 M |
| --- | --- |

| 1997 | $ 4.7 M |
| --- | --- |

| 1998 | $ 10.4 M |
| --- | --- |

| 1999 | $ 6.8 M |
| --- | --- |

3 SCHEDULE OBJECTIVES

Given this start of construction and funding provile, the NSTX Design and Construction Project shall be completed and produce the first plasma by the end of December 1998.

DOE Level 1 Project Milestones are as follows:

DESCRIPTION	BASELINE	ACTUAL

•	Complete DOE Project Validation	April 1995	April 1995

•	Complete DOE Physics Validation 	June 1995	June 1995

•	Complete Environmental Assessment	Dec 1995	Dec 1995

•	Start NSTX Construction	October 1996

•	Commence Operations (First Plasma)	April 1999

Additional DOE Level 2 Control Milestones will be developed in the NSTX Project Execution Plan.

A pulse is defined as a plasma discharge at the device parameters.

The pulse length is the period of constant applied toroidal filedl and full plasma current tests.

The NSTX facility includes the experimental device and all support systems.

As finalized following the NSTX Engineering, Cost, and  Schedule Review.

The actual amount to be spent, which includes escalation factors to account for inflation.

Construction starts wilth procurement and fabrication of major NSTX components, while the preparation of existing facilities such as removing PLT and clearing the PLT test cell may start earlier.

First plasma is defined as an ohmically heated discharge.