Applicability

This procedure is applicable to the entire NSTX Project.

Introduction

This procedure describes how the configuration of NSTX is controlled. This procedure covers changes to the following documents which define the functional or  technical requirements or the design configuration of NSTX:

The NSTX Project Requirements Document (PRD)

The NSTX General Requirements Document (GRD)

The NSTX System Requirements Documents (SRDs)

The NSTX System Design Descriptions (SDDs)

The NSTX Baseline Cost and Schedule

NSTX Drawings

or relevant lower level NSTX design documents.

Further information on these documents may be found in the NSTX Documents & Records Plan.

Referenced Documents

| NSTX-PLAN-PEP | NSTX Project Execution Plan |
| --- | --- |

| NSTX-PLAN-DOC-REC | NSTX Documents and Records Plan |
| --- | --- |

| EMD-001 | Preparing and Processing a Drawing Change Notice (DCN) - Engineering and Technology Development Department Procedure |
| --- | --- |

| NSTX-PROC-004 | Design Verification (Covers calculation checking, drawing checking, and reviews) |
| --- | --- |

| NSTX-PROC-035 | Document Distribution and Control |
| --- | --- |

Procedure

Note:	NSTX documents do not come under configuration control until the first signed off version.

A. Configuration Changes

| Responsibility | Action |
| --- | --- |

| NSTX Cog. Engineer | 1. Identifies need for change to the NSTX Configuration. |
| --- | --- |

|  | 2. Completes the NSTX Configuration Change form, page 1, contained in Attachment 1 of this procedure. Provides as much detail as necessary to adequately describe the proposed change. Additional sheets of paper may be used as necessary with the number of the change form on them. Obtains number for the form from the NSTX Document Administrator. Electronic versions of the form may be found on the NSTX File Server in the folder labelled “Forms.” Note that changes may occur in the functional, technical, or design requirements. A change may effect both requirements and design. Requirements changes typically impact the PRD, GRD, or one of the SRDs. These proposed changes should be clearly identified on the applicable pages of the document and attached to the Configuration Change Form. Design changes typically impact one of the SDDs, ISTPs, or drawings. Details on these changes (specific changes to documents or drawings) should be attached to the Configuration Change Form if available at the time the form is completed. Changes to higher level NSTX controlled documents, projects, standards, or guides are implemented via the NSTX Document Distribution and Control procedure. |
| --- | --- |

|  | 3. Obtains approval signature of WBS Manager on configuration change form. |
| --- | --- |

|  | 4. Sends completed form to the NSTX Engineering Manager with a copy to the NSTX Document Administrator. |
| --- | --- |

| NSTX Engineering Manager | 5. Reviews the form for completeness, consistency, and appropriateness of content. Determines if the proposed change impacts other NSTX documents not indicated on the form and adds this information to the form. |
| --- | --- |

|  | 6. Attaches page 2 of the form. |
| --- | --- |

|  | 7. Completes the bottom of page 1 of the NSTX Configuration Change form classifying the change per the PEP and specifying the required reviews and calculation checks. The requirements for classification of changes are copied from the PEP and are contained in Attachment 4 for easy reference. |
| --- | --- |

|  | 8. Sends proposed configuration change form to both the Chairperson of the Management Review Board (MRB) and Technical Review Board (TRB). The classification of the change clearly indicates which Board is responsible for the next level of approval. |
| --- | --- |

| MRB or TRB Chairperson | 9. Determines best method to effect committee review. Options include distributing form to committee members with specified response dates or formal committee meetings. |
| --- | --- |

|  | 10. Using information from the committee members, either approves the change, denies the change, OR discusses concerns about the change with the NSTX Cog and then approves or denies. Once a decision is made, completes the form and forwards the signed original to the NSTX Cog. Engineer and sends a copy to the NSTX Document Administrator. Note: Approval is not granted until all required signatures have been obtained. |
| --- | --- |

| NSTX Cog.Engineer | 11. If additional approvals are necessary, works with NSTX management to obtain them. As approvals are obtained, sends copies of the form to the NSTX Document Administrator. |
| --- | --- |

| NSTX Document Administrator | 12. Once all approvals have been obtained, forwards a copy of the completed form to Central Drafting. |
| --- | --- |

|  | 13. Maintains records of all approved NSTX Configuration Change Requests and their status on the NSTX File Server. Status values are pending, denied, doc/dwg changes completed - installation approval rqrd, doc/dwg changes completed - installation rqrd, completed, or cancelled. If pending, the status should indicate the level of approvals already received. |
| --- | --- |

| NSTX Cog.Engineer | 14. Implements change. Signs bottom of page 2 of approved NSTX Configuration Change Request when appropriate stage of the change has been completed or cancelled and forwards completed copy to the NSTX Document Administrator. Note: A change to the PRD, GRD, or SRD are considered to be "implemented" with the approval of the corresponding NSTX Configuration Change Request. Incorporating the changes into the actual procedure may be delayed until later. The NSTX Document Administrator is responsible for maintaining records on the status of incorporation of these changes into the original document. |
| --- | --- |

B. Field Changes

An NSTX Field Change Request (FCR) is the authorizing document used to expedite changes during fabrication and installation to drawings or documentation to reflect the "as-built" condition.  An FCR is NOT to be used for changes that impact the PDS, PRD, GRD or SRDs, nor is it to be used to add new scope or significant design changes within a design document or drawing. Examples of appropriate uses for the FCR are minor changes to fabrication or assembly techniques, minor changes to accommodate field interferences, or editorial or drawing error corrections.

| Responsibility | Action |
| --- | --- |

| NSTX Cog | 1. Describes the proposed change and the reasons for the change on the NSTX Field Change Request (attachment 3). Identifies all drawings that are involved in the proposed change. |
| --- | --- |

|  | 2. Obtains number for the form from the NSTX Document Administrator. |
| --- | --- |

|  | 3. Marks up the drawing with the required changes in red ink, annotated with the FCR number. Changes should be legible. |
| --- | --- |

| WBS Manager | 4. Approves FCR. |
| --- | --- |

| NSTX Engineering Manager | 5. Approves FCR. Part of the approval is to assure that changes do not impact higher level documents, such as the SRD, or add new scope or represent a significant design change. Sends copies of the approved FCR to the NSTX Cog. and Drafting. Sends the original FCR to the NSTX Document Administrator. |
| --- | --- |

Attachments

Attachment 1:	NSTX Configuration Change Request Form

Attachment 2:	NSTX Drawing Log Sheets

Attachment 3:	NSTX Field Change Request

Attachment 4:	NSTX Change Classification (from PEP)

NSTX CONFIGURATION CHANGE	ID #		Rev. #

NOTE:  All signatures on this form require a printed name, signature, and date.

NSTX Cog		Date

Provide a title for the change:

CC/WP/Job #: 			Type of change:	Rqmt  		Design

Description and justification:

Cost and Schedule Impact:	Change to scope? 	Yes 		No

Estimated cost  		Estimated impact on schedule

Check and/or list documents impacted by this change:

__ PRD (rev. __)*	__ GRD (rev. __)*	__ SRD (doc # _______)*	__ SDD (doc # _______)

* For these documents, attach copies of the pages to be changed with the proposed changes indicated in red.

Other documents impacted:

Does this change: Affect the operation of any other systems?	Yes 		No

Require changing calculations that justified the original design?   	Yes 		No

If any drawing changes are involved, attach an NSTX Drawing Log Sheet to this form.  Otherwise check the following:     		No drawing changes are involved in this configuration change.

Signature  NSTX Cog

Signature  WBS Mgr

To be completed by the NSTX Project Engineer:

Classification:	 A 		B 		C 		D 		E

Required reviews:   	None 		Peer 		FDR 		PDR 		CDR

Independent calculation checking is required for the following:

Approval required prior to installation?  	Yes 			No 		N/A

Approved NSTX Proj. Eng.

NSTX CONFIGURATION CHANGE	ID #		Rev. #

Approvals (by classification): - Signatures and dates required:

(A, B, C)

(MRB Approval - NSTX Project Director, Chair)

(A, B, C)

(NSTX Program Director)

(A, B)

(PPPL Director, if A,  Safety Review Cmt & Advanced Projects Dept. Head, if B)

(A)

(Department of Energy NSTX Project Manager)

(D, E)

(TRB Approval - NSTX Project Engineering Manager, Chair)

(D)

(NSTX Project Director)

Docs/Dwgs changes completed:   The document changes indicated by this form has been implemented and approved DCN's have been transmitted to Drafting.

NSTX Cog.			Date

Installation Approval:   The changes indicated by this form are released for fabrication and installation. (required for software and hardware changes only)

NSTX Eng. Mgr..			Date

Installation Complete:   The changes indicated by this form are completed. (required for software and hardware changes only)

NSTX Cog.			Date

Change cancelled/withdrawn:  The changes indicated by this form have been cancelled:

NSTX Cog.			Date

Change Request Denied:   The changes indicated by this form are denied

NSTX Eng. Mgr..			Date

| DCN # | transmitted/ disposition | Drawing Numbers | Rev. # | Sheet # | TITLE | TFTR Drawing? |
| --- | --- | --- | --- | --- | --- | --- |

NSTX FIELD CHANGE REQUEST	ID

NOTE:  All signatures on this form require a printed name, signature, and date.

Drawings to be changed

Justification for the change

Initiated

(NSTX Cog)

Approved

(WBS  Manager)

Approved

(NSTX Engineering Manager)

NSTX CHANGE CLASSIFICATIONS

This information is copied directly from the NSTX Project Execution Plan (PEP) and is included here for informational purposes only.

Table 9-2 of the PEP

| Category | Highest Level Approval | Criteria |
| --- | --- | --- |

| A | DOE | • Change Total Project Cost (TPC) • Change Key (Level 0/1) or Control (Level 2) Milestones • Significant ES&H impacts (Requiring changes to the EA) • Out-of-Scope Changes requiring use of Contingency funds not already converted to Management Reserve • Change PDS or PRD |
| --- | --- | --- |

| B | PPPL Senior Management | • Change SAD |
| --- | --- | --- |

| C | NSTX Program Director | • Change GRD |
| --- | --- | --- |

| D | NSTX Project Director | • Change SRD, SDD • In-Scope changes >$50K • Schedule impact that requires changes to NSTX Level 3 milestones |
| --- | --- | --- |

| E | NSTX Project Engineering Manager | • In-Scope changes < $50K • Schedule impact that requires changes to NSTX Project Schedules without impacting Level 3 Milestones • Change controlled drawings • Change functional interface requirements |
| --- | --- | --- |