Applicability

This procedure is applicable to procurements made by PPPL staff for the NSTX project.

Introduction

This procedure describes the steps and guidance for NSTX procurements.  All procurements shall be in accordance with PPPL Procurement Policies and Procedures; guidance is available, when necessary, via the PPPL Procurement Division.

Referenced Documents

| NSTX-PROC-005 | Preparation, Review & Approval of Specifications and Statements of Work |
| --- | --- |

| PPPL Procurement Policies and Procedures |  |
| --- | --- |

Definitions

| Mission Critical | Items or services which have the potential to impact the NSTX critical path or have significant ES&H, quality, or project consequences. The decision on whether a particular item or service is mission critical is made by the appropriate WBS Manager. |
| --- | --- |

Procedure

A.	Procurements ≥ $50K and/or mission critical

| Responsibility | Action |
| --- | --- |

| NSTX Requisitioner | 1. Develops specification or statement of work per NSTX-PROC-005. Specifications or statements of work for hardware fabrication or software development shall require the prospective supplier to submit a Manufacturing/Inspection/Test Plan (MIT) and appropriate quality planning documentation - usually a QA Plan or QA Program Manual or both. |
| --- | --- |

|  | 2. Involves Quality Assurance and Procurement in the review of the specification or statement of work. ES&H shall also be included if ES&H issues are involved. Requests minimally two copies of all deliverables—one for use by the applicable reviewer (QA, ES&H, the requisitioner, etc.) and the other to be compiled by the requisitioner and provided to the NSTX Document Administrator for storage. |
| --- | --- |

| Reviewer | 3. Reviews specification or statement of work and provides feedback to the NSTX Requisitioner. |
| --- | --- |

| NSTX Requisitioner | 4. Incorporates comments, as appropriate. Contacts reviewers to discuss those comments that were not incorporated. Obtains signatures of Quality Assurance on these specifications or statements of work. Sends a copy of final, signed specification or statement of work to the reviewers. |
| --- | --- |

|  | 5. Transmits final specification or statement of work with completed requisition form to Procurement. All requisition forms must be signed by the NSTX Engineering Manager or higher management and the NSTX Project Control Officer. The NSTX Engineering Manager shall judge, based on cost, complexity, and criticality — • the adequacy of the procurement documentation which accompanies the requisition, • the adequacy of the proposed documentation requested of prospective suppliers, • and the procedure for proposal evaluation. |
| --- | --- |

| Procurement Representative | 6. Develops a Request for Proposal (RFP) which should include a list of weighted evaluation criteria developed jointly by the requisitioner and the Procurement Representative. (ref. PPPL Procurement Policies and Procedures, Section 2-15) |
| --- | --- |

|  | 7. Transmits/receives all correspondence to/from prospective vendors, and maintains file of records of same. |
| --- | --- |

| Requisitioner | 8. Upon receipt of proposals, assembles committee to review the proposals. The committee shall minimally include the requisitioner, Quality Assurance, and Procurement Representative. |
| --- | --- |

| Committee | 9. Visits, as a full committee or selected members, the facilities of the most likely prospective supplier(s) to confirm the technical capability and manufacturing competence. |
| --- | --- |

|  | 10. Documents recommendation for selection of a supplier in a memorandum. The memorandum shall include as a minimum: • nature and purpose of the procurement • identification, revision number and issue date of specification or SOW and RFP • names and addresses of offerors • ranking of proposals with respect to evaluation criteria • recommendation for selection of vendor. |
| --- | --- |

| Responsible WBS Manager | 10. Signs recommendation indicating approval. |
| --- | --- |

| Requisitioner | 11. Following completion of contractual activities, provides Drafting with copies of all drawings and the NSTX Document Administrator with copies of all other documentation deliverables, such as Manufacturing, Inspection, and Test Plans or Operating Manuals. See attachment 1 for guidance. |
| --- | --- |

B.	Procurements <$5K AND ≤$50K AND NOT mission critical

General guidelines are listed in this section subject to the discretion of the NSTX Engineer Manager on a case by case basis.

| Responsibility | Action |
| --- | --- |

| NSTX Requisitioner | 1. Provides all necessary information regarding description and required characteristics of the equipment and/or services using a specification or statement of work (per NSTX-PROC-005) unless the procurement can be completely described on the face of the requisition. Includes quality and ES&H requirements, as appropriate. These may be provided as attachments to the requisition. |
| --- | --- |

|  | 2. Obtains the approval signatures of Quality Assurance, the appropriate WBS Manager, the NSTX Engineering Manager, and the NSTX Project Control Officer on the specification, statement of work, or requisition. |
| --- | --- |

|  | 3. Documents approval to proceed with the purchase via a memorandum to project file from the Requisitioner to the Procurement Representation with an approval signature by the responsible WBS Manager. |
| --- | --- |

|  | 4. Following completion of contractual activities, provides Drafting with copies of all drawings and the NSTX Document Administrator with copies of all other documentation deliverables, such as Manufacturing, Inspection, or Test Plans or Operating Manuals. See attachment 1 for guidance. |
| --- | --- |

Attachment 1 - NSTX Procurement Documents and Records

| Statement of Work/Specification | Provides performance & configuration information that may be vital in investigations (failure, upgrade, etc.) during the equipment’s life. | Requisitioner’s copy to be sent to Central Files. |
| --- | --- | --- |

| Requisition | Provides original ordering information for future reference | Requisitioner’s copy to be sent to Central Files. |
| --- | --- | --- |

| P.O./Subcontract | Provides original ordering information for future reference | Copies retained in Procurement for limited time (6 years, 3 mos.). Copies are also available electronically on the PPLACS computer. |
| --- | --- | --- |

| Quality Assurance Program Manual | Documentation of adequacy of the QA system used | Kept in QA file. |
| --- | --- | --- |

| Quality Assurance Plan For This Procurement-include any procedures and procedure qualification records | Documentation of adequacy of the QA/QC controls applied | QA to provide to Central Files. |
| --- | --- | --- |

| Manufacturing/ Inspection/Test (MIT) Plan | Processing and QC details which may be pertinent in investigating a failure and will be helpful in procuring similar equipment | Sent to Central Files by Requisitioner |
| --- | --- | --- |

| Reliability And Maintainability Document | Provides valuable information that may be needed during life of equipment. | Sent to Central Files by Requisitioner |
| --- | --- | --- |

| Workmanship Standards | Essentially part of the QA Plan, but it may be a separate document or may be requested on purchases where no QA Plan is required. | Sent to Central Files by Requisitioner |
| --- | --- | --- |

| Instruction Manuals | Provides valuable information that may be needed during life of equipment. | Sent to Central Files by Requisitioner |
| --- | --- | --- |

| Completed Release For Shipment Form | Will arrive with the item as part of the process history. At this point only serves as record of supplier compliance with PPPL controls. | Sent to Central Files by Requisitioner |
| --- | --- | --- |

| Process History (Documentation Package with Shipment). Commonly included items are: Certificate Of Compliance Material Certifications Planning & Control Documents (Travelers) Inspection Reports Test Reports Discrepancy Reports (Supplier NCR’s) Personnel Qualification Certifications | Arrives with item and provides processing history details which may be pertinent in investigating a failure and will be helpful in procuring similar equipment. | Sent to Central Files by Requisitioner |
| --- | --- | --- |

| Final as-built drawings | Essential documentation of configuration. | Whether vendor-supplied or PPPL updated based on vendor information, to be provided to Drafting by the Requisitioner. |
| --- | --- | --- |

| Correspondence to Supplier that changes requirements. | Can be essential documentation of configuration | Sent to Central Files by Requisitioner |
| --- | --- | --- |

| PPPL-generated Risk Assessment Plan (inspection plan) | Documents PPPL plans for verification of acceptability actions | Sent to Central Files by QA |
| --- | --- | --- |

| PPPL-generated Nonconformance Reports | Documents variances from specification, drawing or other purchase requirements. May be useful in analyzing failures and could be used to add preventive requirements to future procurements. | Sent to Central Files by QA |
| --- | --- | --- |