National Spherical Torus Experiment

NSTX

PROJECT DEFINITION STATEMENT

NSTX-RQMT-PDS-034-00

Revision 0

November 27, 1996

Masayuki Ono		Martin Peng

NSTX Project Director		NSTX Program Director

John A. Schmidt		Rob Goldston

PPPL Advanced Projects Department Head		PPPL Associate Director for Research

Ronald C. Davidson		Jeff Hoy

PPPL Director		DOE NSTX OFES Project manager

Greg Pitonak		N. Anne Davies

DOE NSTX Project Manager		Director, DOE OFES

Princeton Group

This is an uncontrolled copy of a Controlled Document. Check the NSTX File Share server to assure that it is current. The original signed document is on file at NSTX.

RECORD OF REVISIONS

| Revision | Date | ECP | Description of Change |
| --- | --- | --- | --- |

| A | 5/96 | Sinnis | Several adjustments in precision of statements |
| --- | --- | --- | --- |

| B | 7/96 | Peng | Adjustments in definition of plasma pulse length. |
| --- | --- | --- | --- |

| C | 10/96 | Ono | Revised name of NSTX to National Spherical Torus Experiment, incorporation of ECSR comments, and updated TPC. |
| --- | --- | --- | --- |

| 0 | 11/26 | Egebo | Revised TPC to add costs associated with move to D-Site Hot Cell. |
| --- | --- | --- | --- |

TABLE OF CONTENTS

PREFACE	1

1 PERFORMANCE REQUIREMENTS	1

1.1 Device Parameters	1

1.2 Heating and Current Drive	2

1.3 Operational Requirements	2

1.4 Diagnostics	2

2 COST OBJECTIVES	3

3 SCHEDULE OBJECTIVES	3

PREFACE

The mission of the National Spherical Torus Experiment (NSTX) is to investigate, with broad participation by leading U.S. Laboratories, Universities and Industry, the physics principles of:

• Non-inductive start-up, current sustainment and profile control;

• Confinement and transport;

• Pressure limits and pressure gradient driven currents;

• Scrape-off layers and divertors; and

• Stability and disruption-free operation,

in a low aspect ratio (spherical) torus as a plasma confinement innovation.  These principles are to be investigated in the scientifically interesting regimes relevant to the Volume Neutron Source (VNS) and future power plants, characterized by:

• High average βt (plasma pressure/applied toroidal field pressure) ~ 25 - 45 %;

• High pressure gradient driven current fraction ~ 50 - 90 %;

• Fully relaxed, non-inductively sustained current profile;

• Collisionless plasmas with high temperatures and densities; and

• Low aspect ratio R/a ≥ 1.25 with high elongation κ ≥ 2.

This document defines the top-level requirements for the device performance (Section 1), cost (Section 2), and schedule (Section 3) for the NSTX Design and Construction Project. The major participants of the Project will be the Princeton Plasma Physics Laboratory (PPPL), the Oak Ridge National Laboratory (ORNL), the University of Washington, and Columbia University.

More detailed physics performance requirements are summarized in the Project Requirements Document (PRD), engineering performance requirements in the General Requirements Document (GRD), and component performance requirements for the elements of the Work Breakdown Structure (WBS) in the System Requirements Documents (SRD’s).

1 PERFORMANCE REQUIREMENTS

1.1 Device Parameters

The NSTX device shall be designed to provide single null divertor, double null divertor, and inboard limited naturally diverted discharges, in hydrogen and deuterium.  The device shall be capable of operation with the following parameters:

• Plasma Major Radius 	R0 	= 0.85m;

• Plasma Minor Radius	a    	= 0.68m;

• Applied Toroidal Field	BT	= 3.0kG at R0 ;

• Plasma Current 	Ip	= 1.0MA;

• Plasma Elongation	κ 	≥ 2.2;

• Plasma Triangularity	δ	~ 0.4; and

• Plasma Pulse flattop lengths	τpp	~ 0.5 second (inductive-only operation)

~ 5 seconds (driven current operation)

1.2 Startup, Heating and Current Drive

The NSTX facility shall be equipped to deliver to the plasma and handle the following energy inputs for startup, heating and current drive:

• 6 MW of High Harmonic Fast Wave (HHFW) for up to 5 seconds;

• 2 MJ of Coaxial Helicity Injection (CHI) during 5 to 10 milli-seconds;

• 20 kA of CHI injected current for up to 5 seconds; and

• 20 kW of Electron Cyclotron Heating (ECH) for up to 5 milli-seconds.

The NSTX facility design will further account for the adding and handling, as high priority upgrades, the following:

• 400kW of ECH for up to 0.1 seconds; and

• 5 MW of Neutral Beam Injection (NBI) for up to 5 seconds.

1.3 Operation

The NSTX facility, to be located in the D-site hot cell, shall be capable of:

• A 300 second pulse repetition rate;

• Up to 96 pulses per day;

• Up to 5 days per week;

• Up to 3 weeks per month;

• Up to 9 months per year;

• Up to 10 years; and

• Up to 130,000 total pulses.

1.4 Diagnostics

NSTX shall be equipped with diagnostic systems for machine operation, as well as plasma, plasma facing component, and vacuum chamber measurements needed by the NSTX Research Program. The required diagnostics are listed in the PRD. The NSTX facility design will accomodate substantial upgrades to the baseline diagnostic set.

2 COST OBJECTIVES

The NSTX Total Project Cost (TPC) for design, fabrication, and assembly shall not exceed $23.8 million (as spent), predicated on the start of construction in Fiscal Year 1997, and the following funding profile:

| Fiscal Year | Funding |
| --- | --- |

| 1996 | $ 1.0 M |
| --- | --- |

| 1997 | $ 4.7 M |
| --- | --- |

| 1998 | $ 10.5 M |
| --- | --- |

| 1999 | $ 7.6 M |
| --- | --- |

The Construction Cost (TEC) is $21.1 million (as spent), predicated on the start of construction in Fiscal Year 1997.

3 SCHEDULE OBJECTIVES

Given this start of construction and funding Profile, the NSTX Design and Construction Project shall be completed and produce the first plasma by the end of April 1999.

DOE Level 1 Project Milestones are as follows:

DESCRIPTION	BASELINE	ACTUAL

•	Complete DOE Project Validation	April 1995	April 1995

•	Complete DOE Physics Validation 	June 1995	June 1995

•	Complete Environmental Assessment	Dec. 1995	Dec. 1995

•	NSTX Engineering, Cost, and Schedule Review	July 1996	July 1996

•	Start NSTX Construction	October 1996	 October 1996

•	Commence Operations (First Plasma)	April 1999

Additional DOE Level 2 Control Milestones will be developed in the NSTX Project Execution Plan.

A pulse is defined as a plasma discharge reaching the device parameters.

The pulse length is the period of constant applied toroidal field and nearly full plasma current.

The NSTX facility includes the experimental device and all support systems.

600 second pulse repetition for full inductive-only operation.

As determined following the NSTX Engineering, Cost, and  Schedule Review.

The actual amount to be spent, which includes escalation to account for inflation.

The Construction Project starts in FY1997 with allocation of Capital Equipment Funds for the Design and Constrution of NSTX.

The actual amount to be spent, which includes escalation to account for inflation.

The Construction Project starts in FY1997 with allocation of Capital Equipment Funds for the Design and Constrution of NSTX.

First plasma is defined as an ohmically heated discharge.