11-971111-CLN-01

TO: DISTRIBUTION

FROM: C NEUMEYER
SUBJECT:  MINUTES OF VIDEO CONFERENCE ON PFCS

A video conference was convened today with the following attendees.

PPPL

G Barnes	J Chrzanowski	T Egebo	P Heitzenroeder	C Neumeyer       M Ono

ORNL

P Gorenson		B Nelson

Following is a summary of the discussions. Please note ACTION  items indicated.

1.0 Material/Inventory Issues

1.1 Requirements

It was agreed that we need to do a better job of quantifying the material requirements for the various PFC components, now that we will be considering materials other than the FMI 4D.  The following table was offered up as a template for this.

|  | Thermal Cond. |  | Tensile Strength |  | Tmax | Qmax |
| --- | --- | --- | --- | --- | --- | --- |

|  | Normal to Face | Parallel to Face | Normal to Face | Parallel to Face |  |  |
| --- | --- | --- | --- | --- | --- | --- |

|  | W/m-degC |  | PSI |  | deg C | W/cm2 |
| --- | --- | --- | --- | --- | --- | --- |

| IW Rail |  |  |  |  | 1200 | 190 |
| --- | --- | --- | --- | --- | --- | --- |

| IW Slot |  |  |  |  | 1200 | 190 |
| --- | --- | --- | --- | --- | --- | --- |

| IBD Upper Vert |  |  |  |  | 1200 | 510 |
| --- | --- | --- | --- | --- | --- | --- |

| IBD Upper Horiz |  |  |  |  | 1200 | 510 |
| --- | --- | --- | --- | --- | --- | --- |

| IBD Upper Conicals |  |  |  |  | 1200 | 510 |
| --- | --- | --- | --- | --- | --- | --- |

| IBD Lower Vert |  |  |  |  | 1200 | 700 |
| --- | --- | --- | --- | --- | --- | --- |

| IBD Lower Horiz |  |  |  |  | 1200 | 700 |
| --- | --- | --- | --- | --- | --- | --- |

| IBD Lower Conicals |  |  |  |  | 1200 | 700 |
| --- | --- | --- | --- | --- | --- | --- |

| OBD Upper |  |  |  |  | 1200 | 1710 |
| --- | --- | --- | --- | --- | --- | --- |

| OBD Lower |  |  |  |  | 1200 | 1710 |
| --- | --- | --- | --- | --- | --- | --- |

| Passives |  |  |  |  | 1200 |  |
| --- | --- | --- | --- | --- | --- | --- |

| FMI 4D |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |

| POCO |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |

| ATJ |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |

| Other |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |

1.2 Options Previously Identified

Options previously identified for recovery from the shortage of FMI materials were discussed as follows...

a. 	Purchase additional FMI  material

Per G Barnes, quote was received from FMI for materials sufficient to do inner wall rail tiles (168 pieces @ 3"x 7"x1") for $248K and 6-7 month delivery

b. 	Investigate and purchase alternate material

Per G Barnes, quote was received from Allied Signal for materials sufficient to do inner wall rail tiles (168 pieces @ 3"x 7"x 1") for $44K and 6-7 month delivery.  Specs previous TPX RFP. Quotes from additional vendors (Carbone and Kaiser) not yet in hand.

c.	Use all graphite tiles with no carbon-carbon

Per P Gorenson, there are several options available for building the inner wall using graphite tiles. It would be possible to do this in such a way that all of the pieces (except for

the tiles) would be useful later in a retrofit back to the original design. However, it appears that the radial build allowance for the tiles would have to increase from the present ≈ 0.5' to ≈ 1". M Ono noted that this would be highly undesirable in that it would significantly effect the NSTX mission.

Note: Present schedule calls for...

| Component | Installation | Lead Time Months |
| --- | --- | --- |

| IW Tiles (preinstalled on CS) | 8/17 | 9 |
| --- | --- | --- |

| IW Tiles (if installed after CS insertion) | 11/30 | 12.5 |
| --- | --- | --- |

| IBD | 11/30 | 12.5 |
| --- | --- | --- |

| OBD (if preinstalled on domes) | 8/7 | 8.5 |
| --- | --- | --- |

| OBD (if installed after VV assembly) | 11/30 | 12.5 |
| --- | --- | --- |

| Passives (if preinstalled on domes) | 8/7 | 8.5 |
| --- | --- | --- |

| Passives (if installed after VV assembly) | 10/14 | 11 |
| --- | --- | --- |

1.3 Other Options

Other options were discussed as follows...

a. Use stripes on divertors (limit use of Carbon-Carbon Tiles to limited areas)

It was noted that this could prove useful, but would still cost a significant amount of money since a large amount of materials not presently in hand would be required. M Ono was not in favor of this idea.

b. Use all graphite on divertors

This option is the most realistic one, but may not be so limiting as originally thought. It was estimated that, without divertor sweeping, probably the pulse length for the diverted plasmas would have to be reduced from 5 to 2.5 seconds @ 6MW of heating power. Divertor sweeping may permit the full pulse length as originally planned, but this needs to be calculated. An increase in the thickness beyond 1" would not be helpful due to the limited depth of penetration of the heat in 5 seconds.

THE FOLLOWING COURSE OF ACTION WAS DECIDED:

• Pursue the Allied Signal material or alternative for the inner wall rail tiles (ACTION - G Barnes)

- collect information from the other vendors

- evaluate characteristics vs. requirements (mechanical, thermal)

- perform bakeout tests to check outgassing characteristics

- heat flux tests TBD depending on information available from vendors

- initiate material procurement ASAP

• Check how existing FMI inventory might be used on inboard divertors (all, or part of divertor, upper and lower, or lower only) (ACTION - G Barnes  and helper TBD)

• Use existing graphite materials on inboard (pending outcome of above item) and outboard divertors and passive plates

- determine pulse length limitation w/o sweeping (ACTION - B Nelson)

- determine mapping of existing inventory into required tile pieces  (ACTION - G 	Barnes  and helper TBD)

NOTE: If the outcome of the above is found to be satisfactory then we can anticipate a cost increase  over the present budget of ≈ $50K to cover the additional material procurement.

2.0 Geometry/Configuration Issues

2.1 Configuration

The following was agreed to....

| Tile location | thick (in) | material | plasma side | back side | toroidal overlap | poloidal overlap |
| --- | --- | --- | --- | --- | --- | --- |

| centerstack mid-section | 0.551 |  | cylind | cylind | yes | yes |
| --- | --- | --- | --- | --- | --- | --- |

| IB divertor, first conical section | 1 |  | conical | conical | yes | yes |
| --- | --- | --- | --- | --- | --- | --- |

| IB divertor vertical section | 1 |  | cylind | cylind | yes | yes |
| --- | --- | --- | --- | --- | --- | --- |

| IB divertor, second conical section | 1 |  | conical | conical | yes | yes |
| --- | --- | --- | --- | --- | --- | --- |

| IB divertor, horizontal section | 1 |  | flat | flat | yes | yes |
| --- | --- | --- | --- | --- | --- | --- |

| OB divertor | 1 |  | flat | flat | yes | yes |
| --- | --- | --- | --- | --- | --- | --- |

| Secondary passive plate | 1 |  | flat | flat | no | yes |
| --- | --- | --- | --- | --- | --- | --- |

| Primary passive plate | 1 |  | flat | flat | no | yes |
| --- | --- | --- | --- | --- | --- | --- |

One possible exception is the back side of the conical sections of the inboard divertor. For thermal contact reasons, it may be desirable to make these flat. However, this will increase  the machining complexity of the rings which make up these pieces. ACTION - J Chrzanowski to determine if machining of the rings with flats can be obtained without significant cost impact.

2.2 Dimensions

Basic dimensions given in the following figure and table were agreed to.  They have been reviewed by physics (S Kaye, R Maingi). Details which need to be added however are as follows...

• tip at end of slot should have a radius of 1 cm

• gap between passive plates should be 1 in

• radius on tile at midplane end of primary passive plate should be 1"

ACTION - C Neumeyer to issue memo to document, and include notes about radii

|  |  | # | R (in) | Z (in) | # | R (in) | Z (in) |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Inner Wall | Struct | 1 | 6.738 | 0.000 | 2 | 6.738 | 42.617 |
| --- | --- | --- | --- | --- | --- | --- | --- |

|  | PFC | 3 | 7.289 | 0.000 | 4 | 7.289 | 41.780 |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Inner Wall/Inboard Divertor Angled Section | Struct | 5 | 6.738 | 42.617 | 6 | 10.000 | 44.500 |
| --- | --- | --- | --- | --- | --- | --- | --- |

|  | PFC | 7 | 7.289 | 41.780 | 8 | 11.000 | 43.923 |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Inboard Divertor Vertical Section | Struct | 9 | 10.000 | 44.500 | 10 | 10.000 | 62.125 |
| --- | --- | --- | --- | --- | --- | --- | --- |

|  | PFC | 11 | 11.000 | 43.923 | 12 | 11.000 | 61.857 |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Inboard Divertor Vertical/Horizontal Angled Section | Struct | 13 | 10.000 | 62.125 | 14 | 11.732 | 65.125 |
| --- | --- | --- | --- | --- | --- | --- | --- |

|  | PFC | 15 | 11.000 | 61.857 | 16 | 12.309 | 64.125 |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Inboard Divertor Horizontal Section | Struct | 17 | 11.732 | 65.125 | 18 | 22.500 | 65.125 |
| --- | --- | --- | --- | --- | --- | --- | --- |

|  | PFC | 19 | 12.309 | 64.125 | 20 | 22.500 | 64.125 |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Outboard Divertor | Struct | 21 | 23.618 | 65.438 | 22 | 46.004 | 57.918 |
| --- | --- | --- | --- | --- | --- | --- | --- |

|  | PFC | 23 | 23.300 | 64.490 | 24 | 45.686 | 56.970 |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Slot | Struct | 25 | 42.498 | 55.823 | 26 | 45.017 | 54.977 |
| --- | --- | --- | --- | --- | --- | --- | --- |

|  | PFC | 27 | 40.227 | 57.641 | 28 | 45.335 | 55.925 |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Secondary Passive Plate | Struct | 29 | 42.498 | 55.823 | 30 | 49.557 | 44.175 |
| --- | --- | --- | --- | --- | --- | --- | --- |

|  | PFC | 31 | 40.227 | 57.641 | 32 | 48.702 | 43.657 |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Primary Passive Plate | Struct | 33 | 49.651 | 43.973 | 34 | 57.248 | 21.182 |
| --- | --- | --- | --- | --- | --- | --- | --- |

|  | PFC | 35 | 48.702 | 43.657 | 36 | 56.299 | 20.866 |
| --- | --- | --- | --- | --- | --- | --- | --- |

3.0 Other

3.1 Facets on IBD Conicals?

Per 2.1 above it was agreed that J Chrzanowski will evaluate the cost impact of this and make a recommendation.

3.2 Difference between Upper & Lower IBD tiles

Due to the difference in the  pattern and size of the feedthroughs on the upper and lower flanges of the CS casing the upper and lower inboard divertor tile designs will have to be slightly different.  Also, the area available for heat transfer is significantly reduced by the feedthroughs. Although this is probably unavoidable, ACTION- G Barnes to review the feedthroughs and try to simplify/reduce.

3.3 Cooling line sizes?

Still need to reach closure with R Parsells (bakeout system) on tube size and heating/cooling performance. ACTION - G Barnes to coordinate this.

3.4 SOW Status

Since plan to recover from inventory problem now established, ACTION - B Nelson to mark up SOW and cost estimate for final review and approval.

3.5 Do we need a face-face visit?

Will convene conference call Tuesday 11/18 1:30 pm. ACTION - G Barnes to coordinate

cc:

G Barnes	J Chrzanowski	T Egebo	P Gorenson		P Heitzenroeder

B Nelson	M Ono		J Schmidt	NSTX File