13-97-11-18-JHC-01

TO: Charlie Neumeyer..Engineering Project Manager	November 18, 1997

FROM:  Jim Chrzanowski... WBS 1 Manager

SUBJECT: Everson Electric Vendor Visit #6

_____________________________________________________________

On  Monday November 17, 1997 representatives from PPPL visited Everson Electric Company to review the status of both the TF and OH coil projects.  The meeting attendees included:

•	Jim Chrzanowski .....	PPPL Technical representative

•	Phil Heitzenroeder ....	PPPL representative

•	John Schmidt .........	PPPL representative

•	Greg Pitonak .........	PPPL DOE representative

•	Frank Malinowski ...	PPPL QA representative

•	Larry Sutton ..........	PPPL Contracts representative

•	Greg Naumovich .....	Everson- Director of Engineering

•	Doug Hartman ........	Everson-Engineering Supervisor

•	Tuan Hoang ...........	Everson- Project Engineer

•	Al Wallis ..............	Everson- Tooling Design Supervisor

•	Tom Zebro ...........	Everson QA Manager

Agenda

Greg Naumovich provided a tour of the facility for members of the PPPL group who had never visited the Everson Electric plant.  In conjunction with the tour, Frank Malinowski met with Everson QA and technical personnel to work out several QA inspection details for the OH coil tension tube.

Following the tour of the facility the group inspected the in-progress fabrication of the TF CenterStack bundle.  A status meeting was then held which concluded the business at Everson.

Summary of Everson Visit:

TF Coil

•	All of the TF bundle tooling with the exception of the final bundle molds are in house and ready for use.  The final bundle molds should be completed this week.

•	The copper coolant tubes for the first quadrant TF conductors have been soldered in place and insulated and turn insulation applied.

•	The first quadrant TF conductors were being installed in the quadrant mold.

•	The first quadrant will cured this week starting on Thursday, and removed from the mold early next week.

OH Coil

•	The rough machining of the tension tube is in progress with this operation completed by 11/21/97.

•	The completed tension tube will be delivered to Everson by 12/12/97.

•	The winding of the OH coil will begin on January 6, 1998.

•	The OH coil will be completed between the 1st. And 2nd. week of February.  The original delivery date was 1/23/98.

•	The outer molds for the OH coil have been completed.

QA issues:

It was agreed that Everson would witness the final dimensional inspections of the Tension Tube at the manufacturer.  This is being done since Everson does not have the ability at their facility to verify those dimensions and tolerances.  Everson will provide Frank Malinowski a written statement on the agreed upon inspection.

Summation:

Everson appears to be making good progress on the first TF quadrant.  By early next week the first quadrant should be cured.  Everson will continue on the soldering operation for the next quadrant sub-assembly.

Even though Everson’s expected delivery of the OH coil is later then identified on the contract, this delay should not effect the delivery of the Center Stack to the Hot Cell.  The coil is presently scheduled to be mated with the TF bundle the week of 2/23/98.

Cc	P. Heitzenroeder

F. Malinowski

T. Meighan

C. Neumeyer

M. Ono

L. Sutton

R. Templon

Operations Center