13-98-1-16-JHC-01

TO: Charlie Neumeyer..Engineering Project Manager	January 16, 1998

FROM:  Jim Chrzanowski... WBS 1 Manager

SUBJECT: Everson Electric Vendor Visit #14

_____________________________________________________________

On  Wednesday  and Thursday January 14 & 15, 1998 Jim Chrzanowski visited Everson Electric Company to witness the assembly of the four TF bundle quadrants in preparation for curing.  The report of that visit is as follows.

Summary of Everson Visit:

•	The PPPL Technical representative witnessed the assembly of the (4) TF quadrants prior to its installation into the mold.  The steps included:

•	Installation of additional sheets of B-stage insulation (per drawing) along with the center silicone rubber core plug between the quadrants.

•	Once joined, the (4) quadrants were clamped together to provide a tight bundle and to align them to each other prior to proceeding to the next operation.

•	A coating of CTD-112 resin was then applied over the outside face of the (2) quadrants which were not repaired (Quadrants # 1 and 2).

•	One half-lapped layer of CTD-112 B-stage insulation was then applied over the entire TF bundle, followed by one half lapped layer of tedlar tape.

•	A pre-formed steel sleeve was then positioned over the bundle to take up the extra groundwall space in the mold during this curing operation of the CTD-112 insulation.

•	Everson Electric’s QA group was taking a more active role in following the progress of the assembly procedure.

•	The plan was to complete the assembly and installation of the TF bundle into the press mold.  The cure cycle was scheduled to begin on Friday morning depending upon the weather conditions.

•	The PPPL Tech. representative approved the revised TF Traveler to reflect the additional QC coverage as requested by PPPL for the balance of the TF fabrication operations.

•	The OH coil Tension Tube and mandrel were sent out for the final machining operation.  It is anticipated that the Tension Tube would be back to Everson by Monday January 26, 1998 to begin the winding operation.

Cc	P. Heitzenroeder	C. Neumeyer		L. Sutton	     Operations Center

F. Malinowski		G. Pitonak		R. Templon

T. Meighan		M. Ono		M. Williams