4X-990430-RK-01

TO:  NSTX VACUUM INTERFACE MEETING ATTENDEES*

FROM: R. KAITA

*W. BLANCHARD	*L. DUDEK		*D. JOHNSON	*R. KAITA

*H. KUGEL			*C. NEUMEYER	*E. PERRY	*L. ROQUEMORE

This memorandum serves as a record of the NSTX vacuum interface meeting on April 28, 1999. The participants were able to peer review the port covers and windows prior to preparing a DCA to install them. The issues are items ordinarily covered in chits, and the action items address their resolution.

Issues:

1)	Windows:

-	Safety margin policy will not be decided anytime soon.

-	Make decision on quartz or glass solely on purpose of window.

2)	Port Cover Installation Priorities:

-	27” ports require personnel inside vacuum vessel.

-	In-vessel platform will be removed on May 14.

-	Installation of port covers on Bays B, F, H, I, and J cannot be delayed much past then if damage to in-vessel structures below midplane is to be prevented.

-	Bays B, H, and I should not be an issue (commercial port covers from Huntington).

-	Welding schedule is an issue. Bay F port cover is straightforward but Bay J port cover is more complicated and may be a critical path item.

3)	Stress Analysis:

-	New port covers should be all right if Bay J port cover is assessed to be satisfactory.

4)	Safety:

-	Pulse height analysis diagnostic (PHA) may block access to the platform stairs. An aisle which is three feet wide is required.

Action items.

1)	Windows:

-	Order glass and quartz windows needed for pumpdown. (Roquemore)

2)	Port Cover Installation Priorities:

-	Notify Huntington to provide 27” flanges first. (Kaita – DONE).

-	Notify Ramé-Hart to provide Bay J partial shipment. (Kaita – DONE).

3)	Stress Analysis:

-	Perform for Bay J flange. (Dudek)

4) Safety:

-	Ask Borusovic to evaluate for I&C rack and X-ray crystal spectrometer. (Roquemore – DONE).

-	Resolve PHA access concern with Perry (Roquemore).