4X-980520-RK-01

TO: DISTRIBUTION

FROM: R. KAITA

SUBJECT:  REVISED PLAN FOR NSTX MAGNETICS

This memo explains the changes in the plans for the magnetic diagnostics. The original approach had two parts.

1) Build new sensors: This has not changed, and the status is as follows.

a) Center Stack:

i) Plasma current Rogowski coils - FDR held on 3/23/98 and

fabrication is complete.

ii) Flux loops - FDR held on 3/23/98 and installation plan being

prepared.

Summary - Activity 41205 is thus complete.

b) Non-Center Stack:

i) Mirnov coils - Peer Review held on 5/13/98 and design being

finalized.

ii) Halo current Rogowski coils - locations specified in PDR on

9/9/97 and finalized in meeting on 5/11/98.

iii) Flux loops - locations specified in PDR on 9/9/97 and

finalized in meeting on 5/11/98.

Summary - Activities 41251 and 41253 are thus complete.

Note - The original estimate for the magnetics was based on a “cost

per channel” that was NOT meant to be just the price

for the integrators (see below). Fabrication of non-CS

Magnetics (41257) should NOT be a “zero cost” activity,

but should have the following breakdown.

1) 72 passive plate Rogowski coils @$100/coil = $7,200

2) 4 halo current Rogowski coils @$750/coil = $3,000

3) 75 pickup coils @$300/coil = $22,500

TOTAL (to deduct from 41211): $32,700

2) Build new integrators: The original plan was design and build new integrators. This was changed after discussions between R. Hatcher and

R. Marsala early in CY98. They concluded that the best idea was to add remote

readout capability to the PBX-M integrators and use them instead of designing

and building new ones. This resulted in the following changes in activities.

a) Final Design Electronics (41207): Either eliminate or take credit for

its completion.

b) FDR Electronics (41209): Either eliminate or take credit for its

completion (cite this memo as record of informal review).

c) Procure CS magnetic integrator components (41211): Defer to FY99

and reassess in light of remaining budget (see comments at

end of “Build new sensors” section above) and urgency for

replacing PBX-M integrators.

d) Fabricate Mag Integrators (41213): It is not clear why this activity was

separated from the assembly of the integrators (41215). One

possibility is to relabel this as “Modify Mag Integrators” and

declare this as finished when the modifications are complete

(end of June/beginning of July).

e) Assembly CS Magnetic Integrator Assemblies (41215): Defer to FY99

and reassess in light of remaining budget (see comments at

end of “Build new sensors” section above) and urgency for

replacing PBX-M integrators.

The recent jump in WBS 4 spending reflects mainly the fact that the spending on the engineering (Marsala/Hatcher) and implementation (Reese) of the modifications to the PBX-M integrators took place during the last few months. The details provided for Activities 41211, 41213, and 41215 above show why this is not a trend that is expected to continue. In fact, declaring 41213 complete puts us ahead of schedule.

In summary, the primary change in the non-CS Magnetics is to add the fabrication costs (41257) described above. For the CS Magnetics, a plan that would more closely follow what we are now intending to do has 41207 and 41209 as complete (or eliminated), and 41211, 41213, and 41215 as actually a separate activity class called “Replacement of PBX-M Integrators” or “Electronics for Additional NSTX Magnetics Channels.” The activity to “Install Magnetic Integrator Assemblies” (41217) would remain as the last item in both the CS and non-CS magnetics lists.

Distribution:

T Egebo		R Hatcher		D Johnson		H Kugel

R Marsala		B McCormack	C Neumeyer	M Ono

L Roquemore	R Strykowsky	C Such		NSTX File