4X-980527-RK-01

TO: DISTRIBUTION

FROM: R. KAITA

SUBJECT:  BASELINE DIAGNOSTICS TESTING SCHEDULE

Here is my present thinking on what I think the NSTX baseline diagnostics testing schedule should be.

Subsystem			Comments			Days	Seq.	Prereq.

I&C Interface		Check interface with	5	27	52

Commissioning		Central I&C for diag.

in entries to follow

Magnetic Diagnostics	Check with test signals	10	28	27

Commissioning		at vacuum interface from

Rogowski coils, flux

oops, and pickup coils

and check integrator time

constants with anticipated

voltage levels

PFC Diagnostics		Check with test signals	10	29	27

Commissioning		at vacuum interface from

thermocouples and

Langmuir probes and

insure all thermocouples

show same temperature

Copper Plasma Test	Frequency test only of	5	65	28

pickup coils (five days

includes setup as well

as actual testing)

Combined Field		Add two days to original	4	74	28

two for final calibration

of magnetic diagnostics

Notes:

1) Preliminary calibration of magnetic diagnostics will occur during

“energizing of field coils” (Seq. No.’s 70-73).

2) Further “end-to-end” testing of thermocouples can be performed during bakeout tests (Seq. 68).

3) Propose transferring extra ten days in Neumeyer‘s orginal schedule for magnetics and “divertor diagnostics” (now PFC diagnostics) commissioning to these “end-to-end” testing activities.

4) How to perform “end-to-end” commissioning of Langmuir probes without a plasma (at least a glow discharge) remains to be determined.

5) Only other “Day 1” diagnostics are interferometer and TV cameras,

which are not linked to other elements in the testing schedule.

Distribution:

J. Chrzanowski	R. Hatcher		D. Johnson		H. Kugel

B. McCormack	C. Neumeyer	M. Ono		L. Roquemore

C. Such		NSTX File