4X-990112-RK-01

TO: DISTRIBUTION

FROM: R. KAITA

SUBJECT:  DIAGNOSTIC INSTALLATION IN TILES

The X850-TPC First Outage Tasks spreadsheet lists four activities exterior to the vacuum vessel (EX VSL) prior to first plasma. They are as follows.

114 inbwd divertor: install tiles on plates (EX VSL)

117 outbwd divertor: install tiles on plates (EX VSL)

121 secondary pp: install tiles onto plates (EX VSL)

124 primary pp: install tiles onto plates (EX VSL)

These tasks cannot be performed as scheduled for the following reasons.

1) The inboard divertor is an integral part of the center stack and cannot be accessed before the vacuum vessel is vented after first plasma. There are no separate plates on which the tiles can be installed prior to this time, and tasks 115 and 116 (upper and lower  inboard divertor plate installation) do not exist.

2) The fixtures for securing the outboard divertor sections make it impossible for the tiles to be attached prior to their installation. No tiles can be installed before the vacuum vessel is vented after first plasma and the outboard divertor sections are mounted.

3) The primary and secondary passive plates will first be installed and checked for deviations from their expected locations with Loesser’s precision measurement equipment. The plates with then be removed and the supports modified. They will be re-installed and their final locations adjusted with shims. Since this procedure will be impossible with the tiles on the plates, none can be installed before the vacuum vessel is vented after first plasma and plates are mounted.

We are preparing a more detailed installation procedure for the divertor sections and passive stabilizers and their tiles. Since the in-vessel work in general is significant, we also need further planning discussion with a number of WBS units for a credible outage schedule. Meanwhile, we wish to make it clear that no tile installation will be possible prior to first plasma.

Distribution:

G. Barnes		D. Johnson		H. Kugel		B. McCormack

C. Neumeyer	M. Ono		E. Perry		L. Roquemore

R. Strykowsky	C. Such		M. Williams	NSTX File