71960429-TEE-01

TO: Distribution

FROM: T. Egebo
SUBJECT:  Minutes from NSTX Monthly DOE Meeting

The following is a summary of the 4/25/96 NSTX meeting with DOE, at which project issues were discussed, with emphasis on the July Review (Attachment I provides a summary of items discussed).

Location :  LOB - Room B-280

Present :

ORNL: Martin Peng

PPPL:  Masa Ono, Stan Kaye, Charlie Neumeyer, Bob Simmons, Tom Egebo

DOE: Greg Pitonak,  Jeff Hoy (on speaker phone from Germantown)

1) NSTX Review

Greg Pitonak distributed a memo from John Willis appointing Dr. D.B. Montgomery as chair for the review. DOE has requested that the majority of reviewers be from outside of PPPL in order to assure an independent review. Cost for reviewers will not be picked up by NSTX project. Jeff Hoy noted that the FY97 budget proposed for NSTX is $ 5 million and preliminary indications for FY98 budget is $ 9 million (this includes operating and capital equipment). The NSTX project team noted that this would impact the proposed completion date for NSTX.

Action : J. Sinnis to review makeup of review committee and make final recommendation to Jeff Hoy.

Action : DOE (J. Willis) will send out invitation letters to review committee with charge and membership list.

Action: M. Peng to update PDS with revised funding guidance.

Action: S. Kaye to develop strawman operating budget for NSTX.

2) Management Documents

Tom Egebo discussed the status of the Management Documents. PMP and PDS are going through PPPL signature process. PRD draft and GRD are going through internal NSTX management review process. SRD preparation by WBS managers has begun with drafts expected by May 3rd. SDD’s to follow.

Action: T. Egebo to send informal copies of PMP, PDS and GRD to Greg Pitonak and Jeff Hoy.

3) Cost and Schedule preparation

With the exception of the NSTX Machine Assembly plan minimal work has been done on updated cost and schedule estimates. Plans are to increase efforts in cost and schedule development following first issues of SDD’s.

4) Level of Design Development expected by July

The attached handout includes a list of specific deliverables planned for the July review. In general the level of detail will vary with major emphasis being placed on the Tokamak.

Action: Jeff Hoy and Greg Pitonak notify project if level of planned design development is insufficient.

5) Open Discussion

Jeff Hoy mentioned that there was a possible conflict with a planned FEAC meeting the week of the NSTX review.

Action : J. Hoy to advise project of FEAC schedule.

Dr. Anne Davies will be visiting PPPL May 8th and 9th.

Action : M. Peng/M. Ono should be prepared to give Dr. Davies a 1 hour presentation on NSTX if her schedule allows.

Site credits is an important issue in presenting the NSTX cost and schedule baseline.

Action: T. Egebo to assure that site credits are clearly accounted for in each WBS managers estimate and a summary table will be developed to support the NSTX review.

Vendor proposals to lift the PLT machine through the roof were rejected because the cost was higher than forecasted and the requirement to leave the roof open for a two week period was unacceptable. PPPL will pursue two options 1) prepare an RFQ for turn-key proposal for tear down, removal and sale by vendor: 2) develop cost estimate for PPPL to manage tear down, removal and sale of PLT device.

Please advise if there are any questions or comments.

Distribution:

Jeff Hoy (DOE-OFES)

Greg Pitonak (DOE-PG)

R. Goldston

J.A. Schmidt

J. Sinnis

Martin Peng

Robert Simmons

NSTX WBS Managers

NSTX File

Attachment I

NSTX Project Meeting

April 25, 1996

Topics for Discussion

Draft Agenda for NSTX Review

Proposed Team Membership

Management Documentation Status

Bottoms-up Cost Estimating

Critical Path Development

Level of NSTX Design Development Expected by July

Open Discussion

Draft Agenda for NSTX Review July 16-18

Proposed Team Membership

•	NSTX transmitted a Suggested Team Membership along with Suggested Approach, Charter, Agenda and Break Out Teams to DOE

•	DOE is reviewing Team Members -

Bruce Montgomery has agreed to serve as chairman

DOE is looking for more external reviewers

ACTION is currently with DOE, (NSTX will provide support as required)

Issue 1 - Will reviewers cost be handled as TPX ? DOE will provide funds to reviewers for travel ..

Issue 2 - FY funding guidance is necessary (FY97=$5million,FY98 = ??)

Management Document Preparation

Project Management Plan (PMP) has gone through several review cycles (including DOE). All issues have been resolved. Signature Process has begun.

Project Definition Statement (PDS) has been prepared and reviewed . Signature Process has begun.

Project Requirement Document (PRD) a draft copy is being reviewed by NSTX management.

General Requirements Document (GRD) has been prepared and gone through internal review cycle (no show stoppers). GRD has been distributed to WBS managers to use as basis for SRD’s.

System Requirements Documents (SRD)/System Design Descriptions(SDD’s). A procedure has been developed and a kickoff meeting was held with WBS managers on development of SRD/SDD’s using standard format. WBS Managers are developing SRD and than SDD’s which will form the basis for their cost estimates. Draft SRD/SDD’s will  be out for review by mid-May.

Bottoms-up Cost Estimating

Cost Estimates by WBS are pending completion of SRD’s/SDD’s

•	NSTX Assembly has gotten off to good start

•	Plan to have other systems working on estimates by mid-May

Cost and Schedule Estimating Guidelines being developed

Risk Assessment Plan has been developed

Critical Path Schedule Development

A detailed Assembly plan has been developed and distributed to WBS Managers. This is a key step in establishing required delivery dates for components.

Other WBS schedules will be developed as SRD’s/SDD’s progress

Level of NSTX Design Development Expected By July

General

A General Requirements Document (GRD), along with System Requirements Documents (SRDs) will describe the requirements. Although these documents will continue to evolve, it is planned that they will be sufficiently mature to become subject to configuration control following the resolution of chits from the review.

System Design Descriptions (SDDs) will describe the design of the systems. The level of detail will vary, with the major emphasis being placed on Tokamak Systems,  WBS 1.

Cost and Schedule estimates will be developed for the project in coordination with the designs described by the SDDs, again with the major emphasis on WBS 1.

Specific Deliverables Planned for Review

WBS 1 - Tokamak Systems

1) SRD/SDDs for WBS 11, 12, 13

2) Cost Estimate

3) 2-d Space Allocation Drawing

4) CAD drawings of Coils, VV's, PFC's as necessary to describe design concept and provide basis for cost estimates

5) Analysis

- thermal/electric/hydraulic, TF & PF coils

- thermal analysis of bakeout

- stress analysis (limited)

- thermal analysis of PFCs

WBS 2 - Heating Systems

1) SRD/SDDs for WBS 2

2) Cost Estimate

3) Drawings depicting layout of ex-vessel components as necessary to describe design concept and perform cost estimates

4) Layout of ports

5) Conceptual design and drawings of antennae

Note: for the engineering review all drawings will be Macintosh type

Level of NSTX Design Development Expected By July (continued)

WBS 3 - Auxiliary Systems

1) SRD/SDD for WBS 3

2) Cost Estimate

3) P&ID and Flow diagrams

4) Supporting Calculations

Note: for the engineering review all drawings will be Macintosh type

WBS 4 - Diagnostics

1) SRD/SDD for WBS 4

2) Cost Estimate

3) Layout (plan view of machine)

WBS 5 - Power Systems

1) SRD/SDD for WBS 5

2) Cost Estimate

3) Schematic Diagrams

4) Computation of current, voltage, power, and energy requirements based on coil geometry and plasma scenarios.

WBS 6 - Central I&C

1)  SRD/SDD for WBS 6.

2)  Cost Estimate

3)  Central I&C Interface Block Diagram.

4) A general schematic of the proposed Central I&C System.  Will include classes of hardware and software -- not specific vendors, brands or model numbers.

5) General Arrangement of Control Room.

WBS 7 - Project Management

1) Project Cost and Schedule

WBS 8 - Facilities and Assembly

1)  Installation sequence, schedule, and cost estimate.