71-960816-TEE-01

TO: M. Ono

FROM: T. Egebo
SUBJECT: Minutes of Meeting with NSTX Reviewers to discuss Management, Cost & Schedule Issues

Location : PPPL room B280 - G. Pitonak’s office ~ 3:30 pm 7/31/96

Attendees: Greg Pitonak (DOE-PG) Jim Carney(DOE), Tom Egebo(NSTX), Paul Bellamo(SLAC), Charles Neumeyer(NSTX), Dave Gwinn(MIT), John Spitzer(NSTX), Paul Anderson(GAT) and Jim Sinnis(PPPL).

Jim Carney and Greg Pitonak reviewed the NSTX PDS, PMP and cost methodology and provided the following comments:

Cost Estimate:

The methodology used to develop the cost estimates (a combination of vendor quotes, previous purchases, established labor rates,...) is appropriate. If the technical review team is satisfied with the design and do not have issues that result in changes that would result in cost increases, then the estimates are sound.

In response to a question about contingency and risk assessment, Tom Egebo provided the attached "NSTX Risk Assessment-Contingency Analysis Guidelines.

Pitonak challenged the 5% contingency allocated to some of the WBS elements, pointing out that at this stage of the project, that was an unrealistically low value.

Pitonak noted that the 25% G&A rate assumed for the Project may be low in light of informal discussions that suggest that it might be in the neighborhood of 30%. Egebo noted that the Project cannot control this rate and uses the rate established by  the PPPL budget office. Tom noted that a 5% increase in the G&A rate for purchases would result in a cost increase of between $200K and $250K for the Project.

Carney asked for justification of the low schedule risk factor used in the analysis. Egebo noted that except for the center stack, there is slack in the schedule for the other sub-systems. Tom pointed out that the schedule was driven by the availability of funds and that an additional $3m in the FY'97-FY'98 period could pull the first plasma date back to January 1999.

Pitonak noted that a rigorous cost validation could not be performed, and suggested that cost comparisons with TFTR and TPX at the subsystem level would be very helpful. Neumeyer noted that getting these three cost estimates back to a common basis would be very difficult because of site credits, TFM, ...

Pitonak asked about the question that Saltmarsh raised, namely that the first iteration of costs resulted in a ~$25M estimate. What was done to reduce costs to $20.8M?

Tom Egebo noted that the baseline cost estimate includes everything required to meet Project requirements.

Some of the actions that resulted in cost reductions were for capability that exceeded requirements: e.g. Delete the high power ECH system and delete High Speed Process Control Data Communication System (~$1.3M).

Some were for changes in assumptions: e.g. Use TFTR I&C equipment instead of buying new (more that $1M reduction).

Also, Instead of buying transformers, use TFTR transformers (0.4M$) and excluding PLT Removal from NSTX TPC ($0.2M)

PMP and PDS Discussion:

In general Jim Carney was “impressed” with the management plan and supporting documents.

In keeping with the plan to reduce the number of DOE Orders, DOE has issued 430.1 Life-Cycle Asset Management (LCAM) this DOE Order replaces DOE 4700 (as well as additional DOE ORDERS).

The DOE Joint Program Office has provided Direction on Project Management in the form of “Joint Progrm Policy Requirements on Project Management “(which has been endorsed by M. Krebs, Director of ER).

Jim Carney made the following suggestions on modifying the PDS and PMP. These modifications if implemented would essentially assure that the NSTX PMP and PDS satisfy 430.1

Greg Pitonak noted that the present contract with the Laboratory calls for use of 4700. The contract is being re-negotiated and will reflect the changes in applicable DOE Orders.

1) Jim Carney recommends we change the title of the PMP to the "Project Execution Plan", per "Joint Office Program Plan".

2) Page 2 Figure 3-1, Jim recommends we add "PPPL" to the title of this chart since it only refers to PPPL (and not DOE) organization.

3) Page 9 Table 4-1, Jim recommends that we add "responsibility" to the title (NSTX Project Work Breakdown Structure "Responsibility" Matrix).

4) Page 12 Figure 5-1, to the extent that this figure includes milestones (i.e., stars) Jim recommends that  should correspond exactly to the Level 1 and Level 2 milestones shown on page 14.

5) Page 13 Table 5-1, Define TPC and TEC in this chart.

6) Page 14 Table-2, for Level - 0 milestones, simply state "none".

7) Page 14 Table-2, the dates for Level-1 milestones should correspond exactly to the dates in the PDS milestones (on page 3 of PDS).

8) Page 14 Table-2, the start construction date does not match the start construction date in the PDS (page 3).

9) Define First Plasma.

10) Page 17, under 7.2 PMP Jim recommends that we change commissioning to Integrated Systems Test.

11) Add Jeff Hoy to PDS signature block to correspond to page 18 Table 7-1.

12) Page 18 Table 7-1 remove DOE OFES NSTX manager and DOE NSTX Project Manager from PRD approval.

13) Page 26 10.2 PCS Overview. Add a statement that PPPL PCS satisfies the priciples of the "Joint Program Office Plan" as well as DOE 430.1.

Project Definition Statement (PDS)

1) Page 3 - 2. Cost Objectives , Jim recommends that we change the first sentence to " The NSTX Total Project Cost ..."

2) Page 3 - 3. Schedule Objectives, Jim recommends we add Level - 1 to the project milestone list and also add Level 2 to the last sentence that references DOE control milestones.

An action will be placed in Tom Egebo’s name on the NSTX Action Item List to incorporate the above comments.

cc:

J. Schmidt

J. Sinnis

M. Peng

C. Neumeyer

B. Simmons

J. Hoy (DOE OFES)

G. Pitonak (DOE PG)

J. Carney (DOE)