Charge to the reviewers for the "October Check Point"

of the NSTX Center Stack and Ceramic Break Design

Objective:

The objectives of the Checkpoint Review are:

• To demonstrate that the technical issues identified at the Engineering Review are being addressed in a focused manner with adequate resources, such that the completion of the work by the February review can be assured;

• To describe progress in the clarification of physics requirements (disruption, halo currents, heat loads, etc.);

• To present new design solutions to the extent that they have been developed, as a minimum for:

- new OH and PF1 coil designs;

- new schemes for the annular regions between the TF coil, OH 	  coil, and center stack casing;

- new schemes for the reaction of launching loads;

• To describe the status of engineering analysis of the overall design which accounts for electromagnetic and thermal loads under all operating (normal, disruption, bakeout) conditions.

Reviewers:

Dave Gwinn (MIT), Chairman

Paul Anderson (GA)

Jim Chrzanowski (PPPL)

George (Hutch) Neilson (PPPL)

Scope:

The scope of this review will be limited to technical issues associated with the center stack and ceramic break.

Basis:

The technical issues associated with the center stack & ceramic break in the NSTX Engineering Review Committee's report should be used as input to the review. In addition, comments and "Chits" from other participants should be considered.

(A listing of the relevant sections of the review report are included as an attachment to this charge letter.)

Date:

The proposed dates for the review are October 31 and November 1.

Format:

The scope is limited to this one critical area in order to provide the time required to perform an intensive review of the center stack & ceramic break designs.

A clear presentation of loads and load paths should introduce each discussion of design details.

Major portions of the review should be dedicated to "table-top" discussions of the designs where the NSTX engineers and the reviewers pour over drawings of the hardware, review supporting analyses and comment on details of the design and how the design meets the requirements. 
The issues identified at the engineering review should be one organizing input to the check point review. However, the reviewers should be encouraged to think beyond the previously identified issues to assure adequate design progress.

The criteria for "success" at this check point is to prove to the reviewers that the center stack & ceramic break technical issues are being addressed, design solutions are being developed, and the R&D required to support the design solutions have been identified.

Attachment

Listed below are excerpts from the review report that pertain to the center stack and ceramic break.

From 1.1	Overall Engineering Status

There are some significant engineering challenges associated with the design of the center stack and the region of the ceramic breaks used to electrically isolate the center stack from the outer vacuum vessel.  The design concepts presented did not appear to deal adequately with the combination of thermal and electromagnetically induced stress to be expected during either normal operation or the bake-out cycle.  Increased emphasis on engineering support related to these design issues, particularly thermal analysis, should be a high priority of the project.

This increased analysis should focus on a number of specific design details in the center core region and elsewhere, for example:

(1) the proposed abrupt change in conductor cross-section in the OH coil

(2) the proposed out-of-plane support structure for the TF coil outer legs

(3) the upper and lower umbrella region supports

(4) the support and assembly methods for connectors to the inner TF legs

(5) accommodation for radial expansion near the ceramic break

(6) Temporal thermal distribution of the vacuum vessel for both plasma operations and baking

From 1.3	Committee  Summary Response  to The Charge Questions

(b) assembly precision/tolerances for center stack components, coils, etc.

(c) tolerances for Plasma Facing Components (PFCs), particularly the tiles on the center stack.

(5)  Recommendations

(a) Technical Recommendations:

(i) Increased emphasis on up-front engineering design and analysis, particularly thermal analysis of the center stack and ceramic break region during normal operation and bake-out.

(ii) Evaluation of the OH solenoid design, particularly the abrupt change in conductor cross-section.

(iii) Evaluation of the need for a ceramic break.  Could isolated divertor plates be a solution?

(iv) Evaluate the out-of-plane support for the TF outer legs.

(v) Define Research and Development Activities (RDAC's) required, particularly regarding critical fabrication/assembly details of the center stack.

From 2.0 	Detailed Engineering Issues

2.1 Center Core

2.1.1 Structural Issues

(1) The task of the identification and determination of the magnitude of the loads applied to the central core components, both during normal operation and fault conditions, has not been completed.  As a result, it is not possible to evaluate the adequacy of the design with respect to the resultant stresses and deflections.

(2) The out-of-plane stresses due to normal operations and disruptions appear to require considerably more evaluation.

(3) Stress analysis needs to consider properly the superposition of EM and thermal stresses: in boilers the T's may not be "primary" stresses, but they must be considered in restrained magnets.

(4) The definition of the load path for loads in the vertical direction was not complete. The presentations indicated the intention to transfer loads through an incompletely specified material in the annular regions between core

components.  Neither the need for nor the adequacy of such an approach was presented. It was therefore not possible to  evaluate fully the adequacy of the design in this area.

(5) There is a need to assure the radial alignment of the solenoid, controlled against n = 1 halo-induced forces and accommodating differential expansion with respect to the TF core.

(6) The "Shear flex" slip-plane at the top of the machine seems redundant, due to the large variation of the gap it sits in, due to varying temperature differentials.

(7) The umbrellas were shown to be rather flexible torque reaction assemblies.  The toroidal tie-bars in the outer limbs will go slack under some conditions (hot vessel, cool TF) and may be too slim to provide adequate stiffness.  We were told verbally of shear plates to be added between the TF limbs, just outside (perhaps attached to) the umbrellas, but no drawing was provided.

(8) The shoulder-bolted set of fish-plates intended to act as a torque transfer structure are kinetically unsound: the fish-plates are unstable to migrating up the shoulder-bolts (or remaining where pushed up the shoulders, by the vertical expansions they are intended to accommodate) and so at the very least the stiffness  should be analyzed with the fish-plate at the top of the bolts. However, a simple gear-like spline would be much more satisfactory, intuitively robust, and have far less parts.

(9) At present, there appear to be two parallel load paths for the weight of the whole load assembly, one through the lower umbrella and one through the support legs.  Presumably these will fight each other, given installation accuracies and/or thermal differentials.

From 2.1.2 Thermal Expansion

(1) The design features required for thermal isolation and allowance for thermal expansion differentials between the core components (including the inner vacuum vessel wall) during  bakeout, operation, and fault (e.g., loss of coil coolant during bakeout) were not adequately described or analyzed. It was therefore not possible to evaluate  fully the adequacy of the design in this area.

(2) Differential stresses due to bakeout and cooldown are uncertain at this stage of the design and deserve serious consideration in view of the large relative motions reported.

From  2.1.3 OH Transition

(1) The design of the Ohmic Heating solenoid includes transitions in conductor cross section in both upper and lower sections of the solenoid. These transitions resulted in the need for additional OH coils in those regions. The presentations indicated that this feature of the design was chosen to reduce power system requirements for the OH power supply while maintaining a minimized plasma aspect ratio. It is the opinion of the committee that  this was a poor choice, and that the transition in conductor section with its attendant discontinuity in thermal and structural behavior of the solenoid will limit performance and life of the solenoid.

(2) The solenoid suffers in particular at the sharp transition from small to large conductor cross-section.  This need not be sharp, and if spread over 10 to 20 turns there would be a negligible impact on the resistive dissipation (which the existing power supply has to drive.) The stress concentration would likely disappear  and also the need for the awkward G10 filler pieces in the winding would be eliminated.

(3) The conductor transition region should be properly modeled, including both thermal (end of shot) and electromagnetic stresses.

From  2.1.4 Insulation

(1) The operating temperature of the TF insulation is very far above that acceptable in Europe for long-life epoxy-glass + kapton insulation, even with vacuum impregnation, which is not intended here.  We strongly advise making some kind of trial assembly (not necessarily in the design geometry) to check the fatigue life of the proposed insulation system and give a fairly accurate simulation of the insulation compression and shear intended at the most highly stressed parts of NSTX.

(2) As with the TF core, the solenoid insulation has very demanding thermal and mechanical stresses  - same comment as for TF core.

(3) "Cooling wave" differential stresses in the solenoid insulation have not been evaluated yet but can be critical, depending on the cooling wave geometry and propagation speeds.

From  2.1.5 Leads

(1) In MAST and TCV, the exit region of the solenoid tails from the  winding is very  highly stressed.  Both these machines have added spurs of brazed-on copper to the conductor, which complete < half a turn on the end of the solenoid to take the radial load on the existing conductor better than could be taken by the insulation wrap alone.

(2) The transition region at the braze joint appears problematic.

(3) Verify that the "rats nests" potting of the TF (and solenoid) tails is strong enough to stop these tails moving - pure resin is not that hard!

(4) Consider a different connection scheme for the "rats nests" of TF core connections, to avoid a net toroidal loop from the interconnections of the limbs (e.g., treat as six layers instead of 3, or cross the axis. )

(5) We were not shown how the main TF feeder was connected to the coil set: if not considered carefully, this can generate a significant n = 1 error - and already there are rather too many assertions for other n = 1 sources that "a few Gauss doesn't matter".  Unless you pay attention and/or minimize errors, (e.g., the main solenoid feeder loops) where negligible or zero cost is implied, they may add up (in some scenarios of current directions) and catch you out, as happened in the JET design.

From  2.1.6 Assembly

(1) The design features which were intended to locate core components were presented only at the conceptual level and the specification of tolerance for the positioning of central core components was not complete. Although it was not possible to evaluate completely the adequacy of the design in this area, it is the opinion of the committee that the present design for locating core components is deficient.

(2) Consider putting the “ therm” insulation on the solenoid surface (not  forgetting the magnetic diagnostics) instead of trying to stick it to the inside of the (stepped) Inconel tube.

From  2.2.2 Ceramic Break

(1) Differential thermal expansion of the center tube with respect to the main vessel: sometimes 617oC versus near-ambient, sometimes near-ambient versus 150 (or 350 )oC results in approximately a 1" differential movement to

be absorbed by the bellows without putting severe tension on the ceramic rings. This is very demanding on the bellows design.

(2) The analysis of thermal and/or mechanical stresses on the ceramic break not complete enough to have confidence in the survivability of the break.

(3) The design of the vacuum vessel should provide for rapid removal and replacement of the ceramic break in the event of failure.

(4)  An RDAC to produce and evaluate the performance of a prototype ceramic break for the vacuum vessel should be undertaken immediately. This activity will require completion of worst case analysis of thermally and electromagnetically induced motions at the attachment points in order to define the test parameters.

(5) Electrical isolation of the central wall of the vacuum vessel is given as a General Requirement. This requirement should be carefully reviewed by the physics group to assess alternatives which might pose lower risk to the integrity of the vacuum vessel.

(6) The HI insulators may well break over during any strong VDE.  Perhaps a spark-gap (e.g., the divertor throat!) should be provided.  Why are two required?  SPHEX runs like HIT but with a solid copper center rod connected directly to a solid (ungapped) flux conserving shell.  Why are any required?  DIII and TdeV have operated with floating biased divertors, which are enormously easier to engineer.

From  2.2.4 Disruptions

(1) Halo current effects can weld any internal sliding or bolted joints, can rip "single bolt fixed" tiles off their carriers, and can produce large n = 1 forces on the center stack, stabilizer plates, divertor plates, etc. Their magnitudes need to be estimated and the associated stresses calculated and allowed for.

(3) There is a need to have more completely evaluated disruption - induced voltages on OH and PF coils.  Is the insulation with respect to ground adequate?

From  2.4 PF Coils

(1) SND operation generates vertical forces on PF coils including the OH solenoid, which have to be reacted.

From  2.5 Assembly and Alignment

(1) A clear understanding of the alignment requirements between coils, vessel, passive plates, and Plasma Facing Components is required in order to evaluate the system design and assembly requirements. The Physics group needs to develop a "coil location" requirement. The Installation manager needs to develop an installation plan and tooling that will meet those requirements.  Coil magnetic centers, not geometric centers, should be used wherever practical.

(2) There is a consensus that the assembly of the center stack is challenging.  Trade-offs between different assembly scenarios should be carried out.  For example:

(a) Can the inner TF bundle be vacuum impregnated?

(b) Should the Inconel sleeve be split along its length and welded over the assembled coils?  This would allow for prebending of all TF bends, top and bottom before the TF bundle is assembled.  Perhaps the TF,  OH and inner PF's could be combined into a bonded, impregnated assembly.

(3) The vessel-to-vessel support, PF coil to coil supports and center stack system all have sliding surfaces or gaps to allow for thermal expansion differences.  Gaps and sliding systems can develop problems in returning repeatedly to the proper position after thermal cycles or disruption- induced movements.  The system requires precision alignment but it is not clear how this is achieved.

(a) Consider spring loaded key guided PF coils that are automatically returned to hard stops for operational alignment.

(b) Perhaps the PF coil support plates which are welded to the vessel could be designed as flexible supports.  Machining or laser cutting slots could produce flexible supports that would nominally self center the coils.  These flexible supports would increase the path length from the vessel to the PF coils thereby reducing heat loss during bakeout.

From  2.7 Failure Modes

(1) There was talk of accelerating the TF current decay if a fault was detected.  This is the worst possible action to take if the fault is a shorted TF turn. Some "smarter" trip-function matrix is needed.

(2) A "Significant Event" analysis should be performed and plans developed to mitigate all unacceptable conditions.  Some issues to evaluate are:

(a) Loss of site power

(b) A void develops in the heating insulation

(c) Water drenches the device

(d) Coil shorts

(e) PF power supply "Latches On" or "Shuts OFF"

From  6.1 R&D Plan

(1) A "Research and Development" plan needs to be developed with key issues identified with a schedule showing when the desired information is required.  For example:

(a) tests on the insulating scheme should be performed identifying bonding parameters, and electrical hold-off capabilities.  These need to be performed at relevant temperatures.

(b) Helicoflex seals - reliability at temperature

(c) Thermal insulation of center stack; how hot does the epoxy get if  the Inconel wall under the inboard tiles gets to 600oC ?

(d) Splice joints - strength and manufacturability