71-961108-TEE-01

8 November 1996

Dr. John Willis

U.S. Department of Energy

Office of Fusion Energy Science

Office of Energy Research

ER-55, Germantown

Germantown, MD 20874

SUBJECT: STUDY to SITE NATIONAL SPHERICAL TORUS EXPERIMENT 		(NSTX) at D-SITE

Dear Dr. Willis

The purpose of this memo is to forward the results of our study of whether to locate NSTX at PPPL’s D-Site. As you know, the NSTX device is currently planned to be located at PPPL’s C-Site. Due to the early termination of TFTR operation in Fiscal Year 1997, utilization of the D-site facility for NSTX has become an extremely attractive alternative. PPPL’s D-site represents the largest fusion asset in the US and it is of interest for the US fusion program as well as for PPPL to take advantage of this important national asset. Our study has shown that NSTX is very compatible with D-site. D-site offers a number of important advantages for NSTX over the present C-site option:

1. D-Site offers a power system that is better suited than C-Site for the challenging NSTX power requirements not only for the base NSTX program but also for possible future upgrades.

2. Utilization of one of the TFTR NBI beam enables NSTX to obtain the desired NBI capability  [5 sec, 5 MW (80 keV)] without additional R&D. Early NBI operation will enable NSTX to challenge the beta limit for a spherical torus.This is an important NSTX mission element. The NBI is also a flexible tool to introduce plasma rotation for MHD wall stabilization as well as for obtaining high confinement regimes. In the later phase of NSTX with possible upgrades to the center stack, it is possible to accommodate up to 4 TFTR NBI beam systems in the D-Site Hot Cell .

3. The D-Site Hot Cell with its 55 foot high shield wall offers adequate radiation shielding for upgrades using D-D beams. The Hot Cell crane capability meets the NSTX requirements. In addition, the Hot Cell offers a dedicated NSTX Test Cell with its own air ventilation system, well separated from the TFTR device, eliminating possible complications related to the future TFTR removal activities.

4. The present TFTR Control Room will be converted for NSTX. This will provide an ample space for the national research team. The lack of the control room space at PLT was one of the concerns raised at the NSTX Engineering, Cost, and Schedule Review.

71-961108-TEE-01

8 November 1996

5. Although the day one (i.e., TPC) cost for NSTX at D-Site is slightly greater than C-Site by $0.8M, the cumulative cost including the NBI upgrade is $1.6M lower than C-Site. This should have a modest impact on NSTX’s First Plasma date. We are continuing to search for innovations that would allow us to accelerate NSTX’s First Plasma date.

We propose that the cost of clearing the TFTR Hot-Cell ($0.6M) not be included in the Project TPC since this is a planned TFTR S&R activity.

The cost comparison of the C-site and D-site option is shown below.  The cost estimate was developed by the NSTX WBS managers.

Cost Summary of D-site vs. C-site

|  | NSTX at C-site (Escalated k$) | NSTX at D-site Hot Cell (Escalated k$) |
| --- | --- | --- |

| Total Construction Cost (TEC) | $20,405 K | $21,087 K |
| --- | --- | --- |

| Total Project Cost (TPC) | $23,027 K | $23,809 K |
| --- | --- | --- |

| NBI Upgrade | $9,782 K | $7,322 K |
| --- | --- | --- |

| TPC PLUS NBI Upgrade | $32,809 K | $31,131 K |
| --- | --- | --- |

On the basis of the analysis summarized here we propose to change the baseline plan to specify installation of NSTX in the D-Site Hot Cell.

Sincerely,

_____________________________

Ron Davidson

Director

71-961108-TEE-01

8 November 1996

cc:	R. Davidson, PPPL		J. Hoy, DOE-OFES

D. Meade, PPPL		W. Dove,DOE-OFES

R. Goldston, PPPL		J. Faul,DOE-PG

J. Schmidt, PPPL		G. Pitonak,DOE-PG

G.H. Neilson,PPPL

M. Peng, ORNL

M. Ono, PPPL

P. Heitzenroeder, PPPL

C. Neumeyer, PPPL

R. Hawryluk, PPPL

M. Williams, PPPL

Project Files