71-971125-PPPL-TEgebo-01

National Spherical Torus Experiment

NSTX

Statement of Work

for the

Oak Ridge National Laboratory

for

Program Management, Physics Support and Plasma Facing Component Engineering Support

NSTX-SOW-07-001

Revision 0

11/25/97

________________________________

J. Chrzanowski

NSTX Torus WBS Manager

________________________________

C. Neumeyer

NSTX Project Engineer

________________________________

F. Malinowski

PPPL Quality Assurance Engineer

________________________________

J. Levine

NSTX ES&H Engineer

________________________________

M. Ono

NSTX Project Director

1.0 Introduction

This Statement of Work is for the services of an NSTX Program Director, Physics Analyses (WBS 72) supporting the Design and Construction Phase of the NSTX and engineering, design and manufacturing oversight of the NSTX Plasma Facing Components as described in section 3.0 below. The work described in this Statement of Work shall be performed by the Oak Ridge National Laboratory (ORNL).

2.0 Applicable Documents

The document that defines the project management methodology to be applied to NSTX during the design and construction phase is the NSTX Project Execution Plan (PEP), NSTX-PLAN-PEP-032. A WBS dictionary containing a description of the work scope for each WBS element is included as Annex I to the PEP. In addition the following documents are applicable to this Statement of Work:

NSTX Documents and Record Plan (NSTX-PLAN-DOC-017)

Document Distribution and Control Procedure (NSTX-PROC-035)

NSTX Project Requirements Document (NSTX-RQMT-PRD-025)

NSTX General Requirements Document (NSTX-RQMT-GRD-018)

NSTX Quality Assurance Plan (NSTX-Plan-QAP-023)

NSTX Configuration Control (NSTX-PROC-006)

NSTX Design Verification (NSTX-PROC-004)

3.0 Requirements and Responsibilities

3.1 	Project Management & Integration (WBS 71)

3.1.1 ORNL shall provide the services of a senior manager to serve as the NSTX Program Director. The NSTX Program Director has management responsibility for developing and updating the mission, the physics objectives, and the program requirements of the NSTX design and construction activities.

3.2 	Project Physics (WBS 72)

3.2.1 ORNL shall provide Plasma Shaping Design Analysis - Perform MHD equilibrium calculations to determine NSTX plasma shaping flexibility for use on NSTX.

3.3 	Plasma Facing Components (WBS 11)

3.3.1 ORNL shall complete the engineering design of the following:

3.3.1.1 Inner Wall - increase thickness of tiles, replace TZM material with Inconel (except for pins), and incorporate additional pins as required (per test results - 3.3.3)

3.3.1.2 Inboard Divertor - adopt revised scheme for active cooling using panels located within bore of center stack casing. Design cooling circuits for center stack casing flanges.

3.3.1.3  Outboard Divertor - Complete design of supports to the vacuum vessel.

3.3.1.4  Passive Plates - Revise plate geometry and change to faceted front face tiles. Revise the copper plate thickness to resolve bolting issues. Eliminate tile overlap in toroidal direction allowing +/- 1/16” tolerance between tiles in toroidal direction. Tile overlap (overlapping bevels or equivalent) to be maintained in poloidal direction. Include overhang of tiles into toroidal gap between plates. Complete design of supports and jumpers, including brackets to the vacuum vessel. Complete design of saddle connections.

3.3.1.5 General - Develop details of cooling line electrical isolators and vacuum vessel feedthroughs. Finalize locations of diagnostics . Change cooling lines to 1/2”.

3.3.2 Engineering Analysis - Update and document design basis calculations :

•	Thermal analysis for Inner Wall, Inboard Divertor, Outboard Divertor and Passive Plates.

•	Electromagnetic/Structural Analysis for Inner Wall.

3.3.3 Engineering Tests

•	Pullout Tests - Complete pullout tests for inner wall tiles to determine adequacy of pins (tests at high temperature not required).

•	Inner Wall Tile - Construct Test Assembly.

3.3.4 ORNL shall provide sufficient management and administrative support to ensure timely and proper completion of the assigned work.

4.0 Quality Assurance (QA) Requirements

4.1 ORNL activities in support of the NSTX Project shall be performed using controls that comply with DOE Order 5700.6c and address the implementation of QA Programs for Basic and Applied Research as outlined in DOE Standard DOE-ER-STD-6001-92. Specific attention to the Design (calculation checks, validation, etc.) and Document Control (revision control, review cycles, etc.) sections is appropriate for this scope of work.

4.2 ORNL shall inform PPPL of the QA Plan to be used for these activities and submit it for PPPL acceptance. The controls of ORNL NSTX Quality Assurance Plan, QAP-X-97-FE-001, appear to be adequate.  Minor changes are likely needed ("Purpose" and "Clarification’s, Additions, and Deletions") to broaden the applicability of revision 0 of this document.

5.0 Documentation Requirements

Subcontractor shall comply with all NSTX documentation requirements as delineated in the NSTX Project Plans and Project Procedures, including the NSTX Documents & Records Plan .

6.0 Reporting Relationships

6.1	ORNL shall report to the NSTX Physics Manager for technical direction of Project 	Physics Tasks.

6.2	ORNL shall report to the NSTX PFC Manager (George Barnes) for technical 	direction of Plasma Facing Component Tasks.

6.3	The Procurement Technical Representative (PTR) shall be the NSTX Project 	Control Manager. ORNL shall immediately notify the PPPL Subcontract 	Administrator and the PTR whenever technical direction provided will result in cost 	and or schedule impact to previously estimated work. ORNL shall not proceed with 	such work without prior written authorization from the PPPL Subcontract 	Administrator.

7.0 Deliverables (ref 3.3)

Inner Wall Tiles/ center stack casing interface design - 10/31/97

Inboard Divertor/ center stack casing interface design - 10/31/97

Outboard Divertor/ Vacuum Vessel Interface Design - 11/28/97

Passive Plate/ Vacuum Vessel Interface Design - 11/28/97

Inner Wall Tiles Design - 1/31/98

Inboard Divertor Design - 1/31/98

Outboard Divertor Design - 1/31/98

Passive Plate Design - 1/31/98

Documented Analysis Calculations (see 3.3.2) - 1/31/98

Results of Pullout Test (see 3.3.3) - 1/31/98

Heat Flux Test Fixture (see 3.3.3) - 1/31/98

PFC Drawing Tree (spreadsheet format acceptable) - 1/31/98

PFC Drawing Set (as required to fabricate and assemble PFC’s) - 1/31/98

8.0 Funding

The effort described herein will be funded on an annual basis (subject to the availability of funds)