## Slide 1: NSTX-U Facility and Diagnostic Plans for FY 2016- 2018
Masa Ono and J. Menard
FWP 2018 Budget Planning Meeting
April 13, 2016

## Slide 2
Presentation Outline
Facility Operations Status and Plan
Facility Enhancement Status and Plan
Facility Milestones and Budget
Summary

## Slide 3
NSTX-U Facility Is Now Operational
Upgrade Project Completed on Schedule and Cost
HHFW System
1st NBI
2nd NBI
NSTX-U
All six NBI sources are now operational, supporting high performance H-mode experiments

## Slide 4: Latest run plan schedule for 2016 ~ 7.2 run week to date, goal is to operate 18 run weeks
Want as much data as possible for IAEA synopses/meeting, APS-2016
December 2015: 0.4 run weeks (XMP)
January 2016 (3 weeks): 2 run weeks (H-mode), PAC-37
Two week maintenance: NBI T-line repair, Argon purge system, LITER, Diagnostics
• February – March (4 weeks): 2.4 run weeks (routine H-mode)
Two week maintenance: BN piece recovery, NBI Auto/transformer/T-line repair, LGI, MGI, Diagnostics
March – April: (3 weeks) 2.4 run weeks (high power H-mode)
Two week maintenance: BPM, NBI LHe refrigeration turbine regeneration, LGI, MGI, Diagnostics
April – July 10.8 run weeks to complete FY16 run with extended run days
August: Start outage: install high-k, high-Z tiles, …
Resume operations winter 2017 for FY17: ~ 16 run weeks
Outage
Completed Plasma Operations
Planned Plasma Operations
4

## Slide 5: NSTX-U device performance progression
1st year: Limit forces to ½ way between NSTX and NSTX-U, and ½ of the design-point heating of any coil
  Presently operating at BT ~ 0.65T
  Increase to BT ~ 0.8T after completing engineering analysis
2nd year goal: Full field and current, coil heating to ¾ of limit
3rd year goal: Full capability
Parameter | NSTX (Max.) | Year 1 NSTX-U Operations | Year 2 NSTX-U Operations | Year 3 NSTX-U Operations | NSTX-U Ultimate Goal
IP [MA] | 1.2 | ~1.6 | 2.0 | 2.0 | 2.0
BT [T] | 0.55 | ~0.8 (0.65) | 1.0 | 1.0 | 1.0
Allowed TF I2t [MA2s] | 7.3 | 80 | 120 | 160 | 160
IP Flat-Top at max. allowed I2t, IP, and BT [s] | ~0.4 | ~3.5 | ~3 | 5 | 5
5

## Slide 6
Presentation Outline
Facility Operations Status and Plan
Facility Enhancement Status and Plan
Facility Milestones and Budget
Summary

## Slide 7
New
center-stack
2nd NBI
Li granule injector
High-Z PFC diagnostics
Off-midplane 3D coils (NCC)
up to 1 MA plasma gun
Lower divertor cryo-pump
Upgraded CHI for ~0.5MA
Graphite CHI/Lower Bullnose
DBS, PCI, or other intermediate-k
Snowflake
Run Weeks:
Five Year Facility Enhancement Plan (green – ongoing)
Incremental enables 5 year plan enhancements including NCC, ECH
MGI disruption mitigation
4 coil AE antenna
HHFW limiter upgrade
Establish control of:
Rotation
High kq
Laser blow-off
Boronization
Enhanced MHD sensors
Neutron collimator
Charged fusion product
sß
Upgraded halo sensors
Pulse-burst MPTS
18
10-12
16
ne
Integrated Scenarios
Core Science
Boundary Science
+ Particle Control
2015 | 2016 | 2017 | 2018 | 2019
Upgrade Outage
1.5  2 MA, 1s  5s
MAPP
42 ch MPTS
48 ch BES
MSE/LIF
FIReTIP
Major enhancements:
Base funding
incremental funding
Fiscal Year:
1 MW ECH/EBW
12-16
High-Z tile row on lower OBD
CPS dB diag.
0.5-1 MA CHI
qmin
7
LiTER
Upward
LiTER
APD-based GPI
Scanning MLP
XICS
Divertor Prad
Resistive
Bolometer

## Slide 8
MIT PSFC Complements Well Existing NSTX-U Capabilities
Discussions Started on Various Diagnostic Implementations
X-ray Imaging Crystal Spectroscopy
MIT is developing a next generation, servo-driven, compact scanning MLP system
MIT will enhance NSTX-U GPI systems
Avalanche-PhotoDiode (APD)-based GPI

## Slide 9
New
center-stack
2nd NBI
Li granule injector
High-Z PFC diagnostics
Off-midplane 3D coils (NCC)
up to 1 MA plasma gun
Lower divertor cryo-pump
Upgraded CHI for ~0.5MA
Graphite CHI/Lower Bullnose
DBS, PCI, or other intermediate-k
Snowflake
Run Weeks:
Five Year Facility Enhancement Plan (green – ongoing)
Incremental enables 5 year plan enhancements including NCC, ECH
MGI disruption mitigation
4 coil AE antenna
HHFW limiter upgrade
Establish control of:
Rotation
High kq
Laser blow-off
Boronization
Enhanced MHD sensors
Neutron collimator
Charged fusion product
sß
Upgraded halo sensors
Pulse-burst MPTS
18
10-12
16
ne
Integrated Scenarios
Core Science
Boundary Science
+ Particle Control
2015 | 2016 | 2017 | 2018 | 2019
Upgrade Outage
1.5  2 MA, 1s  5s
MAPP
42 ch MPTS
48 ch BES
MSE/LIF
FIReTIP
Major enhancements:
Base funding
incremental funding
Fiscal Year:
1 MW ECH/EBW
12-16
High-Z tile row on lower OBD
CPS dB diag.
0.5-1 MA CHI
qmin
9
LiTER
Upward
LiTER
APD-based GPI
Scanning MLP
XICS
Divertor Prad
Resistive
Bolometer

## Slide 10
Enhanced Capability for PMI Research
Multi-Institutional Contributions
ORNL
Divertor Imaging
Spectrometer
Dual-band fast IR Camera
Multiple fast 2D visible and IR cameras with full divertor coverage
Li I
C II
LLNL, ORNL, UT-K
U. of Illinois, PPPL
LLNL
ORNL
Divertor fast eroding thermocouples
MAPP probe for between-shots surface analysis – Now taking data

## Slide 11
LITERs
First Year Boundary Physics Tools
Boronization, Lithium Evaporators, Granule Injector
Lithium Evaporator (LITERs)
Granule injector (GI) for ELM pacing
Rotating Impeller
Successfully tested
on EAST and DIII-D
Granules: Li, B4C, C
f ~ up to 500 Hz
dTMB Gas Cabinet
for safety
Boronization System
Granular Reservoir
• LITERs filing set up in high bay south of NSTX-U Test Cell.
• Argon purge system implemented for Li safety, used for the quick argon vent.
• Expected to be operational in May.
• Multiple injection and glow made more uniform boronization.
• System is working very well. Multiple # of boronization including daily ones performed. Also being used for He glow discharges.
• Granule injector installed on NSTX-U.
• Undergoing commissioning and initial injection during the next plasma operation.
11

## Slide 12
Successful FDR held in February
  82% of raw materials on-site
  Fabrication contract placed
  Schedule to be delivered in September in time for the installation in NSTX-U.
Final design rated to 10 MW/m2 for 1s heat flux for 1000s of cycles
High-Z Tile to be installed for FY 2017 run
Design to replace a row of the graphite tiles in lower outer divertor
Surface heat flux
Temperature
12
  Installation flexibility introduced to accommodate “as built” vessel tolerances
  Edge and access-way chamfers introduced to reduce heat-flux peaking
Test cut from one of the castellations performed

## Slide 13
Physics design completed in collaboration with ORNL.
  Defined the geometry, plenum sizes, ability to pump various geometries.
Conceptual design process has been initiated:
  Draft GRD has been formulated.
  Initial designer sketches of in-vessel implementation completed.
  Two types of PFCs being investigated.
  CHI/lower bullnose section may be pursued as separate job as it may be enhanced for high Z and flowing Li in the future.
  Goal is to to have the system ready for installation in the 2018-2019 outage under base funding.
Need 0.8 mTorr or better
Lower Divertor Cryo-pump to Provide Pumping over a Wide Range of Divertor Geometries and Core Densities
13
350C
bake
A
Passive
bake
350C
bake
B
CHI/ lower bullnose
Baffle diagonal / upper bullnose
Baffle top / horizontal
tiles
High-Z, high q
Graphite
High-Z, low q
PFC type:
Two PFC Options for CDR
Or

## Slide 14
Divertor Cryo-pump Design Activities Started
Design also includes appropriate PFCs and L-He refrigerator
Cryo-ring
Transfer line layout
Initial in-vessel geometry has been laid out. MIT will design cryo-ring.
  Pump radius, throat dimensions taken from the modeling.
  The entire lower outer divertor region to be reduild.
• Cryo-baffle design to be finalized at CDR.
  Diagnostic access and cryo-ring maintainability are major design consideration.
  Two PFC options (Graphite or high Z) are pursued for CDR.
• A 400W liquid He refrigerator considered to reduce NBI operational risk and operational cost savings.
  A room adjacent to NSTX-U has been identified for energy efficient location with utilities already available.
  Replaces the outdated TFTR-era L-He refrigerator reducing risks to the NBI operations.
14

## Slide 15
TFTR legacy liquid helium refrigerator
A new efficient 400 W liquid helium (L-He) refrigerator to minimize down time risk and reduce operating cost
• 36 years old 800 W refrigerator for NBI #1 and 2 operating at near capacity due to long piping causes significant heat loss – also quite expensive to operate and maintain.
• If a cold box failure occurs, the repair will require reverse engineering and loss of several months will severely impact NSTX-U operations.
Proposed 400 W L-He refrigerator ~ $2.5M
500 feet of supply and return piping
• To be located in the Cryogenics Compressor Room near NSTX-U, accommodates all envisioned loads by benefit of greatly reduced piping and heat loss (x 3-4).
• The unit would reuse power and space previously used for a 225 Watt refrigerator with all the utilities and compressors available.
• Benefit:
  Remove down time risk
  Increase available L-He for NSTX-U including NBI and Divertor Cryo-pump.
  Reduced operating and maintenance cost
NSTX-U
Former TFTR Test Cell

## Slide 16
Implement Divertor Cryo-Pump with base funding
Exploring various options to minimize cost for timely completion
Transfer line layout
16
Schedule for Cryo-pump and PFCs:
  Start formal design collaboration with MIT in Feb 2016.
  CDR – planned in July 2016 with cost and schedule developed
  PDR – planned in Nov. 2016
  FDR – planned in March 2017
  Complete fabrication of in-vessel components – May 2018
  Complete installation of in-vessel and ex-vessel components – Feb. 2019
Cryogenic vacuum feedthrough concept.
Cryopump with redesigned divertor support structures
Schedule for L-He refrigerator:
  PDR in June 2016 with external reviewers
  Start procurement – Sep. 2016.
  Start installation – June 2017
  Commission – Oct. 2017

## Slide 17
New
center-stack
2nd NBI
Li granule injector
High-Z PFC diagnostics
Off-midplane 3D coils (NCC)
up to 1 MA plasma gun
Lower divertor cryo-pump
Upgraded CHI for ~0.5MA
Graphite CHI/Lower Bullnose
DBS, PCI, or other intermediate-k
Snowflake
Run Weeks:
Five Year Facility Enhancement Plan (green – ongoing)
Incremental enables 5 year plan enhancements including NCC, ECH
MGI disruption mitigation
4 coil AE antenna
HHFW limiter upgrade
Establish control of:
Rotation
High kq
Laser blow-off
Boronization
Enhanced MHD sensors
Neutron collimator
Charged fusion product
sß
Upgraded halo sensors
Pulse-burst MPTS
18
10-12
16
ne
Integrated Scenarios
Core Science
Boundary Science
+ Particle Control
2015 | 2016 | 2017 | 2018 | 2019
Upgrade Outage
1.5  2 MA, 1s  5s
MAPP
42 ch MPTS
48 ch BES
MSE/LIF
FIReTIP
Major enhancements:
Base funding
incremental funding
Fiscal Year:
1 MW ECH/EBW
12-16
High-Z tile row on lower OBD
CPS dB diag.
0.5-1 MA CHI
qmin
17
LiTER
Upward
LiTER
APD-based GPI
Scanning MLP
XICS
Divertor Prad
Resistive
Bolometer

## Slide 18
Microturbulence Diagnostics Being Enhanced
To measure ion to electron gyro-scale, magnetic fluctuations
Beam Emission Spectroscopy
for low k turbulence
48 chs being readied
Cross-Polarization Scattering for magnetic fluctuations being developed in collaboration with DIII-D and MAST
Low k
High k
UC Davis
UCLA
High-k scattering for ETG
Available for FY 17
BES-2D-Fiber
Assembly
U Wisconsin
4x1 subharmonic mixer array
Collection optics (Bay L)
4–channel CPS system in 2017

## Slide 19
Enhanced FIDA will measure NBI distribution function
For NBI fast ion transport and current drive physics
Vertical
Tangential
Fast Ion D-Alpha Diagnostics
Taking data on NSTX-U
FIDA Views
• Both vertical (perpendicular) and new tangential (parallel) FIDA systems are ready.
• Both FIDA systems have 10 ms, 5 cm, ≈ 10 keV resolutions.
HHFW
Antennas
CHI Gap
Center-Stack
sFLIP
TAE antennas
FY 2016 - 2017 Energetic Particle Conceptual Design and Diagnostic Upgrade
  SS-NPA installed and taking data.
  sFLIP installed for lost ion measurements
  Active 2 X 2 TAE antennas installed. Initially passive spectroscopy then active excitation at few kW level.
  Proto-type charged fusion product (CFP) profile diagnostic is being prepared to be installed.
  8+8 reflectometry array available for AEs.
UCI
FIU
UCLA

## Slide 20
Disruption Mitigation System for NSTX-U Massive gas injection system at multiple poloidal positions
  - Massive gas injector system at multi
  poloidal location with identical injection set-up
  - Compact power supply proto-type tested at UW
  - A new double solenoid MGI design (zero net J x B
  torque) based on the ORNL ITER MGI design
NSTX-U MGI Valve
• Successful final Design Review of MGI system was held on February 18, 2016.
• All the MGI components including MGI valves were delivered to PPPL from U. Washington and being installed on NSTX-U.
• Preliminary MGI test is planned in May, 2016 for the initial gas pulses into NSTX-U.
  MGI also tested on the U. Washington test stand with magnetic field
Magnets
Magnets
MGI
Valve
U. Washington

## Slide 21
Flexible Mid-Plane Feedback Coils for MHD Studies
NCC will greatly enhance MHD physics studies and control
Base Budget – NCC engineering conceptual design work to develop reliable cost and schedule is being concluded to focus engineering resources to divertor cryo-pump design.
Incremental Budget – Enables continued design, development, and installation of NCC.
Full toroidal NCC array (2 x 12)
Partial toroidal NCC array (2 x 6)
Full NCC
Existing
RWM
coils
Partial NCC
• 6-channel Switching Power Amplifier (SPA) powers independent currents in existing EFC/RWM Coils supporting experiments
• NCC (a facility enhancement) can provide various NTV, RMP, RWM, and EF selectivity with flexibility of field spectrum (n ≤ 6 for full and n≤ 3 for partial)
Columbia U
General Atomics
21

## Slide 22: NCC Lorentz and Thermal Stress Analysis
NCC = Non-axisymmetric Control Coil
NCC Coils Design Activity Made Significant Progress
Test area prepared to perform conductor sample R&D
• Candidate conductor for test sample received for R&D.
• R&D facility prepared and test being conducted.
• The R&D selection criteria include thermal capability, manufacturability, impact on interfacing objects, fabrication lead time and cost.
• Cost and schedule will be prepared as part of the CDR which is targeted for May, 2016.
2 x 12
Coil
Lead
Tile
PP
3 kA,0.1 MW/m2 Plasma Heating,5s pulse,1200 s reprate
Thermal Analysis
End of Last Pulse Temp (8 hours)
With Lead Clamp, 50 C Heat-up, 3kA+ Background Field
22

## Slide 23
New
center-stack
2nd NBI
Li granule injector
High-Z PFC diagnostics
Off-midplane 3D coils (NCC)
up to 1 MA plasma gun
Lower divertor cryo-pump
Upgraded CHI for ~0.5MA
Graphite CHI/Lower Bullnose
DBS, PCI, or other intermediate-k
Snowflake
Run Weeks:
Five Year Facility Enhancement Plan (green – ongoing)
Incremental enables 5 year plan enhancements including NCC, ECH
MGI disruption mitigation
4 coil AE antenna
HHFW limiter upgrade
Establish control of:
Rotation
High kq
Laser blow-off
Boronization
Enhanced MHD sensors
Neutron collimator
Charged fusion product
sß
Upgraded halo sensors
Pulse-burst MPTS
18
10-12
16
ne
Integrated Scenarios
Core Science
Boundary Science
+ Particle Control
2015 | 2016 | 2017 | 2018 | 2019
Upgrade Outage
1.5  2 MA, 1s  5s
MAPP
42 ch MPTS
48 ch BES
MSE/LIF
FIReTIP
Major enhancements:
Base funding
incremental funding
Fiscal Year:
1 MW ECH/EBW
12-16
High-Z tile row on lower OBD
CPS dB diag.
0.5-1 MA CHI
qmin
23
LiTER
Upward
LiTER
APD-based GPI
Scanning MLP
XICS
Divertor Prad
Resistive
Bolometer

## Slide 24
Solenoid-free start-up in support of ST-FNSF
NSTX-U CHI configuration permits ~ 400 kA level start-up
• The resistive voltage divider network was made functional, and many of the components related to a fast voltage monitoring system were installed.
• All of the connections of the gas lines to the CHI gas injection systems have been completed.
• Initial testing of the CHI system into a plasma load will begin in the near future.
• Inj. Flux in NSTX-U is about 2.5 times higher than in NSTX
• NSTX-U coil insulation greatly enhanced for higher voltage ~ 3 kV operation
CHI Start-Up in NSTX-U
U. Washington
An ST-FNSF like CHI configuration will undergo plasma tests on QUEST after FY 2016 NSTX-U operation (after July 2016).
All metal (high-Z) CHI electrodes provide valuable information for NSTX-U (presently graphite electrodes)
QUEST CHI Experiment to test high-Z electrode operation
U. Washington

## Slide 25
HHFW system will be ready for operation
Antenna plasma conditioning to start in April
New Compliant Antenna Feeds
Allow HHFW antenna feedthroughs to tolerate 2 MA disruptions
- Prototype compliant feeds tested to 46 kV in the RF test-stand. Benefit of back-plate grounding for arc prevention found.
- RF diagnostics also installed.
• All sources will be ready to support HHFW operation in April.
Transmission lines installed & tuned.
Antennas were re-installed with the new feeds and back-plate grounding
Additional ground installed

## Slide 26
CHI can form a 200-400 kA seed plasma, but it is too cold for HHFW absorption.
Use of ECH can “bridge the Te gap” to where HHFW and then NB current drive can support the ramp and sustain the current – crucial for OH solenoid-free compact STs
  Good first pass absorption predicted.
Goal of first ECH power in 2019 run with 15% incremental funding.
28 GHz ECH System Design Progressing Well
Complete conceptual design and cost/schedule this year
28 GHz Gyrotron Development
• 2nd generation 1.5 MW 28/35 GHz gyroton being developed at Tsukuba University. (See back-up slide). Power test to start in May.
• Incremental budget enables continued design and procurement of the ECH system.
NSTX-U
Test Cell
Power Supply Room
Gyroton room
28 GHz Gyrotron Room
28 GHz 1 MW Tube by Tsukuba
26
Gyrotron will be located in the TFTR basement. Stray magnetic fields was measured to be negligible

## Slide 27
Presentation Outline
Facility Operations Status and Plan
Facility Enhancement Status and Plan
Facility Milestones and Budget
Summary

## Slide 28
Base NSTX-U Facility/Diagnostic Milestones
To complete Cryo-pump, NCC, and ECH/EBW Engineering Designs in FY 2016
28

## Slide 29
• Research operation started on December 18, 2015. With 7.23 run weeks achieved thus far we are at 40% of 18 run week target.
• The commissioning phase is nearly complete and the plasma operation is now becoming routine and the availability increasing to 90 – 100% range.
• NBI and boronization are now supporting operations with routine H-mode access.
• Very good progress on the plasma control system, quickly achieving H-mode and high performance discharges comparable to the best NSTX plasma parameters.
• A number of enhancements are being implemented to support the NSTX-U research plan. installation of high-Z tiles and complete conceptual engineering design for divertor cryo-pump, NCC, and ECH this year.
• Divertor cryo-pump, outer lower divertor PFCs will be implemented in the base plan.
Summary of Facility and Diagnostics
Research operations successfully started

## Slide 30
Back-Up slides

## Slide 31
Digital System Provides Electromechanical Coil Protection
DCPS supporting the research operation very nicely
Protects the NSTX-U coils and mechanical structure against electromagnetic loads
Computes forces and stresses in realtime based on reduced models of the full mechanical structure
Redundant systems
Full commissioning of the system went very well; DCPS is now routinely supporting operations.
Coil and Plasma Current Measurements
Realtime Acquisition #1
Realtime Acquisition #2
Stand Alone Digital Coil Protection Computer
Digital Coil Protection & Plasma Control Computer
Level-1 Fault Interface
Power Supply Suppress and Bypass
Rectifier Hardware Controls
Discussions on going with ITER for collaboration
Notes: A bunch of sensors give conditioned current inputs
Output is Go/NoGo… Fault/No Fault

## Slide 32: NSTX-U Operations Encountered # of Issues All the issues were resolved
TF Water Fitting Repair – Cracked brass fitting –two out of 72 fittings - traced to possible stress during tightening. Made adjustment to procedure to minimize stress.
Gas Injection System - Traced to a pressure gauge in the high field side gas injection system – broke down due to changing gas line pressure - “Paschen” curve. Moved the pressure gauge to the high pressure side.
Water leaks in power supply room – changed hoses and components – this one could occur in the future because of the vast number of hoses and components.
Protection system related – DCPS and other protection systems – adjusted the protection systems after confirming safe operation.
Water leak in flow meter – broken plastic side wall - replaced all the meters of similar age (~ 16 years)
No significant loss of operations time due to motor generator nor NBI
32

## Slide 33
Both Neutral Beams are still at LHe temperatures. Routine panel regens. Cold box regen this maintenance period after 15 months operation. NBI supporting experiments daily.
Neutral Beam #2
  N2A Source has operated to 86 kV.
  N2B Source has operated to 80 kV.
    High voltage crowbars under investigation this maintenance period.
  N2C Source has operated 80 kV.
Neutral Beam #1
  N1A Source has operated up to 76 kV.
  N1B Source has operated up to 70 kV 1 MW.
  N1C Source had operated up to 90 kV 2 MW.
HHFW Systems – Recovery Corrective Action Plan (CAP) activities to resume operations:
  HHFW #1-4 Recovery CAP completed. Awaiting AC Power to start conditioning.
  HHFW #5-6 testing done & CAP nearly completed. Awaiting AC Power to condition.
Heating System Operations
33

## Slide 34: Excellent Progress on Magnetic Diagnostics
Plasma current, loop voltage, poloidal flux and field measurements in good shape supporting EFIT.
  All integrators recalibrated
  Rogowski coils fully calibrated, and pickup compensations established
  All Mirnov sensors and flux loops have had their position determinations refined based on calibration shots.
New diamagnetic loop system is now operational also supporting EFIT.
  Based on using the Rogowski return loop as a diamagnetic loop.
  Successfully implemented and eliminated the old TF-coil diamagnetic system.
High-n and high-f array is taking data.
  Used for detecting rotating Kink/Tearing modes, *AE modes.
RWM sensors are writing mode fit data to the tree.
  Realtime RWM sensor codes have also been upgraded, now in testing.
34

## Slide 35: Significant Progress in Plasma Control System Now supporting the research operations
PCS has been supporting plasma operations.
  Pre-programmed PF control & simple radial and vertical position control, IP control.
  Gas injection and pre-fill control
  Real-time magnetic sensor calibrations
  Beam control from PCS
  Automatic discharge shutdown following disruption detection.
  rtEFIT running in the background on the control machines
  RWM/EF coil current control from PCS has been restored.
Some older less-reliable real-time digitizers have been replaced, and a new every-shot latency measurement system has been implemented.
Near term PCS steps
  Finish testing rtEFIT and begin to use ISOFLUX shape control
  Finish the recommissioning of the RWM/EF control algorithms
  Then move on to profile control and snowflake divertor control.
35

## Slide 36
Ready now/commissioning
  Magnetics for equilibrium reconstruction
  Halo current detectors
  High-n and high-frequency Mirnov arrays
  RWM / Locked-mode sensors
  MPTS (42 ch, 60 Hz)
  T-CHERS: Ti(R), V(r), nC(R), nLi(R), (51 ch)
  P-CHERS: V(r) (71 ch)
  Edge Rotation Diagnostics (Ti, V, Vpol)
  Beam Emission Spectroscopy (48 ch)
  Midplane ME-SXR (200 ch)
  SAMI edge field pitch diagnoistc
  Midplane tangential AXUV bolometer array (40 ch)
  Ultra-soft x-ray arrays – multi-color
  Fast Ion D profile measurement (perp + tang)
  Solid-State neutral particle analyzer
  Neutron measurements
  Charged Fusion Product
  Fast IR camera (two color)
  Material Analysis and Particle Probe
  AXUV-based Divertor Bolometer
  Tile temperature thermocouple array
  Fast visible cameras
  Visible bremsstrahlung radiometer
  Visible and UV survey spectrometers
  VUV transmission grating spectrometer
  Visible filterscopes (hydrogen & impurity lines)
  Wall coupon analysis
  1-D CCD H cameras (divertor, midplane)
  2-D divertor fast visible cameras (4)
  Two-color intensified 2D cameras TWICE (2)
  Edge neutral density diagnostic ENDD
  IR cameras (30Hz) (3)
  Dust detector
  Edge Deposition Monitors
  Scrape-off layer reflectometer
  Edge neutral pressure gauges
Ready by mid-run
  Fast lost-ion probe (energy/pitch angle resolving)
  Microwave Reflectometer
  MSE-CIF (18 ch)
  MSE-LIF (20 ch)
  Divertor VUV Spectrometer (SPRED)
  Gas-puff Imaging (500kHz)
  Langmuir probe array
  Divertor fast eroding thermocouple
Ready by end of run
  FIReTIP interferometer
Ready next run year
  Laser blow-off system
  Poloidal FIR high-k scattering
  Midplane metal foil bolometer
  Metal foil divertor bolometer
New capability,
Enhanced capability
NSTX-U diagnostics commissioned or being prepared
More than half are led by collaborators
36

## Slide 37
Tsukuba University is developing Prototype 28 / 35 GHz Gyrotron for NSTX-U & G-10/PDX
●Design Parameters of New Tube
Power (MW)
Beam Current (A)
0
80
0
80
Beam Current (A)
0
3
Power (MW)
0
3
28 GHz
34.77 GHz
→ New design of cathode, cavity and mode converter for 1.5 – 2 MW
2986 mm
TE8,5 (28 GHz) & TE10,6 (35 GHz) by the selection rule
• 2 MW calculated outputs at both 28 & 35 GHz are obtained.
• We (Tsukuba) started its fabrication and it will be tested this summer.