ITER Session - Tuesday evening

- Update on Project Management and ITER Design Review given by G. Janeschitz (45 min)

  - Some specific issues in each area mentioned

- GJ then fielded questions and comments, many of them rather critical (45 min)

- Status of Management and Project

  - ITER Design Review is an open process – want to hear from everyone

    - R. Buttery commented that ITER Design Review Web site is password protected

  - ITER “rapidly” staffing up to ~200+ professionals, ~150 subcontractors

    - Comment that did not seem as if there would be enough professionals

      - GJ indicated the numbers could shift between subcontract and professional

  - Trees cleared, site being flattened

  - 2016 is earliest estimate for first plasma

    - If everything goes wrong that can go wrong, not until 2019

    - Probably somewhere in between

- Key Issues in Design Review

  - TF: Q=10 will be hard to achieve if 10% lower TF

    - Degradation of performance with 5% lower TF, but still significant operating space with Q>10

  - TF no longer an issue

    - Problem was with tin strands – not compacted well in each bundle

    - Can compact better, but not 100% sure can meet requirement

    - Bronze strands fulfill ITER requirement

    - Decision not easy

      - All partners can make tin strands

      - Only some partners confident enough to make bronze strands

      - Decision to be made imminently

  - Heating and current drive

    - 1-3 year delay in second NB line

    - Only 8-16 MW on Day 1 with first beamline

    - Severely underpowered

    - Use money from second beamline to augment with ICH and ECH (x2) for Day 1

      - EU/Japan will have to foot costs for second beamline with additional partner funds (not from ITER), OR program will be delayed

      - Concern is that ICRH may not work (based on C-Mod experience with metal walls, except when well-boronized)

      - ECH is expensive, and also may not work

      - 2 x 0 = 0, but at least the money is spent for Day 1

    - Concern that current drive is insufficient (scope out LHCD)

  - RWM/ELM control

  - Blanket design

    - Shimada/Lackner exchange interesting

    - Lackner coordinating a committee to investigate how to decrease time to swap blanket to under 3 years!

      - Being led to say something by Shimada

      - Lackner not ready to commit to any recommendation

      - Shimada seemed to be saying “the design we have is good enough”

  - Tritium release requirements more stringent than previously thought

    - Nothing quantitative