## Sheet1
2011-12 WPI TSG XPs and XMPs
Relevant FY10 XP# | WPI XP# | Lead Author(s) | Title | Requested Run Days | Minimum Requested Run Days | Total Run Time Allocation | Priority 1 FY11 Run Time | Priority 2 FY11 Run Time | Priority 1 FY12 Run Time | Priority 2 FY12 Run Time | Combine with | FY11/12 | Priority | Requirements | Notes | Related Milestone | ITPA Task NSTX-U | Draft XP Received | WPI TSG Review | Run Dates | Comments | Proj. Rev.
XP1009/10 | WPI-1 | G. Taylor | Low Plasma Current Fully Non-Inductive HHFW H-Mode | 1.5 | 1 | 0.5 | 0.5 |  |  |  |  | FY11/12 | 1 | Prf = 3-4 MW, MSE-LIF | With SFSU TSG (FY12: 1 day) & ASC TSG | R12-2 | IOS-5.2 | 2010-01-14 | 2010-01-14 |  |  | 2010-02-16
| WPI-2 | G. Taylor | HHFW Ramp Up of Inductively Initiated Plasma from 250 to 400 kA | 1 | 1 | 0.5 |  |  | 0.5 |  |  | FY11/12 | 1 | Prf = 5 MW, MSE-LIF | With SFSU TSG (FY11: 0.5 days) & ASC TSG. Establish good plasma position control at I_p = 250 kA | R12-2 | IOS-5.2
| WPI-3 | G. Taylor | HHFW Heating of CHI-initiated Plasma | 1.5 | 1 | 0.5 |  |  | 0.5 |  |  | FY11/12 | 1 | Prf = 2-3 MW, MSE-LIF | With SFSU TSG (FY11: 0.5 days, FY12: 0.5 days) & ASC TSG | R12-2
| WPI-4 | G. Taylor | Assess HHFW+NBI H-Mode Operation with Pnbi ~ 6 MW | 2 | 1 | 1 |  |  | 1 |  | 16 | FY12 | 1 | Prf = 5 MW, Pnbi = 6 MW ,MSE, MPTS, CHERS, rf probes, FIDAs | Could combine with WPI-16 | NSTX-U | IOS-5.2
XP1016 | WPI-5 | J. Hosea | Study HHFW Power Coupling Versus ELM Activity | 2 | 1 | 0.5 |  | 0.5 |  |  |  |  | 2 | Prf = 2-3 MW |  |  | IOS-5.2 | 2010-03-29 | 2010-04-01 |  |  | 2010-04-28
XP1017 | WPI-6 | J. Hosea | RF Heating at Divertor/SOL Regions | 2 | 1 | 0 | [6 empty] | 3 | Prf = 2-3 MW, ERD, TS, CHERS, IR, Fast IR, probes | Benchmark AORSA RF code extended to open field lines in the SOL |  | IOS-5.2 | 2010-03-29 | 2010-04-01 |  |  | 2010-04-28
| WPI-7 | J. Hosea | Turbulence Characteristics for HHFW Saturated Stored Energy versus RF Power | 1 | 0.5 | 0 | [6 empty] | 3 | Prf = 4 MW, high-k scattering | With T&T SFG. Setup 135286 HHFW He H-Mode
XP1012 | WPI-8 | B. LeBlanc M. Podesta W. Heidbrink | HHFW Absorption in NBI-Heated Plasmas | 1 | 1 | 1 | 1 |  |  |  | 24 |  | 1 | Prf = 3 MW | Piggtback WPI-24 |  | IOS-5.2 | 2010-03-08 | 2010-02-18 |  |  | 2010-04-26
| WPI-9 | M. Podesta | Dependence of TAE Dynamics on Plasma Rotation | 1 | 0.5 | 0.5 |  |  | 0.5 |  |  |  | 2 |  | Target shot already exists. May require some development time to optimize n=3 braking in L-mode plasma. | IR12-2 | EP-2 | 2010-09-28 | 2010-10-06
| WPI-10 | M. Podesta | Clamping of Edge Rotation by HHFW | 0.5 | 0.5 | 0 | [6 empty] | 3 | Prf ≥ 2 MW, FIDA, sFLIP, ssNPA,MPTS, CHERS, ERD, pCHERS. MSE
XP1011 | WPI-11 | E. Fredrickson | Documentation of GAE Avalanches | 1 | 0.5 | 1 | 1 |  |  |  | 14, 26 |  | 1 | BES, reflectometers, tFIDA, vFIDA, MSE | Target plasmas exists; need new diagnostic data. Combinewith WPI-14 (XP1011) |  | EP-2, EP-4 | 2010-03-10 | 2010-02-18 |  |  | 2010-03-10
| WPI-12 | E. Fredrickson | Document of High Frequency CAE | 0.5 | 0.5 | 0 | [6 empty] | 1 | BES, MSE, reflectometers, Firetip, FIDAs | Target plasma exists XP1011 |  | EP-2
XP1014 | WPI-13 | E. Fredrickson | Documentation of Angelfish | 1 | 0.5 | 0.5 |  |  |  | 0.5 |  | FY12 | 2 | BES, reflectometers, FIReTIP, FIDAs, NPA, MSE | Bt ~ 2.5 kG |  | EP-2, EP-4 | 2010-02-23 | 2010-02-18 |  |  | 2010-04-23
XP1011 | WPI-14 | E. Fredrickson | H-mode TAE Avalanches | 1 | 1 | 0 |  |  |  |  | 11, 26 |  | 1 | BES, reflectometers, FIReTIP, sFLIP, tFIDA, vFIDA, NPA, MSE | Combine with WPI-11 |  | EP-2, EP-4 | 2010-03-10 | 2010-02-18 |  |  | 2010-03-10
| WPI-15 | E. Fredrickson | TAE Antenna Commissioning | 1 | 0.5 | 1 | 1 |  |  |  |  | FY11 | XMP | MSE with beam blips | Target plasmas exists, need to develop antenna source. |  | EP-4
| WPI-16 | M. Bell | HHFW Heating to Increase Non-Inductive Current Fraction in NBI H-modes | 1.25 | 0.5 | 0 |  |  |  |  | 4 |  | 1 | Prf = 3 MW, Pnbi = 4-6 MW, MSE, MPTS, CHERS | Prefer HHFW CD phasing, Could combine with WPI-4 | R12-2, R12-3, NSTX-U | IOS-5.2
| WPI-17 | N. Crocker | Investigation TAE Radial Phase Variation | 0.5 | 0.25 | 0 | [6 empty] | 3 | Multichannel Reflectometer array, BES, FIDA's, M3D-K, NOVA-K, TRANSP | Small vertical plasma jogs of shot like 141711 TAE period without adversely affecting plasma | IR12-2 | EP-2
| WPI-18 | D. Smith | Measure HHFW Wavefield | 0.5 | 0.25 | 0 | [6 empty] | 3 | HHFW with amplitude modulation, BES, X-rays, reflectometry
| WPI-19 | S. Kaye | Assessment of Fast Ion Loss by Microturbulence | 1 | 1 | 0.5 |  |  |  | 0.5 |  |  | 3 |  | T&T TSG | IR12-2 | EP-3
| WPI-20 | R. Maingi | Comparison of H-mode Pedestal Characteristics with RF and NBI | 1 | 0.5 | 0 |  |  |  |  | 5, 25 |  | 3 | Prf = 3 MW | Need to have RF H-mode developed before this XP. Move to Boundary TSG? | FY11 JRT?
| WPI-21 | A. Bortolon | Effect of Low Frequency MHD on Fast-Ion Confinement | 1 | 1 | 0 | [6 empty] | 3 | FIDA, MPTS, MSE, Mirnov, NPAs, FILD, BE | SPIRAL, FIDASIM. Start with data from XP1015 | IR12-2 | EP-2
| WPI-22 | A. Bortolon | Effect of Induced 3D Fields on Fast-Ion Distribution | 1.5 | 1 | 1 | 0.5 | 0.5 |  |  | 27 |  | 1 | FIDA's, MPTS, MSE, Mirnov, NPAs, FILD. | Requires low impurity level. SPIRAL, NUBEAM, and FIDASIM |  | EP-6
| WPI-23 | S. Medley | High Energy Feature Study with NPA and NBI Scans | 0.5 | 0.3 | 0 | [6 empty] | 3 |  | Needs non-lithiumized machine |  | EP-2
| WPI-24 | D. Green | Benchmark Predictive Capability of Advanced Quasi-linear RF Simulation Codes. | 0 | 0 | 0 |  |  |  |  | 8 |  | 1 | HHFW,ERD, FIDA, Edge probes, MPTS, CHERS, Reflectometer. AORSA, sMC, NuBeam and CQL3D. | Combine with WPI-8 (XP1012) |  | IOS-5.2
| WPI-25 | A. Diallo | Plasma Current Scaling of the Pedestal Structure in RF Heated ELMy H-mode | 0 | 0 | 0 |  |  |  |  | 5, 20 |  | 3 | MPTS, CHERS, Reflectometry, GPI, High-k, BES, MSE | Piggyback on WPI-5. Move to Boundary TSG? | NSTX-U
| WPI-26 | A. Bortolon | Effect of High Frequency Bursting Modes on NBI Current Drive Efficiency | 0.5 | 0.5 | 0 |  |  |  |  | 11, 14 |  | 3 | FIDA, MPTS, MSE, Mirnov, NPAs, FILD, BES | piggyback on XP1011 (WPI-11 & WPI-14) | IR12-2
| WPI-27 | A. Loarte | Assessment of effects of 3-D fields on fast particle losses in ITER | 2 | 1 | 0 |  |  |  |  | 22 |  | 1 |  | Transfer from ITER/CC. Combne with WPI-22 |  | EP-6
| WPI-28 | A. Bortolon | t-FIDA Commissioning | 1 | 0.5 |  | 1 | 0.5 |  |  |  | FY11 | XMP | FIDAs, MPTS, MSE, Mirnov, NPAs, FILD | XMP - Requires low impurity level, perform 1-2 weeks after start of run. SPIRAL, NUBEAM, and FIDASIM |  | EP-6
XMP-26 | WPI-29 | J. Hosea | HHFW Plasma Conditioning to High RF Power | 4 | 4 | 4 | 3 | 3 | 1 | 1 |  | FY11/12 | XMP | Prf = 5 MW | XMP
2011-03-16 |  |  | Total XP Days | 26.75 | 17.3 | 7.5 | 3 | 1 | 2.5 | 1
|  |  | Run Guidance | 10 | 10 | 10 | 3 | 1 | 4.5 | 1.5
Revision 8 |  |  | Total XMP Days | 6 | 5 |  | 5 | 4 | 1 | 1