## Slide 1
In-Vessel installations and calibrations have concluded, and activities have shifted to preparations for installing the new centerstack. Last in-vessel activities will be the installation of last rows of tiles, and the possible installation of a new window at Bay B.
Most Buswork ready & reinstalled in the NTC by September.
Centerstack, flex bus and umbrella covers in place by late November.
Clean/Photo/Close in December, followed immediately by the initial pump-down/leak check. NSTX-U turned over to Operations.
A limited Centerstack bake is planned for January/February.
Field Coil Power Testing and the ISTP to CD-4 in February.
  Assumes that the full-bake and preparations for Physics Operations will occur after CD-4
  No Vessel Entry after CD-4
Transition to Operations
Milestones to NSTX-U CD-4

## Slide 2
The NSTX-U Activity Certification Committee (ACC) reviews continue, and is comprised of representatives from PPPL Engineering, Research, Safety, and the DOE PSO is currently reviewing technical and safety systems for NSTX-U
A PPPL Internal QA Audit of NSTX-U Start-Up has been performed, and has resulted in a punch list of critical Start-Up and Test Procedures for both CD-4 and subsequent physics operations.
A Readiness for Operations Review is being arranged through the University, and is prerequisite for our safety certificate prescribing allowable operating parameters. Committee members from LANL, GA, JLAB, MIT, ORNL, CCFE & UW will be here for this review in December.
Approvals for Operations

## Slide 3
Center Column Assembly
  Assembly of the Center Stack Casing is ongoing in the South High Bay.
  The center column pedestal has been fabricated and is being fit-up.
  Assembly/leak-check/fit-up of the ceramic breaks and PF coils is in progress.
  The TF/OH assembly will be ready to be brought to the South High Bay in October.
  Centerstack, flex bus, umbrella covers in place on NSTX-U by November.
TVPS and Gas Delivery Systems
  Assembly of the TVPS is going well and should be ready for pre-operational testing in Oct.
  High and low field gas fueling systems pre-op testing in Oct.
  MGI vacuum vessel interfaces in progress, but system will not be installed until after CD-4.
TMB System
  Dang Cai has completed a preliminary design that will be reviewed on Monday afternoon.
  Working towards a January 2015 installation.
Preparations for Operations

## Slide 4
MPTS Commissioning
  Work packages in place to complete VV work and verify sight lines.
  Still much work on flight tube, laser dump, and alignment systems. Competing for resources.
  MPTS racks/optics box installed in Sept. Fibers/power in Oct.
  Still need to schedule time for MPTS calibrations. After CD-4?
  Design/layouts are being developed for the new MPTS Burst laser.
PF1 Field Changes
  PF1A and PF1C Upper and Lower Coils will be powered.
  PF1B Upper and Lower will not be powered at the start of the run (terminated into resistors and MOV’s).
  FCPC has been configured.
  Connections/labeling in the test cell still required.
Preparations for Operations

## Slide 5
MG#1 Weld Repairs
  Weld repairs have been completed.
  Re-commissioning of MG# 1 is planned in September.
Field Coil Power Conversion (FCPC) Commissioning
  AC primary Power Systems and new rectifier firing generators ready to support Ops
  The new PLC-based fault relaying system to replace electromagnetic relays is being commissioned. Individual rectifier power testing will follow.
  The Digital Coil Protection System (DCPS) software is being tested, and hardware is being designed/fabricated. Integrated system testing in September.
  The Power System Real Time Control (PSRTC) is being designed and and is expected to be ready for testing in October.
RF Systems
  Reinstallation of RF piping for HHFW has been rescheduled for after CD-4.
  The ECH Pre-ionization system will be ready for CD-4 operation.
Preparations for Operations

## Slide 6
Ip Calculator
  Schematics have been completed and circuit board assembly/testing in progress.
  All parts are here at PPPL.
  Integrated system testing has been rescheduled for November.
Stand Alone Digitizers (SAD II)
  System FDR is being rescheduled for this month.
  Assembly/testing complete in September.
Test Cell Mods
  A design for a new North Door shield wall has been completed. Work will start in Oct.
Neutron Calibration
  The new source on site, but equipment for calibration must be redesigned/built.
  Calibration must be performed with all VV structures in place.
Preparations for Operations

## Slide 7
Neutral Beam #2
  Primary power systems and protective relaying are ready to start power supply testing.
  Re-commissioning/testing of the low voltage supplies (Arc, Fil, Decel) has been completed.
  Ion sources are being installed.
  NB#2 will be ready to pump-down in December. Maybe an earlier pump-down for leak check.
  Refrigerator start-up and cryogenic cool-down in mid-October.
  Expect to start ion source pre-operational testing (PTP-11) in December to complete the NB#2 CD-4 in Dec./Jan. As always, ion source operations will restrict test cell access.
Neutral Beam #1
  After CD-4, will begin to re-commission NB#1, although will attempt to make parallel progress whenever possible.
Preparations for Operations