## Slide 1
In-Vessel installations and calibrations have been completed. Clean/Photo/Close is complete. Neutral Beam ducts are in place and the remainder of the primary vacuum boundary seals are being installed.
Buswork installations in progress.
We expect to be under vacuum and leak checking by the end of the month.
A limited Centerstack bake is planned for February.
Field Coil Power Testing and the ISTP to CD-4 in March.
  Assumes that the full-bake and preparations for Physics Operations will occur after CD-4
  No Vessel Entry after CD-4
Transition to Operations
Milestones to NSTX-U CD-4

## Slide 2
The NSTX-U Activity Certification Committee (ACC) reviews continue, and is comprised of representatives from PPPL Engineering, Research, Safety, and the DOE PSO is currently reviewing technical and safety systems for NSTX-U
A PPPL Internal QA Audit of NSTX-U Start-Up has been performed, and has resulted in a punch list to track the >120 critical Start-Up and Test Procedures for both CD-4 and subsequent physics operations.
A Readiness for Operations Review will be held next week, and is prerequisite for our safety certificate prescribing allowable operating parameters. Committee members from LANL, GA, JLAB, MIT, ORNL, CCFE & UW will be here for this review.
Approvals for Operations

## Slide 3
Center Column Assembly
  Complete and installed.
TVPS and Gas Delivery Systems
  Assembly of the TVPS is complete and ready for pre-operational testing.
  High and low field gas fueling systems pre-op test procedures have been approved.
  TVPS and GDS control systems are still being commissioned
  MGI vacuum vessel interfaces in progress, but system will not be installed until after CD-4.
TMB System
  TMB system design is complete.
  All required components are on order
  Working towards a January 2015 installation.
Preparations for Operations

## Slide 4
MPTS Commissioning
  In-vessel work completed, and sight lines verified.
  Installation of flight tube in progress
  MPTS racks/optics box have been installed
  Still need to schedule time for MPTS calibrations. After CD-4.
  Design/layouts have bben developed for the new MPTS Burst laser.
PF1 Field Changes
  PF1A and PF1C Upper and Lower Coils will be powered.
  PF1B Upper and Lower will not be powered at the start of the run (terminated into resistors and MOV’s).
  FCPC has been configured.
  Connections/labeling in the test cell still required.
Preparations for Operations

## Slide 5
MG#1 Weld Repairs
  Weld repairs have been completed.
  Maintenance procedures in progress with plans to spin up the set in December.
Field Coil Power Conversion (FCPC) Commissioning
  AC primary Power Systems and new rectifier firing generators ready to support Ops
  The new PLC-based fault relaying system to replace electromagnetic relays is complete and tested. Individual rectifiers are being prepared for open circuit testing.
  The Digital Coil Protection System (DCPS) has been installed, and is undergoing pre-operational testing.
  The Power System Real Time Control (PSRTC) design is complete and is being tested in conjunction with the rectifier firing generators. DCPS and PSRTC will be ready to support FCPC Dummy Load testing.
RF Systems
  Completion of the reinstallation of RF piping for HHFW has been rescheduled for after CD-4.
  The ECH Pre-ionization system will be ready for CD-4 operation.
Preparations for Operations

## Slide 6
Ip Calculator
  Design & Schematics have been completed and circuit board assembly/testing in progress.
  Test Procedures and an Operations Manual have been approved
  Integrated system testing has been rescheduled for February.
Stand Alone Digitizers (SAD II)
  Design is complete and reviewed.
  Assembly/testing/installation complete by late December.
Test Cell Mods
  A design for a new North Door shield wall has been completed. Installation in Dec/Jan
Neutron Calibration
  Completed for two in-vessel diameters
Preparations for Operations

## Slide 7
Neutral Beam #2
  Primary power systems have been energized, and testing of Accelerator circuits in progress.
  Re-commissioning/testing of the low voltage supplies (Arc, Fil, Decel) has been completed.
  Ion sources are being installed and wired. Pre-operational testing in progress.
  NB#2 will be ready to pump-down in December.
  Helium Refrigerator compressors have been started and clean-up of process gas in progress.
  Expect to start ion source pre-operational testing (PTP-11) in December to complete the NB#2 CD-4 in Jan/Feb. As always, ion source operations will restrict test cell access.
Neutral Beam #1
  After CD-4, will begin to re-commission NB#1, although will attempt to make parallel progress whenever possible.
Preparations for Operations