## Slide 1
The ES&H Executive Safety Board (upon recommendation of the Activity Certification Committee - ACC) has approved NSTX-U operations within the bounds of our Safety Assessment Document and Safety Certificate. The NSTX-U Start-Up (OP-NSTX-02) and Coil Energization (ISTP-001 have been exercised to a point to allow the “CD-4” plasma using OH, TF(.5T), PF3U/L & PF5.
Additional stages of the ISTP will be performed to provide field coil capability for commissioning the machine to support research operations, and then the actual performance of approved XP’s.
The ACC will still need to review and approve additional NSTX-U capabilities such as:
  Neutral Beam Injection
  Boronization with deuterated Trimethylboron (dTMB) using up to 50 grams
  Introduction of elemental lithium in the NSTX-U Test Cell up to 2kG.
Approvals for Operations

## Slide 2
Currently in the 2nd phase of the ISTP
  Qualify coil systems PF4, PF2U/L & PF1aU/L for operation
  Limited combined field shots for magnetic diagnostics.
  Restore PF1cU to service (PF1cL already used to commission Rogowski’s)
MPTS Rayleigh/Raman Scattering Calibrations
  Alignments need to be verified. New cameras will help
  Calibration of this new system will take ~ 5 dedicated days.
Vessel Vent in nitrogen for port work
  Install Argon Purge System TIV’s (needed for Lithium)
  Install new DTI diagnostic
  Replace Bay B Camera Shutter
  LITER and MAPP interference checks
  Bay J window installation for IRVB
  Bay L port obstruction measurement
  Window inspection/cleaning if necessary
Preparations for Operations

## Slide 3
dTMB Commissioning
  Provide time/resources for control system commissioning before the start of the bake
NSTX-U Vessel Bake
  Commission system to provide 70C water to PF1B for ~270C tile heating.
  Bakeout procedure is being updated.
  Modest temperature ramp times are being specified.
  Will remain at temperature for a tentative 3 weeks.
  Recovery from the bake expected to take ~1 week (leak checking, etc.).
Switching Power Amplifier (SPA) Re-commissioning
  SPA’s will be tested into a local resistive load during the vessel bake
  Time will be allotted to re-commissioning the RWM coils during the bake recovery.
Coaxial Helicity Injection (CHI)
  The CHI Capacitor bank has been reassembled and dummy load tested
  The CHI Control System needs to be updated before integrated system testing
  CHI operating procedures are being updated.
Preparations for Operations

## Slide 4
3rd Phase of the ISTP before Research Operations
  TF (.65T), PF (18kA), and longer pulse lengths.
NSTX-U Commissioning
  A period of plasma operations for machine evaluation, conditioning, and magnetic calibrations
NSTX-U Experimental Operations
  Planning to start first Experimental Proposals (XP’s) by October 9th.
  Scheduled to run 12 weeks in FY16..
Initial Operations

## Slide 5
Both Neutral Beams are at Lhe temperatures.
Neutral Beam #2
  N2A Source has just started Beam conditioning at 33kV
  N2B Source is Beam conditioning and running well at 45kV
  N2C Source had to be replaced and is in Arc Conditioning
Neutral Beam #1
  N1A is being prepared to start Arc Conditioning
  N1B does not have an ion source in place. A fresh spare has been moved to the test stand to begin preliminary electrical tests and Hi-Pots.
  N1C has a fresh ion source in place and undergoing initial checks before starting conditioning.
RF Systems
  RF Source Conditioning has started.
  Plan to start antenna conditioning in parallel with the vessel bake.
  Need Dedicated Conditioning Time on All Systems.
Heating System Operations