## Slide 1
NSTXU has resumed full Plasma Operations daily
2.33 run weeks accumulated thus far toward the 18 run week goal
241 plasmas on 289 attempts
Subsystems routinely supporting ops
    (MG, FCPC, NBI, DCPS, PCS, TVPS, GIS, Magnetics, CODAC, MDS+, etc…)
NBI: 4 sources supporting initial plasma operations (1ABC, 2C)
  2A and 2B high voltage transmission line faults on initial conditioning
RF fault 1/05/16 while starting up to do antenna conditioning
  Arc fault in HHFW#5 crowbar cabinet
  Breaker suboptimal operation
  Recovery in progress
  Corrective Action Plan completed. All six systems will be improved.
  Successful Peer Review held yesterday
  Repairs and changes in progress
NSTXU Initial Operations FY 2016

## Slide 2
MPTS is operational daily
dTMB Commissioning completed. Routine TMB operations to support ops.
NSTX-U Diagnostics set increasing
  Diagnostic installations continued over the maintenance weeks
  Many TVPS shutter controls completed over maintenance weeks
Additional GIS system testing
Switching Power Amplifier (SPA) operational
Coaxial Helicity Injection (CHI)
  The CHI Cap Bank and Control System continues commissioning and testing to support operations.
Progress on MGI installations
Progress on LITER
Progress on PCS control algorithms
New Features Available for Operations

## Slide 3
PF1CU increasing leakage current during morning 5 kV hipot
  Trapped water found in can around coil
  Drying has been effective in reducing leakage current
  Testing indicates the coil is sound
  Coil not needed in next operations stint so observations will continue
TF water fitting compliance
  Fittings needed some compliance to handle expansion
  WCC package completed
  Upper TF fittings completed. Lower TF fittings in progress today.
Coil set operational per set limits
Coil Issues Addressed During Maintenance Weeks

## Slide 4
Both Neutral Beams are still at LHe temperatures. Routine panel regens.
Neutral Beam #2
  N2A Source has operated to 60 kV. High voltage transmission line repairs completed.
  N2B Source has operated to 60 kV. High voltage transmission line repairs completed.
  N2C Source had operated and injected power up to 75 kV.
Neutral Beam #1
  N1A Source had operated and injected power up to 75 kV.
  N1B Source had operated and injected power up to 65 kV.
  N1C Source had operated and injected power up to 85 kV.
RF Systems
  RF HHFW #1-6 dummy load tested to 1 MW 0.5 seconds prior to Holidays.
  Plan to start antenna conditioning after arc fault recovery is completed.
  Still need some dedicated conditioning time needed on all systems.
Heating System Operations

## Slide 5
New areas posted requiring radiation training and dosimetry for Gallery
  No occupancy issues at this time
No access in the South High Bay during plasma operations
  TFTR Test Cell needed for LITER fill and testing
No access in MPTS LASER room
HP evaluating N, NE, and E NTC walls and other areas as we increase levels to get data
Penetrations and new shielding will be considered on a case by case basis.
As usual everything in the NTC has to be smeared and cleared by HP before leaving the NTC if left inside the NTC overnight.
2 shift HP coverage
New and Ongoing Requirements

## Slide 6
TMB this weekend
Scrub this weekend
Operations planned for the next 4 weeks
XMPs and XPs planned
Striving to have 6 NBI sources operational next week
RF Recovery may permit 4 sources operational for antenna conditioning and initial HHFW experiments with 2 to follow as CAPs are completed.
Next maintenance week planned 3/07/16
Operations planned through July 1 to make 18 run weeks…
Next