## Slide 1: NSTX-U Five Year Plan Refresh Status
S.M. Kaye
NSTX-U Team Meeting
4 March 2020

## Slide 2: NSTX-U will be refreshing 2014-2018 Five Year Research Plan for the period 2021-2025
Reorganize elements from 9 TSGs + Working groups into 3 mission Objectives
Responsive to recent research results, NAS, PAC recommendations and recent Community Planning Process
A boundary condition for the refreshed 5 Yr plan is NO major upgrades during this period, including …
  1 MW ECH, NCC, large scale swap for high-Z tiles
  Cryopump*, Divertor TS*
Liquid lithium program could be a central element in 2026-2030 plan
  Possible NSTX-U preparatory activities and deployments in 2021-2025 informed by technology R&D and LTX-b results
* Possible component of 2026-2030 plan

## Slide 3: Plan is being refreshed through a “One-Team” approach
Included input from feedback from potential collaborating partners on defining NSTX-U mission Objectives and underlying elements
  Videoconference on high-level Objectives; three vcs to flesh out each Objective
  How NSTX-U research can help optimize design of next-step devices (ST as well as higher aspect ratio paths)
  Burning plasma (i.e., ITER)-related physics issues
  Theory support and predictive model development
  Measurements needed to achieve goals
    Will help inform response to FOAs and FWP updates on diagnostics development and research
“Final” draft plan developed after FOA preproposal stage (early March) to ensure all input taken into account

## Slide 4: From Josh King presentation (1/22/20)

## Slide 5: Timeline for Five-Year Plan refresh
Jan. 22: Videoconference to discuss High-Level Objectives and information regarding refresh of plan
Jan. 27 (Mon), 30 (Thurs), Feb. 3 (Mon) 1 PM: Videoconferences to discuss and develop details of three Objectives
Early-Feb: FOAs issued, preproposals due Feb. 27
Mid-Feb: Complete detailed outline of plan, distribute to group for feedback
Early March: FES gives go/no-go on preproposals; Draft Plan outline finalized
April 1: Draft plan written
May 13-14: Plan vetted to NSTX-U PAC
June 9-11: Plan plus Collaborating Partner proposals reviewed by external panel
Mid-July: Funding decisions; Plan finalized by end of FY20
FES wants approved Plan and proposal reviews to be able to fund for FY21 (for full five years)

## Slide 6: Mission Objectives
Objective 1 (W. Guttenfelder):
  Extend confinement and stability physics basis at low-A and high beta to lower collisionality relevant to burning plasma regimes [NAS-1, 2, CPP-2]
Objective 2 (D. Battaglia):
  Develop operation at large bootstrap fraction and advance the physics basis required for non-inductive, high-performance and low-disruptivity operation of steady-state compact fusion devices [CPP-2]
Objective 3 (R. Maingi):
  Develop and evaluate conventional and innovative power and particle handling techniques to optimize plasma exhaust in high performance scenarios [TEC-1, CPP-3]
Dedicate some run time to:
  Support additional critical fusion science and technology development needs utilizing the unique regimes accessible in NSTX-U [NAS-1, CPP-4]