## Template
Item | Originator | Concern/Recommendation | Committee Comment/Action | Current Status | Verification Information
1 | Sichta | Consider a future software functional review, which includes a written document describing the software functions, interlocks, FMEA, and EPICS communication. | Concur: Action Schmitt
2 | Lawson | Interfaces with the Plasma Current Calculator need to be finalized. | Concur: Action Schmitt, Lawson
3 | Kaita | Make sure that there is a cog. Engineer who is responsible for completion of electrical installation procedures and drawings, and insuring that electrical installation work is executed. The electrical cog. Engineer needs to work closely with the mechanical cog. engineer to insure that the proper connections are made to the valves and a suitable integrated system test procedure (ISTP) is formulated | Concur: Action Schmitt, vonHalle
4 | Kaita | Insure that TIV control and interlocks are scheduled for implementation by the MGI need date. | Concur: Action Schmitt, Blanchard
5 | vonHalle | MGI Grounding Diagrams need to be reviewed/approved by the PPPL Grounding Engineer. Similarly all installation/access procedures need to be reviewed by the PPPL Electrical Safety Specialist | Concur: Action Schmit, Ramakrishnan, Anderson
6 | Lawson | Provide proper grounding stick and cap bank grounding points | Concur: Schnitt, McBride, Westover