

**Chit Resolution Report for**

**Field Scope**

**NSTX-U-1-2-2-CRR\_100 R1**

Prepared By: M. Safabakhsh, Cognizant Engineer

Approved By: Y. Zhai, NSTX-U Project Engineer

Approved By: R. Ellis, Chief Engineer

**Record of Changes**

|  |  |  |
| --- | --- | --- |
| **Rev.** | **Date** | **Description of Changes** |
| 0 | 1/21/2020 | Initial Release |
| 1 | 1/23/2020 | Chit Resolution from FDR 1 |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

**FDR 1:**

|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| VVHW Recovery Field Scope FDR | VVHWRECFSFDR01 | Complete the chit resolutions from previous reviews. |

Response: Chit Report was completed and signed as DMS Number:

NSTX-U-1-2-2-CRR\_100; 1/21/2020 (Closed)

|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| VVHW Recovery Field Scope FDR | VVHWRECFSFDR03 | CALC\_1-1-3-2\_CALC\_100 is missing the COG signature. Need this signature, and then filing in DMS (work with Kathleen). |

Response: The calculation form was fully signed and submitted through Kathleen to DMS on 12/19/2019. (Closed)

|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| VVHW Recovery Field Scope FDR | VVHWRECFSFDR04 | Include DVVR chits in chit report. Chit report must reference closing document numbers. |

Response: DVVR chits that were pertinent to the FDR scope are addressed in the Chit Report that was prepared for the FDR, as the Chit report was unsigned at the time of the review. (Closed)

|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| VVHW Recovery Field Scope FDR | VVHWRECFSFDR05 | NSTXU\_1-1-2\_CALC\_101 & NSTXU\_1-1-2\_CALC\_102 need to be filed in DMS. |

Response: The subject calculations were signed and posted in the DMS. (Closed)

|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| VVHW Recovery Field Scope FDR | VVHWRECFSFDR06 | Cut the lower spoke lid blocks off instead of altering them or their connection to the pedestal |

Response: The chit was considered, accepted, and is incorporated in the procedure (D-NSTXU-IP-VVHW-4087, Lower Umbrella Reinforcement Installation and Adjustment). (Closed)

|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| VVHW Recovery Field Scope FDR | VVHWRECFSFDR07 | Frictional Reusability Assessment test report must be signed by the RE and filed in DMS |

Response: The subject Test Report has been posted into DMS:

NSTXU\_1-1-2-1-2\_TREP\_100. (Closed)

|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| VVHW Recovery Field Scope FDR | VVHWRECFSFDR08 | Provide WAF form for the cost and schedule for all field scope task including labor, materials, etc. |

Response: The WAF information was developed, shared with the DRC and posted to the dashboard. (Closed)

|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| VVHW Recovery Field Scope FDR | VVHWRECFSFDR09 | For the lower spoked lid, does the tracking distance in the joint between the 2 g10 plates and the bushing meet the 0.3 inch tracking length requirement? |

Response: Vertical tracking distance (0.344 inch) meets the 0.3 inch requirement. The horizontal tracking distance (0.219 inch) does not meet the 0.3 inch requirements due to the restricted dimensions of the bolt and hole on the lid. Note that 0.3 inch tracking distance is required for not cleaned air. Silicone RTV has more than 10 times in electrical breakdown strength than that of air. Tests have been done (for other tasks) and proved that fully cured silicone RTV works very well in high V insulation in a small structure, see the test report (C-NSTX-PTP-VVIH-004, MPC 01). Using silicone RTV to seal the joint of G-10 bushing and plates meets the requirement of tracking distance. And this is incorporated in the procedure (D-NSTXU-IP-VVHW-4087, Lower Umbrella Reinforcement Installation and Adjustment). This requirement comes from NSTX-U-RQMT-SRD-004-02 Section 10.4.1 a. The casing electrical insulation with respect to ground shall be designed for a 2kV rms high-pot test voltage of duration 1 minute. 2kV rms=2.8 KV peak. By using the 10 kV/inch rule, it requires 0.3 inch air gap clearance. If using RTV to fill the air gap, it requires much less clearance. Closed

|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| VVHW Recovery Field Scope FDR | VVHWRECFSFDR12 | PF 2,3,4,5 clamps:  If tubes are used to protect threads they should be short enough to remain unloaded with the clamping force applied Silicon rubber pads should be used under the clamping plates to eliminate crushing high spots on the coil ground wrap Bellevilles should be included under the stud nuts to allow thermal expansion of the coil without significantly altering the clamping preload. Clamping preload needs to be set to exceed the net load allowed in the DCPS we need to check 20 ft-lbs vs. 45 ft-lbs |

Response: Inspection of all the tubes is in the works. Adding components such as silicon rubber and Belleville washers was not needed for PF2/3 as the PF2/3 coils are not pinned. An analysis was performed for PF4/5 and at the pinned locations, rubber pads will be added to increase friction and reduce the risk of slipping at these locations. The resolution for PF2/3 in response to this chit is documented in the memo MAG-200122-KC-01. The concern of crushing high spots on the coil ground wrap was mitigated due to coil construction. When the coil ground wrap was cured, the top and bottom were pressed flat eliminating high spots. Clamping torque values of 43 ft-lbs is the historical torque for PF 2,3,4,5 clamps and continued to use that torque will continue to be used.

**PDR 1:**

|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| Vacuum Vessel & Internal Hardware DVVR | VVIHFSPDRI01 | Create/update wiring diagrams to show all the components that need to be connected to the grounding system. |

Response: Analysis has been conducted on adequacy of the grounding of PF4-5 clamps. (see calculation form NSTXU\_1-1-3\_CALC\_100 Rev. 0). The task of completing the wiring diagrams will be assigned to the coil reclamping project team.


|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| Vacuum Vessel & Internal Hardware DVVR | VVIHFSPDRI02 | Consider performing an examination of as-built and machined part tolerances (tolerance stack up) to ensure that the frictional contact area is sufficient to prevent galling/slippage on the Truss OD/Clamp interface. What is the OD tolerance on the Truss? What is the machined ID tolerance of the Clamp? |

Response: Design drawing (D-DC11318) notes the dimensions and tolerances.

Sufficient safety margin in effective coefficient of friction (0.2) and strength of members are ensured (see calculation form NSTXU\_ 1-1-3-2 CALC 100). Closed

|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| Vacuum Vessel & Internal Hardware DVVR | VVIHFSPDRI03 | Ensure that the clamps location on the rods does not overlap the internal threads of the rod OR ensure that the clamping load does not penetrate into the rod end threads and adversely affect thread fatigue life. |

Response: The compression of the female threads due to the clamp may actually improve the fatigue life, and in any event will do no harm. See below snapshot and drawing numbers D-DC11318 and D-DC11331. Closed



|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| Vacuum Vessel & Internal Hardware DVVR | VVIHFSPDRI04 | Consider a higher strength bolt for the clamping system so that the Safety Factors can be greater. |

Response: Sufficient safety margin is included in the design of components. See details in calculation form (NSTXU\_ 1-1-3-2 CALC 100) and drawings

(D-DC11331); (D-DC11317). Closed

|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| Vacuum Vessel & Internal Hardware DVVR | VVIHFSPDRI05 | Consider re-surfacing engaging carbinite surfaces to avoid indexing due to old carbinite engagement divots. This is relative to anticipated alignment needs that will position pieces in different locations from their previous assembly. |

Response: Carbonite re-use and re-clamping (at different orientations) have been tested and proved not substantial reduction in coefficient of friction. See test report (Frictional Reusability Assessment of Carbinite-Coated Interfaces in NSTX-U) (NSTXU\_1-1-2-1-2\_TREP\_100). Closed

**PDR 2:**

|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| Vacuum Vessel & Internal Hardware PDRII | VVIHFSPDRII01 | Specify clearance requirements of TF coil to support based on analysis and capture in requirements document. Verify all design requirement basis are captured in requirements documents. |

Response: Refer to Jiaraong's calculation (NSTXU\_1-1-2\_CALC\_101) on VV9 chit and presentation which defines the clearance. The clearance meets the requirement that the support not contact the coil during operation. NSTX-U Dimensional Control Requirements NSTX-U-RQMT-RD-011-01provides the alignment requirements of the TF Coil. Closed

|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| VVIH Field Scope PDRII | VVIHFSPDRII03 | For the lower lid spoke bolted connection, you will have to ensure that the gap between the G10 plates is a little bit larger than the length of the G10 tube otherwise the tube will be crushed. |

Response: The G10 bushing is designed 5 mils shorter to provide the gap (see drawings E-DC1579 and C-DC1910). Closed

|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| VVIH Field Scope PDRII | VVIHFSPDRII04 | Use a gap filling structural epoxy to fill between the bolt and the hole/G10 bushing. |

Response: Comparing with G10 grade compressive strength, epoxy grout is not a matching replacement. The low stiffness of epoxy grout makes it ineffective compared to the stiffness of the G-10 components, and therefore we did not use it. Closed.

|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| VVIH Field Scope PDRII | VVIHFSPDRII05 | The realignment of the TF Bundle will result in the pedestal moving which in turn will relocate the ends of the spokes. The current locations of the welded blocks will not align. Recommend that the current blocks be removed and new block be field fit and welded on after TF Bundle alignment. |

Response: The existing welded blocks will be removed. Installation and assembly of the new welded blocks is part of reassembly scope and will be addressed at assembly in compliance with PPPL engineering requirements.

This is addressed in the procedure (D-NSTXU-IP-VVHW-4087, Lower Umbrella Reinforcement Installation and Adjustment), and referred from the drawings E-DC1579, C-DC1910. Closed

|  |  |  |
| --- | --- | --- |
| **Review** | **ID** | **Chit** |
| VVIH Field Scope PDRII | VVHWRECFSFDR10 | For the lower spoked lid, does the tracking distance in the joint between the 2 g10 plates and the bushing meet the 0.3 inch tracking length requirement? |

Response: Vertical tracking distance (0.344 inch) meets the 0.3 inch requirement. The horizontal tracking distance (0.219 inch) does not meet the 0.3 inch requirements due to the restricted dimensions of the bolt and hole on the lid. Note that 0.3 inch tracking distance is required for not cleaned air. Silicone RTV has more than 10 times the electrical breakdown strength than that of air. Tests have been done (for other tasks) and proved that fully cured silicone RTV works very well in high V insulation in a small structure, see the test report (C-NSTX-PTP-VVIH-004, MPC 01). Using silicone RTV to seal the joint of G-10 bushing and plates meets the requirement of tracking distance. And this is incorporated in the procedure (D-NSTXU-IP-VVHW-4087, Lower Umbrella Reinforcement Installation and Adjustment). Closed