## Slide 1: Excerpts from PAC report (p.1/3)
The PAC’s main concerns lie more in the potentially over-aggressive timeline for some milestone completions and experimental plans The incremental changes to larger high-Z coverage of the wall and introduction of liquid Li will affect the boundary science in an irreversible way. Therefore, the experimental timeline may be the most critical for the Boundary SG. The PAC is concerned that the necessary machine capabilities and equipment/upgrade/diagnostic availabilities may not line up with the timelines proposed to meet some of the Boundary SG research goals. NSTX-U is encouraged to identify all critical paths in their project plans and revise the scheduling and resource allocations accordingly so all elements are consistent.
R17-1: The PAC is concerned about the disconnect between the development of control of divertor radiation feedback, implementation of divertor radiation diagnostics, snowflake control development, time to test appropriate control algorithms and the R17-1 milestone. Not promised in milestone. Snowflake control is lagging behind? We don’t think this is an issue – Ahn/Vlad to follow up
R17-2: … it seems doubtful that the impact of a high-Z wall on operating scenarios in NSTX-U can be appropriately assessed with only a single row of high-Z tiles: Mike J
Cryopump refrigeration system: The PAC would like confirmation that the new refrigeration unit will be installed, integrated and implemented by the end of the FY2018 planned shutdown period. No CDR yet – not ready for PAC consumption. Maingi
Upward LiTER: It is important that the upward LiTER be available with sufficient time for proper assessment of particle control with lithium surfaces before changing the divertor tiles or installing the new cryopump – Kaita
1

## Slide 2: Excerpts from PAC report (p.2/3)
Pedestal diagnostics: The PAC is concerned there are not sufficient pedestal specific diagnostics to complete scientific missions in FY2016 and perhaps FY2017 campaigns. 42 channel - Diallo
Granule injector before lithium: It was not clear to the PAC how the injector schedule is impacted by LiTER lithium, cryopump, or high-Z OBD operations. LGI available now – no issue.
RF coupling diagnostics: The PAC is concerned that the diagnostic coverage at the antennas and through the scrape-off layer may be insufficient in resolving the questions of RF through the scrape-off layer. Matt R. to follow up with Rory; talk w/Kaita about MIT idea
Pre-filled Li targets: … but we emphasize the need for appropriate time and resources to be put into this project to finish it on a timeline that is acceptable for fabrication and installation. Mike J; Skinner recommends Mike J to discuss this at a liquid metal seminar
We recommend close collaboration with MAST Upgrade for the snowflake work – Menard/Maingi
…not to discount the energetic particles as an integrated problem for the boundary – Travis Gray to follow up
In the longer term, the BN limiter for the HHFW antenna will need to be replaced with a high-Z limiter as NSTX-U moves to full high-Z coverage, but this is not reflected in the graphic displaying the timeline for the transition. Not sure if we need to do this – other repercussions. Majeski.
Charge Question 2
However, given the scope of open questions and needs for ITER, the PAC feels there is room to contribute across a wider range of topics for the boundary and PFCs. The improved scaling of the SOL width, detachment physics and radiative divertor physics all seem like topics that could be of high interest to ITER. The PAC recommends communicating with the ITER team the NSTX-U research plans along these linesas an outreach to develop stronger collaborative ties between NSTX-U and ITER: Ahmed, Ahn/Vlad, Skinner&Jaworski, Chang to follow up
2

## Slide 3: Excerpts from PAC report (p.3/3)
Charge Question 3
The PAC cautions that when working towards integrated modeling and predictive capabilities that the theory collaborators need to be in close contact with both their experimental counterparts from the Boundary SG and the theorists and modelers from the other NSTX-U SGs. Maingi, Chang talk to Poli, Stan, Chuck
The PAC did not see a comprehensive plan for integrated modeling of the boundary and wall at NSTX-U … XGC ... WallDYN... The PAC would like to see a report on the vision and future plans for integrated modeling of the boundary and wall at the next PAC meeting. Maingi, Chang, Jaworski, Stotler
(Synthetic diagnostics? Where are they covered? – Need discussion in BP SFG- Skinner)
Charge Question 4
The secondary priority is the non-axisymmetric control coils (NCC). The NCC have direct impact on the boundary, primarily through ELM control. 3-D fields can also play an important role in heat flux profiles in standard and advanced divertors. Given that these topics are areas of emphasis for the NSTX-U research plan, it is clear that the NCC could be a very useful tool for the Boundary SG. This should be balanced against the resource demands that installation of these coil sets will make on the NSTX-U program, and the fact that the 3-D field effects and ELM suppression physics can and are being studied on other machines. Thought should be given to the unique ST aspects of this work in striking this balance. Jong-Kyu Park, Todd Evans to follow
(High-Z upgrade will affect all SG – how to begin discussion across SG?)
(Langmuir probes – MJ needs postdoc)
(Common area for diagnostic status? Reinke)
3