## Slide 1: Status and Plans for NSTX-U Recovery
S. Gerhardt, J. Menard, C. Neumeyer, R. Feder, and the NSTX-U Research and Engineering Teams
NSTX-U PAC-39
January 9, 2018
B-318, PPPL
This research was sponsored by the U.S. Dept. of Energy under contract DE-AC02-09CH11466

## Slide 2: Outline
Overview of Recovery & Extent of Condition
Technical Content and Impact of Recovery
Extent of Cause Review & ASO

## Slide 3: Outline
Overview of Recovery & Extent of Condition
Technical Content and Impact of Recovery
Extent of Cause Review & ASO

## Slide 4: What is NSTX-U “Recovery”?
FY2017: DOE requested PPPL to review “Extent of Condition” and submit Corrective Action Plan (CAP) as a laboratory Notable Outcome
Extent of Condition motivated by:
  4/15: OH “Arc Flash” incident
  9/15: Inadequate inboard divertor bake
  5/16: CS cooling tubes wrong material, induced current/motion, breaches
  5/16: Bent PF1AU bus bar
  6/16: Internal short in PF1AU coil
Recovery = Implementation of Extent of Condition CAP
PF1A
PF1B
PF1C
OH Coil
Cooling tubes
OH Ground Braid
Inboard Divertor

## Slide 5: 17 Reviews in FY2017 Enabled Us to Determine the Path Forward
12 Design Verification and Validation Reviews (DVVRs)
  1170 “chits” covering entire NSTX-U technical scope  443 “DVVR Issues”
  Then evaluated issue/event probability, duration, and severity  categorize / prioritize
2 Extent of Condition Reviews, chaired by Tom Todd
  Assessed issues and conclusions of the DVVRs and the PPPL planned response
  Issued 2 reports  recommendations to ensure safety and reliability of the ST core
Design Integration Review
Conceptual Design Review
Cost and Schedule Review
 346 page report submitted: Recovery scope + CAP
Total of 47 external reviewers between Extent of Condition Reviews and DVVRs
Recommendations adopted after careful & in-depth deliberations between NSTX-U, EoC Committee, PU, & DoE

## Slide 6: 6 Major Scope Areas Define Recovery
Rebuild all six inner-PF coils with a mandrel-free design
Replace plasma facing components that cannot be qualified for the full range of mechanical and projected thermal loads
Improve the “polar regions” (machine top and bottom)
Implement mechanical instrumentation to assess quality of mechanical models, trend machine behavior
Eliminate the safety issues identified with the medium temperature water system used during bakeout, improve He distribution system
Improve the neutron shielding of the test cell
Improved Reliability Safety and Compliance

## Slide 7: Outline
Overview of Recovery & Extent of Condition
Technical Content and Impact of Recovery
Extent of Cause Review & ASO

## Slide 8: New Inner PF Coils Designed to Improve Testability and Manufacturability
Three Mandrel-Free Coils
EoCondition Recommendations
  Retail all PF-1a/1b/1c coils
  Use designs that facilitate turn-to-turn testing
Previous coils fabricated on permanent mandrels
  Advantages: Precision winding surface, VPI mold, intrinsic structural support
  Disadvantages: mandrel is passive conductor
    Impacts turn-to-turn acceptance tests
    Deemed unacceptable during extent of condition review
New coils: removable mandrels
  Required new winding methods, tooling
  Major schedule impact: had been intending to use permanent mandrels until mid-May 2017
New coil design simplifies fabrication
Original PF1A Coil with Mandrel
PF1A
PF1B
PF1C

## Slide 9: New Inner PF Coils Fabrication Strategy Devised to Ensure Quality
Address quality concerns: All coil manufacturers must first successfully produce a prototype PF1A coil
  Prototype quality will be assessed by:
    On-site surveillance
    High-pot and turn-to-turn testing
    Destructive testing (sectioning)
Will use up to 4 manufacturers
  Three companies + PPPL all manufacturing prototypes
  on-site surveillance for industrial suppliers maintained through production phase
All production coils will be tested to full current and full I2t on a custom test-stand before installation on NSTX-U
Portable Clean Room at PPPL
Winding line at PPPL

## Slide 10: Improved PFC Designs
Two significant issues found with as-installed PFC designs
  Halo loads not fully accounted for in initial tile fixturing design
  Narrower SOL width now projected
Path Forward
Halo loads revisited based on NSTX, NSTX-U, MAST, other tokamak data
5 year plan research objectives + most recent SOL width models  updated heat flux specs
  PFC working group instrumental in forming these requirements
Divide tile scope into 2 regions:
  “Targeted Improvement” to chamfers, fixture scheme, material
  “Full Redesign” to enhance thermal performance  castellated tiles
All tiles will be designed to withstand BT= 1.0 T, IP=2.0 MA disruptions
Targeted Improvements
Full Redesign

## Slide 11: Castellated Tiles Maximize the Allowable Heat Flux
End of pulse thermal stresses for a castellated tile
Deployment of castellated tiles on the inner targets
Castellations minimize the surface compressive stresses for a given surface temperature
Testing material and component samples at Penn State high heat flux test facility (ORNL, PPPL)

## Slide 12: Improving Design of Polar Regions to Ensure High Performance and Reliability
Tile gap between inner and outer vessels only large enough to accommodate thermal and mechanical motion, fit-up tolerances
Issues identified
  PF1B coil limited divertor bakeout temperature
  2 large ceramic insulators potential vacuum risk
  Use of single O-rings  potential for leaks
  Plasma can sometimes impinge on PF1C enclosure
Solutions
  PF1B supported by slings  thermally isolated
  Lower ceramic insulator eliminated
  Double O-rings with pumped interspaces
  Tiles will bridge the CHI gap
Castellated Outboard Tile
Castellated Inboard Tile
Closed CHI Gap
Research / Programmatic Impact:
Coaxial Helicity Injection (CHI) as previously implemented is now excluded

## Slide 13: Key Research Impacts of Recovery Redesign
CHI program eliminated in its previous form.
  Elimination of lower ceramic insulator improves system reliability, at the expense of this research capability
  CHI design with purely internal electrodes may be realized
    Retained 2 kV power supply capability and commensurate coil design for all inner-PF coils with the express goal of allowing rapid field changes for CHI.
Ramped tiles will provide a favored helicity.
  However, a modest “reversed helicity” requirement is retained for regions where the intermediate legs of snowflake divertors may land
All inner-PF coils retained.
Bakeout system will be significantly improved, in both safety and functionality.
Leak probability and O-ring permeation significantly reduced.
Elimination of lower ceramic insulator benefits future liquid lithium research.
Tile designs are highly optimized for heat flux handling.
RF and NB systems maintained as before.
Core machine reliability should be significantly improved via numerous targeted improvements.

## Slide 14: Outline
Overview of Recovery & Extent of Condition
Technical Content and Impact of Recovery
Extent of Cause Review & ASO

## Slide 15: Extend of Cause Review Thoroughly Examined the Processes Used for Work at PPPL
Team of independent experts
  DoE Chicago ISC, ORNL, FNL, BNL, PNNL, MIT, expert consultants
Reviewed previous incident reports and CAPs dating back to NCSX, reviewed PPPL procedures, interviewed >20% of staff
  And issued reports, with Judgments of Need
In response, PPPL developed the Integrated Corrective Action Plan (ICAP), providing corrective actions across all of the laboratories management systems.
  QA/QC, Training & Qualifications, Engineering Design, Project Management, Configuration Management, Work Planning and Control, Contractor Assurance, Performance Management

## Slide 16: ICAP will Bring PPPL Management Systems Inline with Complex-Wide Standards
Lack of project-independent oversight of all laboratory activities
Create a project-independent Chief Engineer and set of Technical Authorities (subject matter experts reporting to CE)
Lack of risk-based decision making when determining appropriate level of rigor
Formalize a more rigorous graded approach (rigor commensurate with risk)
Insufficient rigor in design assurance
Enhance PPPL’s policies on engineering design assurance
Lack of clear ownership of structures, systems, and components
More clearly defined and delineated roles and responsibilities
Inadequacies in work planning and control
Strengthen the Project Management Office, Project Status Review Board, Work Planning Review Board
ICAP

## Slide 17: Summary
Reviews have determined what needs to be repaired / replaced
We have developed new designs to repair and improve components
Upgrades to laboratory processes will improve rigor of work at PPPL
Recovery will significantly enhance NSTX-U reliability & safety, provide highest-performance ST device as a robust user facility

## Slide 18: Backup

## Slide 19: NSTX-U is Now Required to Operate Under the Accelerator Safety Order
Accelerator = Device that can accelerate charge particles and create a radiation area
DOE Order 420.2 mandates a greater level of rigor in processes related to safety of employees, the public, and the environment
Initiating upgrades to our safety documentation, project training and qualification, project configuration management,…
One or more Accelerator Readiness Reviews will be required, leading to DoE site office permission to operate

## Slide 20: The NSTX-U Recovery Project Taking Specific ICAP Actions to Improve Performance
Hire a project manager
  Done: R. Feder has extensive experience fusion facilities
Complete a Preliminary Project Execution Plan
  Iterating with DoE
Set up an Interim Project Document Management System
  Done: Chit resolution system and interim DMS functioning
Stand up an Independent Advisor Board for Recovery
  In progress: Board formed and charter written
Update the project QA plan
  Rev. 0 of the QA plan is being revised given new lab-wide procedures
Enhance QA/QC and testing for critical component
  Continuous effort, e.g. enhanced magnet testing

## Slide 21: New Organization Created to Support Recovery
Shown is the present organization
  Has been considerable evolution in details over the year.
Responsible Engineer roles cover the technical scope of the project.
Project manager added in November.
Systems Engineering
and Integration
S. Gerhardt
Integrated
Analysis
P. Titus
Diagnostics
R. Ellis III
Central I&C
G. Tchilinguirian
Real Time Control
& Protection
F. Hoffmann
Power Systems
J. Dellas
Heating Systems
T. Stevenson
Vacuum & Fueling
Systems
D. Cai
VV & Internal Hdwe
M. Smith
Magnets
S. Raftopoulos
Cooling & Bakeout
Systems
J. Petrella
Test Cell
N. Atnafu
Planning & Control
S. Langish
COEs
Plasma Facing
Components
M. Jaworski
Tokamak
Core
D. Loesser
Responsible Engineers
Project Administration
K. Lukazik
Operations, ASO
T. Stevenson
Red = OBS
Construction
L. Dudek
CAD
Integration
TBD
Work Control
Center
F. Jones
Project Manager
R. Feder
NSTX-U Recovery
Director: J. Menard
Deputy: S. Gerhardt
Quality Assurance
F. Malinowski
ES&H
J. Levine
Chief Engineer
V. Riccardo
Procurement Liaison
A. White
Project Engineer
C. Neumeyer

## Slide 22: DVVR Process Identified the Issues with NSTX-U
Conducted 12 DVVRs between Jan. 18th and April 20th
Collected 1170 “chits”
Collapsed these into 443 “DVVR Issues” for the Extent of Condition Review
“Scored” the “Issues” with a system that involved event probability, duration, and severity
Topic | #chits | Topic | #chits
Integrated design | 94 | Power Systems | 84
VV & Internal Hardware | 216 | Heating Systems (NBI+RF) | 96
Magnets | 147 | Real-Time Control & Protection | 93
Vacuum & Fueling | 64 | Central I&C | 101
Cooling Systems | 71 | Bakeout System | 76
Diagnostics | 104 | Test Cell | 24

## Slide 23: The Two Extent of Condition Reviews Assessed PPPL Response to DVVRs
4 days reviews in each of March and May, 2017
Issued 2 reports with many recommendations focused on ensuring the reliability of operations.
Individual | Institution | Individual | Institution
Tom Todd, (chair) | UKAEA, retired | Ursel Fantz | IPP-Garching
Rem Haange | ITER, retired | Ron Parker | MIT
Rich Callis | General Atomics, retired | John Smith | General Atomics
Frank Casella | ORNL | Michel Huget | ITER, retired
Martin Cox | CCFE | Dennis Youchison | ORNL
Brian LaBombard | MIT | Graeme Murdoch | ORNL
Arnie Kellman | General Atomics |  | 
Total of 47 external reviewers between Extent of Condition Reviews and DVVRs