## Slide 1: NSTX-U Project / Facility Status
Masa Ono and Jon Menard
NSTX-U FY 2016 Q1 Review Meeting
February 8, 20156

## Slide 2
Facility Operations Status and Plan
On-Going Facility Enhancement Status and Plan
Longer Term Facility Enhancement Status and Plan
Summary
Back-up: Explanation of Increments
Outline

## Slide 3
FY 2016 plasma operations started
Expecting to run 18 run weeks in FY 2016
Boronizations
Plasma Operations started on Dec. 18.
H-Mode!
PAC 37
• After CD-4, we vented briefly to install various items before the bake.
• Bakeout was completed with good vacuum pressure in October
• During ISTP, MGs experienced control problem during ISTP. The problem resolved and MG#1 is supporting the operations.
• Plasma operation started on Dec. 18 and ran for 2.5 days before the holiday.
• The first boronization performed on Jan. 4, 2016 and performed four times.
• NBI injection started and H-mode access achieved quickly.
APS
ISTW 2015
November 2015
December 2015
January 2016
ISTP
Post bake
Plasma Operation
Holiday
February
Maintenance

## Slide 4
Digital System Provides Electromechanical Coil Protection
DCPS supporting the research operation very nicely
Protects the NSTX-U coils and mechanical structure against electromagnetic loads
Computes forces and stresses in realtime based on reduced models of the full mechanical structure
Redundant systems
Full commissioning of the system went very well; DCPS is now routinely supporting operations.
Coil and Plasma Current Measurements
Realtime Acquisition #1
Realtime Acquisition #2
Stand Alone Digital Coil Protection Computer
Digital Coil Protection & Plasma Control Computer
Level-1 Fault Interface
Power Supply Suppress and Bypass
Rectifier Hardware Controls
Discussions ongoing with ITER for collaboration
Notes: A bunch of sensors give conditioned current inputs
Output is Go/NoGo… Fault/No Fault

## Slide 5: Excellent Progress on Magnetic Diagnostics
Plasma current, loop voltage, poloidal flux and field measurements in good shape supporting EFIT.
  All integrators recalibrated
  Rogowski coils fully calibrated, and pickup compensations established
  All Mirnov sensors and flux loops have had their position determinations refined based on calibration shots.
New diamagnetic loop system is now operational also supporting EFIT.
  Based on using the Rogowski return loop as a diamagnetic loop.
  Successfully implemented and eliminated the old TF-coil diamagnetic system.
High-n and high-f array is taking data.
  Used for detecting rotating Kink/Tearing modes, *AE modes.
RWM sensors are writing mode fit data to the tree.
  Realtime RWM sensor codes have also been upgraded, now in testing.

## Slide 6: Significant Progress in Plasma Control System Now supporting the research operations
PCS has been supporting plasma operations.
  Pre-programmed PF control & simple radial and vertical position control, IP control.
  Gas injection and pre-fill control
  Real-time magnetic sensor calibrations
  Beam control from PCS
  Automatic discharge shutdown following disruption detection.
  rtEFIT running in the background on the control machines
  RWM/EF coil current control from PCS has been restored.
Some older less-reliable real-time digitizers have been replaced, and a new every-shot latency measurement system has been implemented.
Near term PCS steps
  Finish testing rtEFIT and begin to use ISOFLUX shape control
  Finish the recommissioning of the RWM/EF control algorithms
  Then move on to profile control and snowflake divertor control.

## Slide 7
Ready now/commissioning
  Magnetics for equilibrium reconstruction
  Halo current detectors
  High-n and high-frequency Mirnov arrays
  RWM / Locked-mode sensors
  MPTS (42 ch, 60 Hz)
  T-CHERS: Ti(R), V(r), nC(R), nLi(R), (51 ch)
  P-CHERS: V(r) (71 ch)
  Edge Rotation Diagnostics (Ti, V, Vpol)
  Midplane ME-SXR (200 ch)
  Midplane tangential AXUV bolometer array (40 ch)
  Ultra-soft x-ray arrays – multi-color
  Fast Ion D profile measurement (perp + tang)
  Solid-State neutral particle analyzer
  Neutron measurements
  Charged Fusion Product
  Fast IR camera (two color)
  Material Analysis and Particle Probe
  AXUV-based Divertor Bolometer
  Tile temperature thermocouple array
  Fast visible cameras
  Visible bremsstrahlung radiometer
  Visible and UV survey spectrometers
  VUV transmission grating spectrometer
  Visible filterscopes (hydrogen & impurity lines)
  Wall coupon analysis
  1-D CCD H cameras (divertor, midplane)
  2-D divertor fast visible cameras (4)
  Two-color intensified 2D cameras TWICE (2)
  Edge neutral density diagnostic ENDD
  IR cameras (30Hz) (3)
  Dust detector
  Edge Deposition Monitors
  Scrape-off layer reflectometer
  Edge neutral pressure gauges
Ready by mid-run
  Fast lost-ion probe (energy/pitch angle resolving)
  Microwave Reflectometer
  Beam Emission Spectroscopy (48 ch)
  MSE-CIF (18 ch)
  MSE-LIF (20 ch)
  SAMI edge field pitch diagnoistc
  Divertor VUV Spectrometer (SPRED)
  Gas-puff Imaging (500kHz)
  Langmuir probe array
  Divertor fast eroding thermocouple
Ready by end of run
  FIReTIP interferometer
Ready next run year
  Poloidal FIR high-k scattering
  Midplane metal foil bolometer
  Metal foil divertor bolometer
New capability,
Enhanced capability
NSTX-U diagnostics to be installed during first year
More than half are led by collaborators

## Slide 8
Both Neutral Beams are still at LHe temperatures. Routine panel regens.
Neutral Beam #2
  N2A Source has operated to 60 kV. High voltage transmission line repairs completed.
  N2B Source has operated to 60 kV. High voltage transmission line repairs completed.
  N2C Source had operated and injected power up to 75 kV.
Neutral Beam #1
  N1A Source had operated and injected power up to 75 kV.
  N1B Source had operated and injected power up to 65 kV.
  N1C Source had operated and injected power up to 85 kV.
RF Systems
  RF HHFW #1-6 dummy load tested to 1 MW 0.5 seconds prior to Holidays.
  Plan to start antenna conditioning after arc fault recovery is completed.
  Still need some dedicated conditioning time needed on all systems.
Heating System Operations

## Slide 9: Latest run plan schedule for 2016 Goal is to operate 18 run weeks
FY16 budgets are favorable enough to support 18 weeks
Want as much data as possible for IAEA synopses/meeting, APS-2016
December: 0.5 run weeks (XMP)
January: ~ 2 run weeks (XMP, XP), PAC-37
Two week maintenance: Neutral Beam T-line repair, Argon purge system, LITER, Diagnostics
• February: ~ 3 run weeks
March ~ 3 run weeks
  Mid-run assessment in March/April
April – June 9.5 run weeks, complete FY16 run
July: Start outage: install high-k, high-Z tiles, …
Resume operations winter 2017 for FY17: ~16 run weeks

## Slide 10: NSTX-U device performance progression
1st year: Limit forces to ½ way between NSTX and NSTX-U, and ½ of the design-point heating of any coil
  Presently operating at BT ~ 0.65T
  Increase to BT ~ 0.8T after completing engineering analysis
2nd year goal: Full field and current, coil heating to ¾ of limit
3rd year goal: Full capability
Parameter | NSTX (Max.) | Year 1 NSTX-U Operations | Year 2 NSTX-U Operations | Year 3 NSTX-U Operations | NSTX-U Ultimate Goal
IP [MA] | 1.2 | ~1.6 | 2.0 | 2.0 | 2.0
BT [T] | 0.55 | ~0.8 (0.65) | 1.0 | 1.0 | 1.0
Allowed TF I2t [MA2s] | 7.3 | 80 | 120 | 160 | 160
IP Flat-Top at max. allowed I2t, IP, and BT [s] | ~0.4 | ~3.5 | ~3 | 5 | 5

## Slide 11
Facility Operations Status and Plan
On-Going Facility Enhancement Status and Plan
Longer Term Facility Enhancement Status and Plan
Summary
Back-up: Explanation of Increments
Outline

## Slide 12
New
center-stack
2nd NBI
Li granule injector
High-Z PFC diagnostics
Off-midplane 3D coils (NCC)
up to 1 MA plasma gun
Lower divertor cryo-pump
Upgraded CHI for ~0.5MA
LLD using bakeable cryo-baffle
DBS, PCI, or other intermediate-k
Divertor Prad
Snowflake
Run Weeks:
Five Year Facility Enhancement Plan (green – ongoing)
2015: Engineering design for high-Z tiles, Cryo-Pump, NCC, ECH
MGI disruption mitigation
4 coil AE antenna
HHFW limiter upgrade
Establish control of:
Rotation
High kq
Laser blow-off
Boronization
Enhanced MHD sensors
Neutron collimator
Charged fusion product
Upgraded halo sensors
Pulse-burst MPTS
18
10-12
16
ne
Integrated Scenarios
Core Science
Boundary Science
+ Particle Control
2015 | 2016 | 2017 | 2018 | 2019
Upgrade Outage
1.5  2 MA, 1s  5s
MAPP
42 ch MPTS
48 ch BES
MSE/LIF
FIReTIP
Major enhancements:
Base funding
+15% incremental
Fiscal Year:
1 MW ECH/EBW
12-16
High-Z tile row on lower OBD
dB diag. - incremental
0.5-1 MA CHI
qmin
LiTER
Upward
LiTER

## Slide 13
LITERs
First Year Boundary Physics Tools
Boronization, Lithium Evaporators, Granule Injector
Lithium Evaporator (LITERs)
Granule injector (GI) for ELM pacing
Rotating Impeller
Successfully tested
on EAST and DIII-D
Granules: Li, B4C, C
f ~ up to 500 Hz
dTMB Gas Cabinet
for safety
Boronization System
Granular Reservoir
• LITERs filing set up in high bay south of NSTX-U Test Cell
• Argon purge system being implemented for safety
• Multiple injection and glow made more uniform boronization.
• System is working very well. Third boronization complete. Also being used for He glow discharges.
• Remote control undergoing tests
• Stand complete
• Vacuum interlock requirements identified and implementation plan specified

## Slide 14
Enhanced Capability for PMI Research
Multi-Institutional Contributions
ORNL
Divertor Imaging
Spectrometer
Dual-band fast IR Camera
Multiple fast 2D visible and IR cameras with full divertor coverage
Li I
C II
LLNL, ORNL, UT-K
U. of Illinois, PPPL
LLNL
ORNL
Divertor fast eroding thermocouples
MAPP probe for between-shots surface analysis – Now taking data

## Slide 15
Microturbulence Diagnostics Being Enhanced
To measure ion to electron gyro-scale, magnetic fluctuations
Beam Emission Spectroscopy
for low k turbulence
48 chs being readied
Cross-Polarization Scattering for magnetic fluctuations being developed in collaboration with DIII-D and MAST
Low k
High k
UC Davis
UCLA
High-k scattering for ETG
Available for FY 17
BES-2D-Fiber
Assembly
U Wisconsin
4x1 subharmonic mixer array
Collection optics (Bay L)

## Slide 16
Successful PDR held in December
  Final drawings and installation issues nearly complete (FDR mid-Feb.)
  82% of raw materials on-site
Final design rated to 10 MW/m2 for 1s heat flux for 1000s of cycles
  Installation flexibility introduced to accommodate “as built” vessel tolerances
  Edge and access-way chamfers introduced to reduce heat-flux peaking
Design “lesson’s learned” already informing cryo-pump PFC design
  Geometric flexibility emphasized to avoid stress-limited design
  Tight tolerancing in sub-structure emphasized to avoid time-intensive installation tasks
High-Z Tile Design Nearly Complete
(See M. Jaworski’s PAC talk for more detail - plan to be ready by the 2016 outage)
Surface heat flux
Temperature

## Slide 17
Disruption Mitigation System for NSTX-U Massive gas injection system at multiple poloidal positions
  - Massive gas injector system at multi
  poloidal location with identical injection set-up
  - Compact power supply proto-type tested at UW
  - A new double solenoid MGI design (zero net J x B
  torque) based on the ORNL ITER MGI design
NSTX-U MGI Valve
• Conceptual Design Review of MGI system was held on October 16. Recommended changes were incorporated into the power system hardware.
• All the MGI components including MGI valves were delivered to PPPL from U. Washington.
• Preparation are being made to commission the MGI system on NSTX-U this year.
  MGI also tested on the U. Washington test stand with magnetic field
Magnets
Magnets
MGI
Valve
U. Washington

## Slide 18
Solenoid-free start-up in support of ST-FNSF
NSTX-U CHI configuration permits ~ 400 kA level start-up
• CHI will start with the present 2 kV capability then enhanced to higher voltage as needed.
• Control system updates for the CHI cap bank have been completed, and the system is ready for remote testing.
• The CHI control room procedure has been updated.
• Inj. Flux in NSTX-U is about 2.5 times higher than in NSTX
• NSTX-U coil insulation greatly enhanced for higher voltage ~ 3 kV operation
CHI Start-Up in NSTX-U
U. Washington
An ST-FNSF like CHI configuration will undergo plasma tests on QUEST after FY 2016 NSTX-U operation
CHI electrodes installed in QUEST, CHI power supply and gas injection system fabricated at U-Washington
QUEST CHI Experiment to test high-Z electrode operation

## Slide 19
HHFW system will be ready for operation in March
All sources are ready to start antenna conditioning
New Compliant Antenna Feeds
Allow HHFW antenna feedthroughs to tolerate 2 MA disruptions
- Prototype compliant feeds tested to 46 kV in the RF test-stand. Benefit of back-plate grounding for arc prevention found.
- RF diagnostics also installed.
• All sources will be ready to support HHFW operation in March.
Transmission lines installed & tuned.
Antennas were re-installed with the new feeds and back-plate grounding
Additional ground installed

## Slide 20
Enhanced FIDA will measure NBI distribution function
For NBI fast ion transport and current drive physics
Vertical
Tangential
Fast Ion D-Alpha Diagnostics
FIDA Views
• Both vertical (perpendicular) and new tangential (parallel) FIDA systems are ready.
• Both FIDA systems have 10 ms, 5 cm, ≈ 10 keV resolutions.
HHFW
Antennas
CHI Gap
Center-Stack
sFLIP
TAE antennas
FY 2016 - 2017 Energetic Particle Conceptual Design and Diagnostic Upgrade
  SS-NPA installed but investigating pick-up problem.
  sFLIP is installed for lost ion measurements
  Active 2 X 2 TAE antennas installed. Initially passive spectroscopy then active excitation at few kW level.
  Proto-type charged fusion product (CFP) profile diagnostic to be installed this year.
  8+8 reflectometry array available for AEs.
UCI
FIU
UCLA

## Slide 21
Facility Operations Status and Plan
On-Going Facility Enhancement Status and Plan
Longer Term Facility Enhancement Status and Plan
Summary
Back-up: Explanation of Increments
Outline

## Slide 22
New
center-stack
2nd NBI
Li granule injector
High-Z PFC diagnostics
Off-midplane 3D coils (NCC)
up to 1 MA plasma gun
Lower divertor cryo-pump
Upgraded CHI for ~0.5MA
LLD using bakeable cryo-baffle
DBS, PCI, or other intermediate-k
Divertor Prad
Snowflake
Run Weeks:
Five Year Facility Enhancement Plan (green – ongoing)
2015: Engineering design for high-Z tiles, Cryo-Pump, NCC, ECH
MGI disruption mitigation
4 coil AE antenna
HHFW limiter upgrade
Establish control of:
Rotation
High kq
Laser blow-off
Boronization
Enhanced MHD sensors
Neutron collimator
Charged fusion product
Upgraded halo sensors
Pulse-burst MPTS
18
10-12
16
ne
Integrated Scenarios
Core Science
Boundary Science
+ Particle Control
2015 | 2016 | 2017 | 2018 | 2019
Upgrade Outage
1.5  2 MA, 1s  5s
MAPP
42 ch MPTS
48 ch BES
MSE/LIF
FIReTIP
Major enhancements:
Base funding
+15% incremental
Fiscal Year:
1 MW ECH/EBW
12-16
High-Z tile row on lower OBD
dB diag. - incremental
0.5-1 MA CHI
qmin
LiTER
Upward
LiTER

## Slide 23
Divertor Cryo-pump Design Activities Started
Physics Design Described at PAC 33 by J. Canik, ORNL
Cryo-ring
Transfer line layout
Initial in-vessel geometry has been laid out. MIT will design cryo-ring.
  Pump radius, throat dimensions taken from the modeling.
  Is a significant perturbation, requiring a rebuild of basically the entire lower outer divertor.
  High-Z tile research will contribute to the choice of PFCs (see M. Jaworski’s talk)
Specification in progress for the Liquid He refrigerator.
  Likely suitable model found
  Location in room adjacent to NSTX-U has been identified.
Ex-vessel liquid He plumping and transfer Dewar is under design.

## Slide 24: NSTX-U boundary / PFC plan: add divertor cryo-pump, transition to high-Z wall, study flowing liquid metal PFCs
5yr goal: Integrate high E and T with 100% non-inductive
10yr goal: Assess compatibility with high-Z & liquid lithium PFCs
Cryo + full lower outboard high-Z divertor
Lower OBD
high-Z row of tiles
B+C BN
Li High-Z
2016
2017-18
2018-19
Heatable high-Z PFCs for liquid Li (including pre-filled)
Cryo + high-Z FW
and OBD
+ liquid Li divertor (LLD)
2020-21
High-Z tile row
Up + downward Li evaporator, possible pre-filled Li tiles (FY18)
High-Z tile row
All high-Z FW +
divertors
+ flowing LLD
module
2022-23
or
Flowing Li module (Concept, location, size TBD)
Cryo-pump
Downward Li evaporator +
Li granule injector

## Slide 25: High Z, Liquid Lithium, and Cryo-Pump Enhancements
We are assessing the viability of supporting two separate enhancements: (1) Cryo-pump and (2) heatable high-Z PFC with liquid Li capabilty:
• Heatable high-Z PFCs with liquid lithium divertor capability ~ $ 6-7 M
• Cryo-pump system ~ $ 6- 7 M
Heatable high-Z PFCs for liquid Li (including pre-filled)
Cryo-pump
Also as a part of facility reliability enhancement, a cryo-plant (helium refrigerator) upgrade is envisioned (~ $2.5M). The existing helium refrigerator is 35 years old and it if fails may cause loss of NSTX-U plasma operation in a given year. It is also located far from NSTX-U which causes more than 50% heat loss. The existing system could become a back-up refrigerator and support other cryogenic needs at PPPL.

## Slide 26
TFTR legacy liquid helium refrigerator
A new efficient 400 W liquid helium (L-He) refrigerator to minimize down time risk and reduce operating cost
• 35 years old for NBI #1 and 2 operating at near capacity
• If a failure occurs, the risk is estimated to be 6 months to 1 year of down-time.
• Back up L-He on NSTX-U without causing down time or as a site credit for future projects if needed.
Proposed 400 W L-He refrigerator ~ $2.5M
500 feet of supply and return piping
• Located near NSTX-U, accommodates all envisioned loads (NBIs and cryo-pump) by benefit of less piping and heat loss.
• The unit would reuse power and space previously used for a previous 225 Watt refrigerator.
• The existing NBI controls PLC and operations staff can operate this system with only minor adaptations.
• The existing NBI tank Farm and liquid Nitrogen systems would support this 400 Watt refrigerator.
NSTX-U
Former TFTR Test Cell

## Slide 27
Flexible Mid-Plane Feedback Coils for MHD Studoes
NCC will greatly enhance MHD physics studies and control
Base – Engineering design work on NCC to be performed in 2016 – 2017 to develop reliable cost and schedule.
Full toroidal NCC array (2 x 12)
Partial toroidal NCC array (2 x 6)
Full NCC
Existing
RWM
coils
Partial NCC
• 6-channel Switching Power Amplifier (SPA) powers independent currents in existing EFC/RWM Coils.
• NCC (a facility enhancement) can provide various NTV, RMP, RWM, and EF selectivity with flexibility of field spectrum (n ≤ 6 for full and n≤ 3 for partial)
Columbia U
General Atomics

## Slide 28: NCC Lorentz and Thermal Stress Analysis
NCC = Non-axisymmetric Control Coil
NCC Coils Design Activity Made Significant Progress
NCC Physics Design Presented by J-K Park at PAC 33
• Selected candidate conductors and test sample received for R&D.
• The R&D selection criteria include thermal capability, manufacturability, impact on interfacing objects, fabrication lead time and cost.
• Helium cooling system or no direct cooling options will be quantified.
• Cost and schedule will be prepared as part of the CDR which is targeted for May, 2016.
2 x 12
Coil
Lead
Tile
PP
3 kA,0.1 MW/m2 Plasma Heating,5s pulse,1200 s reprate
Thermal Analysis
End of Last Pulse Temp (8 hours)
With Lead Clamp, 50 C Heat-up, 3kA+ Background Field

## Slide 29
CHI can form a 200-400 kA seed plasma, but it is too cold for HHFW absorption.
Use of ECH can “bridge the Te gap” to where HHFW and then NB current drive can support the ramp and sustain the current – crucial for OH solenoid-free compact STs - Talk by F. Poli at this PAC.
  Good first pass absorption predicted.
Goal of first ECH power in 2019 run with 15% incremental funding.
28 GHz ECH System Design Progressing Well
Develop engineering design and cost/schedule this year
28 GHz Gyrotron Development
• 2nd generation 1.5 MW 28/35 GHz gyroton being developed at Tsukuba University. (See back-up slide)
• The gyrotron is being constructed. Will be tested this summer.
NSTX-U
Test Cell
Power Supply Room
Gyroton room
28 GHz Gyrotron Room
28 GHz 1 MW Tube by Tsukuba
Gyrotron will be located in the TFTR basement. Stray magnetic fields was measured to be negligible

## Slide 30
1) Supporting our 18 run-week milestone
2) Improving reliability of critical systems that support operation
3) Supporting our collaborator needs to install their hardware
4) Any additional funds available will be used to support the major enhancements (Divertor Cryo-Pump and High-Z)
Highest Priority for Incremental Funding
See back-up slide for more detail

## Slide 31
• Research preparation progressing well. Team is vigorously preparing diagnostics and research tools for the first year of plasma operations.
• Research operation started on December 18, 2015. Very good progress on the plasma control system. Routine H-mode obtained shortly after the second boronization.
• After two week maintenance period, the plasma operation is restarting this week with all NBI and new capabilities and diagnostics.
• Engineering design work continuing for the major facility enhancements: divertor cryo-pump, high-Z tiles, ECH, and NCC.
• Considering two enhancements: the divertor cryo-pump in parallel with the heatable high-Z PFCs with LL divertor capability.
• 400 W L-He refrigerator is also being considered for risk reduction.
Summary of Facility and Diagnostics
Research operations successfully started

## Slide 32
Back-up Slides

## Slide 33: NSTX-U Developing Tools for Measuring Core and Boundary Radiation
Midplane Bolometer
CDR Nov. 2015
M. Reinke, ORNL
plasma
testing 32-ch system for viewing lower x-pt late in FY16 campaign
thin Pt foil, heated by radiation, imaged by IR camera
Prototype IR video bolometer (IRVB) with NIFS and DIFFER
Redesign and expand bolometer diagnostics to support FY17 operations
  16 ch of lower divertor viewing for boundary radation
  24 ch tangential midplane core radiation