## Slide 1: NSTX-U Project / Facility Status
Masa Ono and Jon Menard
NSTX-U FY 2016 Q2 Review Meeting
May 3, 2016

## Slide 2
Facility Operations Status and Plan
On-Going Facility Enhancement Status and Plan
Summary
Outline

## Slide 3: Latest run plan schedule for 2016 ~ 7.2 run week to date, goal is to operate 18 run weeks
Want as much data as possible for IAEA synopses/meeting, APS-2016
December 2015: 0.4 run weeks (XMP)
January 2016 (3 weeks): 2 run weeks (H-mode), PAC-37
Two week maintenance: NBI T-line repair, Argon purge system, LITER, Diagnostics
• February – March (4 weeks): 2.4 run weeks (routine H-mode)
Two week maintenance: BN piece recovery, NBI Auto/transformer/T-line repair, LGI, MGI, Diagnostics
March – April: (3 weeks) 2.4 run weeks (high power H-mode)
Three week maintenance: BPM, NBI LHe refrigeration regeneration & leak repair, LGI, MGI, Diagnostics
May – August - 10.8 run weeks to complete FY16 run with extended run days
August: Start outage
Outage
Completed Plasma Operations
Planned Plasma Operations

## Slide 4: LHe Refrigerator Cold Box Leak Leaks were found and repaired along with a similar piece
The LHe Refrigerator Cold Box leak was determined to be in a piece of pipe used as a thermocouple diode well. The temperature measurement at this location was no longer in service because those types of diodes are obsolete. The pipe was cut off and capped. The cap was seal welded and QC inspected.
A second similar well was also cut out and capped and welded as a precaution.
Another very small leak in another location was discovered and likewise capped and welded.
After leak checking, the Cold Box shell was replaced and vacuum restored. The LHe refrigerator was put back into service and initial operations indicate that the unit is back to full capacity. BL 1 & 2 cool down complete and operations started.
Interior of the LHe Refrigerator Cold Box
Thermocouple diode well

## Slide 5
Cryogenics repairs completed. Restart of LHe refrigerator complete. Cooldown of BLs in progress for operations yesterday (Monday, May 2, 2016) and starting up NBI operation today.
Neutral Beam #2
  N2A Source had operated to 86 kV. (Hipot to 90 kV completed.)
  N2B Source had operated to 80 kV. (High voltage investigation completed.)
  N2C Source had operated to 80 kV.
Neutral Beam #1
  N1A Source had operated to 76 kV. (New source conditioning still in progress)
  N1B Source had operated to 70 kV.
  N1C Source had operated to 90 kV.
RF Systems
  HHFW #1-4 Recovery CAP completed. Ready to start antenna conditioning.
  HHFW #5-6 CAP completed. Awaiting protective relay installation (imminent)
  RF awaiting AC Power repairs in switchyard (completion imminent)
Heating System Operations
NBI system should be approaching full performance

## Slide 6: We are using dTMB now for PFC Conditioning, and Will Switch to Lithium in a Few Weeks
We have been boronizing the ATJ graphite PFC at a rate of 1 bottle per week.
  1 bottle = 10 grams dTMB in a Helium background was the standard quanta of boronization in NSTX.
  Started NSTX-U run with a full bottle boronization each Sunday, found conditions were degrading by the end of the week.
  Switched to 1/5 bottle boronization late 2nd shift each evening.
    Provides more consistent conditions day-to-day.
We are working towards using lithium evaporators during this run.
  Cables for motor control drives are among pacing items.
  Still need to complete procedure revisions, do ACC reviews.
  Installing an Ar Purge System (APS) to fill the vessel with Ar in the event of a catastrophic vent during lithium evaporation.
  Target date for lithium use is early June.

## Slide 7: We are Working to Deploy/Commission Additional Systems in the Remaining Duration of the Run
Langmuir probe electronics
Massive Gas Injector (UW) – disruption mitigation
Lithium Granule Injector – ELM pacing
SAMI (Univ. York) – EBW physics, field pitch at edge (next slide)
High Harmonic Fast Wave Heating & Current Drive
  AC power problem on sources delayed operation.
  Sources 1-4 are nearing operation, 5 & 6 are ~1-1.5 months out.
Infrared Video Bolometer (ORNL, NIFS)
Divertor SPRED (LLNL)
Fusion Products Detector (FIU)
CHI Instrumentation & Gas Feeds (UW)
TF Coil Bending Stress Instrumentation for 0.8 T Operation
  Use existing instrumentation chassis to confirm that the outer leg bending is consistent with predictions from the mechanical analysis branch.

## Slide 8: Synthetic Aperture Microwave Imaging (SAMI) diagnostic now calibrated and operating on NSTX-U
SAMI RF front-end and antenna array installed on NSTX-U
First used successfully on MAST
Image can be focused post shot
Measures EBW coupling efficiency, plasma turbulence, and pitch angle of magnetic field in the plasma edge with high radial resolution
SAMI EBW Emission Data from MAST
SAMI* measures 10-35.5 GHz emission using 16 local oscillators and an array of antennas to image over a large field of view [Collaboration with Univ of York, Durham Univ & CCFE in UK]
Two probing beams used for 2-D Doppler Back Scattering
Emission data digitized at 250 mega samples/sec

## Slide 9: NSTX-U device performance progression
1st year: Limit forces to ½ way between NSTX and NSTX-U, and ½ of the design-point heating of any coil
  Presently operating at BT ~ 0.65T
  Increase to BT ~ 0.8T after completing engineering analysis
2nd year goal: Full field and current, coil heating to ¾ of limit
3rd year goal: Full capability
Parameter | NSTX (Max.) | Year 1 NSTX-U Operations | Year 2 NSTX-U Operations | Year 3 NSTX-U Operations | NSTX-U Ultimate Goal
IP [MA] | 1.2 | ~1.6 | 2.0 | 2.0 | 2.0
BT [T] | 0.55 | ~0.8 (0.65) | 1.0 | 1.0 | 1.0
Allowed TF I2t [MA2s] | 7.3 | 80 | 120 | 160 | 160
IP Flat-Top at max. allowed I2t, IP, and BT [s] | ~0.4 | ~3.5 | ~3 | 5 | 5

## Slide 10: NSTX Upgrade Lead Extension Qualifications Confirmed by Calculations and Cyclic Fatigue Test
INSTRON Cyclic Tester and Test Fixture
TF Inner to Outer Connection Details
• The CuCrZr TF lead extensions and all the related parts associated with the connections between the inner and outer TF conductors are qualified to be acceptable for up to 300 pulses at BT = 0.8 Tesla.
• It successfully passed the cyclic fatigue test to the .8 T level for 6000 cycles (20 * 300 cycles expected in this run period at 0.8T).
• The full 1.0Tesla level to 400,000 cycles is being conducted this week.
• Components are being inspected, analyzed tested and replaced as needed to qualify operation at full performance after the shut-down starting in August of 2016.

## Slide 11: Longer Term Plan Supports Operations in FY-17
Present run projected to run through mid-August
Maintenance period shown mid-August thru December 2016
  OH Water Heater
  Passive Plate Replacement
  TF Coil Maintenance and Partial Parts Replacement
  High-Z tiles
  Diagnostic work including high-k, FIReTIP, bolometer, laser blow-off
Diagnostic calibrations, bakeout, leak checking and coil testing through March 2017
Operations April thru September: 5.5 months for 16 run weeks.
TF Lead Extensions
High-Z Tiles
Bakeout
Passive Plate
Diag Cal.
Diag Cal.
ISTP
Diag. Install
FY-17 Run
FY-16 Run
OH Water Heater
Pump
Vent & Purge

## Slide 12
Facility Operations Status and Plan
On-Going Facility Enhancement Status and Plan
Summary
Outline

## Slide 13
New
center-stack
2nd NBI
Li granule injector
High-Z PFC diagnostics
Off-midplane 3D coils (NCC)
up to 1 MA plasma gun
Lower divertor cryo-pump
Upgraded CHI for ~0.5MA
Graphite CHI/Lower Bullnose
DBS, PCI, or other intermediate-k
Snowflake
Run Weeks:
Five Year Facility Enhancement Plan (green – ongoing)
Incremental enables 5 year plan enhancements including NCC, ECH
MGI disruption mitigation
4 coil AE antenna
HHFW limiter upgrade
Establish control of:
Rotation
High kq
Laser blow-off
Boronization
Enhanced MHD sensors
Neutron collimator
Charged fusion product
sß
Upgraded halo sensors
Pulse-burst MPTS
18
10-12
16
ne
Integrated Scenarios
Core Science
Boundary Science
+ Particle Control
2015 | 2016 | 2017 | 2018 | 2019
Upgrade Outage
1.5  2 MA, 1s  5s
MAPP
42 ch MPTS
48 ch BES
MSE/LIF
FIReTIP
Major enhancements:
Base funding
incremental funding
Fiscal Year:
1 MW ECH/EBW
12-16
High-Z tile row on lower OBD
CPS dB diag.
0.5-1 MA CHI
qmin
LiTER
Upward
LiTER
APD-based GPI
Scanning MLP
XICS
Divertor Prad
Resistive
Bolometer

## Slide 14
New
center-stack
2nd NBI
Li granule injector
High-Z PFC diagnostics
Off-midplane 3D coils (NCC)
up to 1 MA plasma gun
Lower divertor cryo-pump
Upgraded CHI for ~0.5MA
Graphite CHI/Lower Bullnose
DBS, PCI, or other intermediate-k
Snowflake
Run Weeks:
Five Year Facility Enhancement Plan (green – ongoing)
Incremental enables 5 year plan enhancements including NCC, ECH
MGI disruption mitigation
4 coil AE antenna
HHFW limiter upgrade
Establish control of:
Rotation
High kq
Laser blow-off
Boronization
Enhanced MHD sensors
Neutron collimator
Charged fusion product
sß
Upgraded halo sensors
Pulse-burst MPTS
18
10-12
16
ne
Integrated Scenarios
Core Science
Boundary Science
+ Particle Control
2015 | 2016 | 2017 | 2018 | 2019
Upgrade Outage
1.5  2 MA, 1s  5s
MAPP
42 ch MPTS
48 ch BES
MSE/LIF
FIReTIP
Major enhancements:
Base funding
incremental funding
Fiscal Year:
1 MW ECH/EBW
12-16
High-Z tile row on lower OBD
CPS dB diag.
0.5-1 MA CHI
qmin
LiTER
Upward
LiTER
APD-based GPI
Scanning MLP
XICS
Divertor Prad
Resistive
Bolometer

## Slide 15
LITERs
First Year Boundary Physics Tools
Boronization, Lithium Evaporators, Granule Injector
Lithium Evaporator (LITERs)
Granule injector (GI) for ELM pacing
Rotating Impeller
Successfully tested
on EAST and DIII-D
Granules: Li, B4C, C
f ~ up to 500 Hz
Boronization System
Granular Reservoir
• LITERs filing set up in high bay south of NSTX-U Test Cell.
• Argon purge system implemented for Li safety, used for the quick argon vent.
• Expected to be operational in June.
• Multiple injection and glow made more uniform boronization.
• System is working very well. Multiple # of boronization including daily ones performed. Also being used for He glow discharges.
• Undergoing commissioning and initial injection during the next plasma operation.
GI installed on NSTX-U

## Slide 16
Successful FDR held in February
  82% of raw materials on-site
  Fabrication RFQ being prepared
  Schedule to be delivered in September in time for the installation in NSTX-U
Final design rated to 10 MW/m2 for 1s heat flux for 1000s of cycles
High-Z Tile to be installed for FY 2017 run
Design to replace a row of the graphite tiles in lower outer divertor
Surface heat flux
Temperature
  Installation flexibility introduced to accommodate “as built” vessel tolerances
  Edge and access-way chamfers introduced to reduce heat-flux peaking
Test cut from one of the castellations performed

## Slide 17
Physics design completed in collaboration with ORNL.
  Defined the geometry, plenum sizes, ability to pump various geometries.
Conceptual design process has been initiated:
  Draft GRD has been formulated.
  Initial designer sketches of in-vessel implementation completed.
  Two types of PFCs being investigated.
  CHI/lower bullnose section may be pursued as separate job as it may be enhanced for high Z and flowing Li in the future.
  Goal is to to have the system ready for installation in the 2018-2019 outage under base funding.
Need 0.8 mTorr or better
Lower Divertor Cryo-pump to Provide Pumping over a Wide Range of Divertor Geometries and Core Densities
350C
bake
A
Passive
bake
350C
bake
B
CHI/ lower bullnose
Baffle diagonal / upper bullnose
Baffle top / horizontal
tiles
High-Z, high q
Graphite
High-Z, low q
PFC type:
Two PFC Options for CDR
Or

## Slide 18
Divertor Cryo-pump Design Activities Started
Design also includes appropriate PFCs and L-He refrigerator
Cryo-ring
Transfer line layout
Initial in-vessel geometry has been laid out. MIT will design cryo-ring.
  Pump radius, throat dimensions taken from the modeling.
  The entire lower outer divertor region to be reduild.
• Cryo-baffle design to be finalized at CDR.
  Diagnostic access and cryo-ring maintainability are major design consideration.
  Two PFC options (Graphite or high Z) are pursued for CDR.
• A 400W liquid He refrigerator considered to reduce NBI operational risk and operational cost savings.
  A room adjacent to NSTX-U has been identified for energy efficient location with utilities already available.
  Replaces the outdated TFTR-era L-He refrigerator reducing risks to the NBI operations.

## Slide 19
TFTR legacy liquid helium refrigerator
A new efficient 400 W liquid helium (L-He) refrigerator to minimize down time risk and reduce operating cost
• 36 years old 800 W refrigerator for NBI #1 and 2 operating at near capacity due to long piping causes significant heat loss – also quite expensive to operate and maintain.
• If a cold box failure occurs, the repair will require reverse engineering and loss of several months will severely impact NSTX-U operations.
Proposed 400 W L-He refrigerator ~ $2.5M
500 feet of supply and return piping
• To be located in the Cryogenics Compressor Room near NSTX-U, accommodates all envisioned loads by benefit of greatly reduced piping and heat loss (x 3-4).
• The unit would reuse power and space previously used for a 225 Watt refrigerator with all the utilities and compressors available.
• Benefit:
  Remove down time risk
  Increase available L-He for NSTX-U including NBI and Divertor Cryo-pump.
  Reduced operating and maintenance cost
NSTX-U
Former TFTR Test Cell

## Slide 20
Implement Divertor Cryo-Pump with base funding
Exploring various options to minimize cost for timely completion
Transfer line layout
Schedule for Cryo-pump and PFCs:
  Start formal design collaboration with MIT in Feb 2016.
  CDR – planned in July 2016 with cost and schedule developed (Notable Outcome)
  PDR – planned in Nov. 2016
  FDR – planned in March 2017
  Complete fabrication of in-vessel components – May 2018
  Complete installation of in-vessel and ex-vessel components – Feb. 2019
Cryogenic vacuum feedthrough concept.
Cryopump with redesigned divertor support structures
Schedule for L-He refrigerator:
  PDR in June 2016 with external reviewers
  Start procurement – Sep. 2016.
  Start installation – June 2017
  Commission – Oct. 2017

## Slide 21
New
center-stack
2nd NBI
Li granule injector
High-Z PFC diagnostics
Off-midplane 3D coils (NCC)
up to 1 MA plasma gun
Lower divertor cryo-pump
Upgraded CHI for ~0.5MA
Graphite CHI/Lower Bullnose
DBS, PCI, or other intermediate-k
Snowflake
Run Weeks:
Five Year Facility Enhancement Plan (green – ongoing)
Incremental enables 5 year plan enhancements including NCC, ECH
MGI disruption mitigation
4 coil AE antenna
HHFW limiter upgrade
Establish control of:
Rotation
High kq
Laser blow-off
Boronization
Enhanced MHD sensors
Neutron collimator
Charged fusion product
sß
Upgraded halo sensors
Pulse-burst MPTS
18
10-12
16
ne
Integrated Scenarios
Core Science
Boundary Science
+ Particle Control
2015 | 2016 | 2017 | 2018 | 2019
Upgrade Outage
1.5  2 MA, 1s  5s
MAPP
42 ch MPTS
48 ch BES
MSE/LIF
FIReTIP
Major enhancements:
Base funding
incremental funding
Fiscal Year:
1 MW ECH/EBW
12-16
High-Z tile row on lower OBD
CPS dB diag.
0.5-1 MA CHI
qmin
LiTER
Upward
LiTER
APD-based GPI
Scanning MLP
XICS
Divertor Prad
Resistive
Bolometer

## Slide 22
Enhanced FIDA will measure NBI distribution function
For NBI fast ion transport and current drive physics
Vertical
Tangential
Fast Ion D-Alpha Diagnostics
Taking data on NSTX-U
FIDA Views
• Both vertical (perpendicular) and new tangential (parallel) FIDA systems are ready.
• Both FIDA systems have 10 ms, 5 cm, ≈ 10 keV resolutions.
HHFW
Antennas
CHI Gap
Center-Stack
sFLIP
TAE antennas
FY 2016 - 2017 Energetic Particle Conceptual Design and Diagnostic Upgrade
  SS-NPA installed and taking data.
  sFLIP installed for lost ion measurements
  Active 2 X 2 TAE antennas installed. Initially passive spectroscopy then active excitation at few kW level.
  Proto-type charged fusion product (CFP) profile diagnostic is being prepared to be installed.
  8+8 reflectometry array available for AEs.
UCI
FIU
UCLA

## Slide 23
Disruption Mitigation System for NSTX-U Massive gas injection system at multiple poloidal positions
  - Massive gas injector system at multi
  poloidal location with identical injection set-up
  - Compact power supply proto-type tested at UW
  - A new double solenoid MGI design (zero net J x B
  torque) based on the ORNL ITER MGI design
NSTX-U MGI Valve
• Successful final Design Review of MGI system was held on February 18, 2016.
• All the MGI components were installed on NSTX-U and the control is being installed.
• Preliminary MGI test is planned in May, 2016 for the initial gas pulses into NSTX-U.
  MGI also tested on the U. Washington test stand with magnetic field
Magnets
Magnets
MGI
Valve
U. Washington

## Slide 24
• The commissioning phase is nearly complete and the plasma operation is now becoming routine and the availability increasing to ~ 90 % range.
• NBI and boronization are now supporting operations with routine H-mode access. NBI is approaching the full capability. HHFW is starting up. Will switch to lithium in June.
• Very good progress on the plasma control system, quickly achieving H-mode and high performance discharges comparable to the best NSTX plasma parameters.
• Plan to achieve parameters well beyond NSTX in the near future. In preparation for the 0.8 T operation later this year, a cyclic fatigue test was successfully conducted on the TF lead extension e-beam weld joint.
• A number of enhancements are being implemented to support the NSTX-U research plan. installation of high-Z tiles and complete conceptual engineering design for divertor cryo-pump, NCC, and ECH this year.
• Divertor cryo-pump, outer lower divertor PFCs will be implemented in the base plan.
Summary of Facility and Diagnostics
We are at 40% of the 18 run weeks

## Slide 25: Back-up Slides

## Slide 26
MIT PSFC Complements Well Existing NSTX-U Capabilities
Discussions Started on Various Diagnostic Implementations
X-ray Imaging Crystal Spectroscopy
MIT is developing a next generation, servo-driven, compact scanning MLP system
MIT will enhance NSTX-U GPI systems
Avalanche-PhotoDiode (APD)-based GPI

## Slide 27
Enhanced Capability for PMI Research
Multi-Institutional Contributions
ORNL
Divertor Imaging
Spectrometer
Dual-band fast IR Camera
Multiple fast 2D visible and IR cameras with full divertor coverage
Li I
C II
LLNL, ORNL, UT-K
U. of Illinois, PPPL
LLNL
ORNL
Divertor fast eroding thermocouples
MAPP probe for between-shots surface analysis – Now taking data

## Slide 28
Microturbulence Diagnostics Being Enhanced
To measure ion to electron gyro-scale, magnetic fluctuations
Beam Emission Spectroscopy
for low k turbulence
48 chs being readied
Cross-Polarization Scattering for magnetic fluctuations being developed in collaboration with DIII-D and MAST
Low k
High k
UC Davis
UCLA
High-k scattering for ETG
Available for FY 17
BES-2D-Fiber
Assembly
U Wisconsin
4x1 subharmonic mixer array
Collection optics (Bay L)
4–channel CPS system in 2017

## Slide 29
Flexible Mid-Plane Feedback Coils for MHD Studies
NCC will greatly enhance MHD physics studies and control
Base Budget – NCC engineering conceptual design work to develop reliable cost and schedule is being concluded to focus engineering resources to divertor cryo-pump design. CDR in May 2016.
Incremental Budget – Enables continued design, development, and installation of NCC.
Full toroidal NCC array (2 x 12)
Partial toroidal NCC array (2 x 6)
Full NCC
Existing
RWM
coils
Partial NCC
• 6-channel Switching Power Amplifier (SPA) powers independent currents in existing EFC/RWM Coils supporting experiments
• NCC (a facility enhancement) can provide various NTV, RMP, RWM, and EF selectivity with flexibility of field spectrum (n ≤ 6 for full and n≤ 3 for partial)
Columbia U
General Atomics

## Slide 30: NCC Lorentz and Thermal Stress Analysis
NCC = Non-axisymmetric Control Coil
NCC Coils Design Activity Made Significant Progress
Test area prepared to perform conductor sample R&D
• Candidate conductor for test sample received for R&D.
• R&D facility prepared and test being conducted.
• The R&D selection criteria include thermal capability, manufacturability, impact on interfacing objects, fabrication lead time and cost.
• Cost and schedule will be prepared as part of the CDR which is targeted for May, 2016.
2 x 12
Coil
Lead
Tile
PP
3 kA,0.1 MW/m2 Plasma Heating,5s pulse,1200 s reprate
Thermal Analysis
End of Last Pulse Temp (8 hours)
With Lead Clamp, 50 C Heat-up, 3kA+ Background Field

## Slide 31
New
center-stack
2nd NBI
Li granule injector
High-Z PFC diagnostics
Off-midplane 3D coils (NCC)
up to 1 MA plasma gun
Lower divertor cryo-pump
Upgraded CHI for ~0.5MA
Graphite CHI/Lower Bullnose
DBS, PCI, or other intermediate-k
Snowflake
Run Weeks:
Five Year Facility Enhancement Plan (green – ongoing)
Incremental enables 5 year plan enhancements including NCC, ECH
MGI disruption mitigation
4 coil AE antenna
HHFW limiter upgrade
Establish control of:
Rotation
High kq
Laser blow-off
Boronization
Enhanced MHD sensors
Neutron collimator
Charged fusion product
sß
Upgraded halo sensors
Pulse-burst MPTS
18
10-12
16
ne
Integrated Scenarios
Core Science
Boundary Science
+ Particle Control
2015 | 2016 | 2017 | 2018 | 2019
Upgrade Outage
1.5  2 MA, 1s  5s
MAPP
42 ch MPTS
48 ch BES
MSE/LIF
FIReTIP
Major enhancements:
Base funding
incremental funding
Fiscal Year:
1 MW ECH/EBW
12-16
High-Z tile row on lower OBD
CPS dB diag.
0.5-1 MA CHI
qmin
LiTER
Upward
LiTER
APD-based GPI
Scanning MLP
XICS
Divertor Prad
Resistive
Bolometer

## Slide 32
Solenoid-free start-up in support of ST-FNSF
NSTX-U CHI configuration permits ~ 400 kA level start-up
• The resistive voltage divider network was made functional, and many of the components related to a fast voltage monitoring system were installed.
• All of the connections of the gas lines to the CHI gas injection systems have been completed.
• Initial testing of the CHI system into a plasma load will begin in the near future.
• Inj. Flux in NSTX-U is about 2.5 times higher than in NSTX
• NSTX-U coil insulation greatly enhanced for higher voltage ~ 3 kV operation
CHI Start-Up in NSTX-U
U. Washington
An ST-FNSF like CHI configuration will undergo plasma tests on QUEST after FY 2016 NSTX-U operation (after July 2016).
All metal (high-Z) CHI electrodes provide valuable information for NSTX-U (presently graphite electrodes)
QUEST CHI Experiment to test high-Z electrode operation
U. Washington

## Slide 33
HHFW system will be ready for operation
Antenna plasma conditioning to start in May
New Compliant Antenna Feeds
Allow HHFW antenna feedthroughs to tolerate 2 MA disruptions
- Prototype compliant feeds tested to 46 kV in the RF test-stand. Benefit of back-plate grounding for arc prevention found.
- RF diagnostics also installed.
• All sources will be ready to support HHFW operation in May.
Transmission lines installed & tuned.
Antennas were re-installed with the new feeds and back-plate grounding
Additional ground installed

## Slide 34
CHI can form a 200-400 kA seed plasma, but it is too cold for HHFW absorption.
Use of ECH can “bridge the Te gap” to where HHFW and then NB current drive can support the ramp and sustain the current – crucial for OH solenoid-free compact STs
  Good first pass absorption predicted.
Goal of first ECH power in 2019 run with 15% incremental funding.
28 GHz ECH System Design Progressing Well
Complete conceptual design and cost/schedule this year
28 GHz Gyrotron Development
• 2nd generation 1.5 MW 28/35 GHz gyroton being developed at Tsukuba University. (See back-up slide). Power test to start in May.
• Incremental budget enables continued design and procurement of the ECH system.
NSTX-U
Test Cell
Power Supply Room
Gyroton room
28 GHz Gyrotron Room
28 GHz 1 MW Tube by Tsukuba
Gyrotron will be located in the TFTR basement. Stray magnetic fields was measured to be negligible